## Slide 1: Revamp the activities! General meeting– February 27, 2024
Università degli studi di Milano (umil)

## Slide 2: Agenda
Major changes in the amendment
  New partners
  WPs, Deliverables, Tasks
Revamping the activities
  WP4: Selecting core Cyber Range infrastructure
  WP3: Define CRSA models to support CR instancing and start thinking to training scenarios (CRST)
  WP5: Start thinking on integration (server installation) and pilots’ validation
Financial Information

## Slide 3: Amendment
Inclusion in the Consortium of two new partners
  Ethical AI (Cyprus) - Academic – 5 secondments (60 PM)
  Trinomial (Cyprus) – Non-academic – 5 secondments (60 PM)
Ethical AI will take responsability of WP3 «AERAS Models & Model-driven Cyber Range programmes creation»
Trinomial will take responsibility of WP5 «Platform Integration, Pilots, and Validation»
NO further extensions, project will end at M66

## Slide 4: WP3: AERAS Models & Model-driven Cyber Range programmes creation
D3.1 CRSA Models and CRSA-driven Cyber Range programme specification language M54 – Leader EAIN
D3.2 AERAS Models and CRSA-driven Cyber Range programme V1 M58 – Leader TRID
D3.3 AERAS Models and CRSA-driven Cyber Range programme V2 M66 – Leader EAIN
Task 3.1 CRSA language definition and tool support - M06-66: Leader: EAIN
Task 3.2 CRSA-driven Cyber Range program development - M09-66: Leader: TRID
Task 3.3 Adaptation of CRSA models to changes in threat landscape - M09-66: Leader: EAIN
Task 3.4 Hybrid Cyber Security Risk Analysis Models - M09-66: Leader: TRID

## Slide 5: WP4 Key Components Development
D4.1 AERAS Cyber Range Tools - V1 M54 – Leader CUT
D4.2 AERAS Monitoring, Assessment and Adaptation mechanisms - V1 M54 – Leader UMIL
D4.3 AERAS Cyber Range Tools – V2 M66 – Leader AEGIS
D4.4 AERAS Monitoring, Assessment and Adaptation mechanisms – V2 M66 – Leader UMIL
Task 4.1 Cyber Range & Simulation tools - M09-66: Leader: CUT
Task 4.2 Visualisation tools - M09-66: Leader: AEGIS
Task 4.3 Real time trainee assessment & Cyber Range programmes Evaluation - M09-66: Leader: UMIL
Task 4.4 Real time Cyber Security Assurance Models, and CSLA monitoring - M09-66: Leader: CUT
Task 4.5 CRST programmes adaptation mechanisms M09-66: Leader: UMIL

## Slide 6: WP5 Platform Integration, Pilots, and Validation
D5.1 Initial Prototype of integrated AERAS platform M56 – Leader TRID
D5.2 AERAS Evaluation Framework and Pilot Set Up Guidelines M56 – Leader UMIL
D5.3 AERAS initial prototype pilot validation report M60 – Leader UPAT
D5.4 Final Prototype of integrated AERAS platform M66 – Leader TRID
D5.5 AERAS final prototype pilot validation report M66 – Leader PAGNI
D5.6 Final AERAS evaluation report M66 – Leader UMIL
Task 5.1 Integration of tools and components and testing of integrated AERAS platform - M24-62: Leader: TRID
Task 5.2 Pilots Evaluation Methodology & Setup - M24-62: Leader: UMIL
Task 5.3 Pilot validation - Smart Hospital Environment - M28-66: Leader: UPAT
Task 5.4 Pilot validation - Healthcare Authority - M28-66: Leader: PAGNI

## Slide 7: WP4 core architecture
Proposal of using Kypo Standalone version as core Cyber Range infrastructure (open ti discussion)
  Investigate how we can extend it with AERAS specific components and models
  Study Kypo’s endpoints to manage the infrastructure from AERAS interface
GIT Repo
CRSA-CRST
Submodels Extractor
Visualization
Performance Evaluator
Cyber System Monitor
Cyber System Risk Evaluator
Programme Evaluator
AERAS INFRASTRUCTURE

## Slide 8: WP4 upcoming Deliverables
D4.1 AERAS Cyber Range Tools - V1 M54 Focus on:
  Selection of the core architecture
  Study on KYPO endpoints and how to access them to instance the trainign environments
  Definition of the main communication flows
  Definition of the main data exchange among modules
D4.2 AERAS Monitoring, Assessment and Adaptation mechanisms - V1 M54 Focus on
  Definiton of the main properties on trainees’ perfomrmance and cyber-system specific characteristics
  Definition of the methodologies used to monitor
  Use of CRSA models in the monitoring activities

## Slide 9: WP3 Core models
AERAS models:
  CRSA models specify potential cyber-attacks, the security mechanisms used against them, and the methods for assessing their effectiveness
  CRST models define training scenarios, directly connected with the security threats they want to focus on, specifying the type of training we want to execute
    Questionnaire-based: questions, possible answers, type of questions…
    Interactive using cyber range: type of VMs to deploy, virtual topology, type of exercise to request to trainees
    Mixed: questionnaires and VMs
AERAS modules and Kypo based on models to deploy the training activities
The Submodels Extractor should extract from CRSA and CRST specific for a training activity the specific submodel needed for a specific module to run

## Slide 10: WP3 upcoming deliverables
D3.1 CRSA Models and CRSA-driven Cyber Range programme specification language M54 Focus on
  Definition of CRSA structure
  Definition of CRST structure
  Specification of submodels w.r.t. AERAS and KYPO modules

## Slide 11: WP5 Integration and evaluation
Installation of a first testing environment
  Based on Openstack (to be instaleld and configured)
  Running a Kypo instance
A server at UMIL is available for testing purposes
Definition of the base evaluation techniques for the pilots

## Slide 12: WP5 Upcoming deliverables
D5.1 Initial Prototype of integrated AERAS platform M56 Focus on
  Report on the first testing installation to be then replicated in Pilots’ premises
  Description of first installation steps
D5.2 AERAS Evaluation Framework and Pilot Set Up Guidelines M56 – Leader UMIL
  Defintion of the set of KPIs, criteria and methodology to evaluate the AERAS platform.
  Provide guidelines and documentation to support the piloting phase

## Slide 13: Financial information
Total Budget: 1.435.200,00 €
Paid by EC (85%): 1.219.920,00 €