## Slide 1: Amendment Confirmation General meeting– December 5th, 2023
Università degli studi di Milano (umil)

## Slide 2: Agenda
Project extension
Secondments reshuffling
WPs reshuffling
Milestones Update

## Slide 3: Project extension
PO granted us a 6-month extension
New end date: M72 – 30 November 2025
We are now at M49
All the remaining secondments, WPs and deliverables will be updated accordingly

## Slide 4: Secondments reshuffling: STATUS
3 partners will complete the expected secondments
  CUT
  AEGIS
  UPAT
3 partners with partial commitment
  UMIL
  STS-CY
  PAGNI
1 partner with no secondment
  TSI

## Slide 5: Secondments reshuffling: proposed solution
Inclusion in the Consortium of two new partners
  Ethical AI (Cyprus) - Academic – 5 secondments (60 PM)
  Trinomial (Cyprus) – Non-academic – 5 secondments (60 PM)
CUT will committ 12 an additional secondment (12 PM)
Exchange of PMs
  12 PM from UMIL to CUT
  12 PM from UMIL to Ethical AI
  48 PM from TSI to Ethical AI
  12 PM from PAGNI to Trinomial
  48 PM from STS-CY to Trinomial
TSI will leave the Consortium

## Slide 6: Secondments reshuffling: UPDATED BUDGET
new BUDGET |  |  |  |  |  |  |  |  | 
PARTNER | NO. SECONDMENT MONTHS | COSTS FOR SECONDED STAFF MEMBERS |  | RESEARCH, TRAINING AND NETWORKING COSTS |  | MANAGEMENT AND INDIRECT COSTS |  | TOTAL COSTS | DIFF
 |  | COST PER UNIT | TOTAL | COST PER UNIT | TOTAL | COST PER UNIT | TOTAL |  | 
UMIL | 24 | 2.100,00 € | 50.400,00 € | 1.800,00 € | 43.200,00 € | 700,00 € | 16.800,00 € | 110.400,00 € | -110.400,00 €
TSI | 0 | 2.100,00 € | 0,00 € | 1.800,00 € | 0,00 € | 700,00 € | 0,00 € | 0,00 € | -220.800,00 €
CUT | 60 | 2.100,00 € | 126.000,00 € | 1.800,00 € | 108.000,00 € | 700,00 € | 42.000,00 € | 276.000,00 € | 55.200,00 €
STS-CY | 12 | 2.100,00 € | 25.200,00 € | 1.800,00 € | 21.600,00 € | 700,00 € | 8.400,00 € | 55.200,00 € | -220.800,00 €
AEGIS | 24 | 2.100,00 € | 50.400,00 € | 1.800,00 € | 43.200,00 € | 700,00 € | 16.800,00 € | 110.400,00 € | 0,00 €
PAGNI | 36 | 2.100,00 € | 75.600,00 € | 1.800,00 € | 64.800,00 € | 700,00 € | 25.200,00 € | 165.600,00 € | -55.200,00 €
UPAT | 36 | 2.100,00 € | 75.600,00 € | 1.800,00 € | 64.800,00 € | 700,00 € | 25.200,00 € | 165.600,00 € | 0,00 €
TRI | 60 | 2.100,00 € | 126.000,00 € | 1.800,00 € | 108.000,00 € | 700,00 € | 42.000,00 € | 276.000,00 € | 276.000,00 €
ETH | 60 | 2.100,00 € | 126.000,00 € | 1.800,00 € | 108.000,00 € | 700,00 € | 42.000,00 € | 276.000,00 € | 276.000,00 €
TOTAL | 312 |  | 655.200,00 € |  | 561.600,00 € |  | 218.400,00 € | 1.435.200,00 € | 0,00 €
TO BE RETURNED TO UMIL
TO BE SENT BY UMIL
Then,
First,

## Slide 7: Secondments reshuffling: organization
The focus will be on pilots’ development and course development
All the secondments of new partners will happen in PAGNI and UPAT
  Ethical AI to PAGNI (ESR4-5-6-7-8)
  Trinomial to UPAT (ESR14-15-16-18-23)
UPAT (ESR26) will second to AEGIS instead of STS-CY (confirmed?)
UMIL (ESR1) will second to Trinomial
CUT (ESR3) will second to AEGIS and twice to PAGNI (confirmed?)

## Slide 8: WP3 reshuffling
Ethical AI will take responsability of WP3 «AERAS Models & Model-driven Cyber Range programmes creation»
Extended until M66
D3.1 CRSA Models and CRSA-driven Cyber Range programme specification language extended to M52 – Leader ETH
D3.2 AERAS Models and CRSA-driven Cyber Range programme V1 extended to M58 – Leader TRI
D3.3 AERAS Models and CRSA-driven Cyber Range programme V2 extended to M66 – Leader ETH

## Slide 9: WP4 reshuffling
WP4 Key Components Development – Leader CUT
Extended to M66
D4.1 AERAS Cyber Range Tools - V1 extended to M52 – Leader CUT
D4.2 AERAS Monitoring, Assessment and Adaptation mechanisms - V1 extended to M52 – Leader UMIL
D4.3 AERAS Cyber Range Tools – V2 extended to M66 – Leader AEGIS
D4.4 AERAS Monitoring, Assessment and Adaptation mechanisms – V2 extended to M66 – Leader UMIL

## Slide 10: WP5 reshuffling
Trinomial will take responsibility of WP5 «Platform Integration, Pilots, and Validation»
Extended to M72
D5.1 Initial Prototype of integrated AERAS platform extended to M56 – Leader TRI
D5.2 AERAS Evaluation Framework and Pilot Set Up Guidelines extended to M56 – Leader UMIL
D5.3 AERAS initial prototype pilot validation report extended to M60 – Leader UPAT
D5.4 Final Prototype of integrated AERAS platform extended to M68 – Leader TRI
D5.5 AERAS final prototype pilot validation report extended to M68 – Leader PAGNI
D6.6 Final AERAS evaluation report extended to M72 – Leader UMIL

## Slide 11: WP6 reshuffling
WP6 «Communication, Dissemination, Impact Creation» leader AEGIS
Extended to M72

## Slide 12: Milestones update
M1 and M2 achieved
M3 CRSA Language Definition – D3.1 extended to M52
M4 AERAS Models & Components Release – V1 – D3.2/D4.1/D4.2 extended to M52
M5 AERAS Prototype Integration and Pilot validation – D5.1/D5.2/D5.3 extended to M60
M6 AERAS Models & Components Release – V2 – D3.3/D4.3/D4.4 extended to M66
M7 Final AERAS Platform Pilot validation – D5.4/D5.5 extended to M72