## SecondmentsList (1)
Secondment No. | Researcher No. | Researcher Category | Sending Partner | Sending Country | Sending Country Group | Sending Sector Academic | Seconded to Partner | Seconded to Country | Seconded Country Group | Seconded Sector Academic | Starting Month | Duration | Work Package | Status
1 | 1 | ER | 1. UMIL (BEN) | Italy | EU/AC | Yes | 4. STS (BEN) | Switzerland | EU/AC | No | 7 | 4 | 2. Requirements & Platform Design | Active
2 | 1 | ER | 1. UMIL (BEN) | Italy | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 16 | 4 | 4. Key Components Development | Active
3 | 1 | ER | 1. UMIL (BEN) | Italy | EU/AC | Yes | 6. PAGNI (BEN) | Greece | EU/AC | No | 31 | 4 | 4. Key Components Development | Active
4 | 2 | ER | 1. UMIL (BEN) | Italy | EU/AC | Yes | 6. PAGNI (BEN) | Greece | EU/AC | No | 9 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
5 | 2 | ER | 1. UMIL (BEN) | Italy | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 15 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
6 | 2 | ER | 1. UMIL (BEN) | Italy | EU/AC | Yes | 4. STS (BEN) | Switzerland | EU/AC | No | 24 | 4 | 5. Platform Integration, Pilots, and Validation | Active
7 | 3 | ER | 1. UMIL (BEN) | Italy | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 6 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
8 | 3 | ER | 1. UMIL (BEN) | Italy | EU/AC | Yes | 6. PAGNI (BEN) | Greece | EU/AC | No | 20 | 4 | 4. Key Components Development | Active
9 | 3 | ER | 1. UMIL (BEN) | Italy | EU/AC | Yes | 4. STS (BEN) | Switzerland | EU/AC | No | 32 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
10 | 4 | ESR | 1. UMIL (BEN) | Italy | EU/AC | Yes | 4. STS (BEN) | Switzerland | EU/AC | No | 14 | 4 | 4. Key Components Development | Active
11 | 4 | ESR | 1. UMIL (BEN) | Italy | EU/AC | Yes | 6. PAGNI (BEN) | Greece | EU/AC | No | 24 | 4 | 5. Platform Integration, Pilots, and Validation | Active
12 | 4 | ESR | 1. UMIL (BEN) | Italy | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 28 | 4 | 5. Platform Integration, Pilots, and Validation | Active
13 | 5 | ER | 8. TSI (BEN) | Greece | EU/AC | Yes | 4. STS (BEN) | Switzerland | EU/AC | No | 13 | 4 | 2. Requirements & Platform Design | Updated
14 | 5 | ER | 8. TSI (BEN) | Greece | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 19 | 4 | 4. Key Components Development | Updated
15 | 5 | ER | 8. TSI (BEN) | Greece | EU/AC | Yes | 4. STS (BEN) | Switzerland | EU/AC | No | 27 | 4 | 5. Platform Integration, Pilots, and Validation | Updated
16 | 6 | ER | 8. TSI (BEN) | Greece | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 15 | 4 | 4. Key Components Development | Updated
17 | 6 | ER | 8. TSI (BEN) | Greece | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 28 | 4 | 5. Platform Integration, Pilots, and Validation | Updated
18 | 6 | ER | 8. TSI (BEN) | Greece | EU/AC | Yes | 4. STS (BEN) | Switzerland | EU/AC | No | 40 | 4 | 5. Platform Integration, Pilots, and Validation | Updated
19 | 7 | ER | 8. TSI (BEN) | Greece | EU/AC | Yes | 4. STS (BEN) | Switzerland | EU/AC | No | 13 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Updated
20 | 7 | ER | 8. TSI (BEN) | Greece | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 20 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Updated
21 | 7 | ER | 8. TSI (BEN) | Greece | EU/AC | Yes | 4. STS (BEN) | Switzerland | EU/AC | No | 37 | 4 | 4. Key Components Development | Updated
22 | 8 | ER | 8. TSI (BEN) | Greece | EU/AC | Yes | 4. STS (BEN) | Switzerland | EU/AC | No | 13 | 4 | 4. Key Components Development | Updated
23 | 8 | ER | 8. TSI (BEN) | Greece | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 19 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Updated
24 | 8 | ER | 8. TSI (BEN) | Greece | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 25 | 4 | 4. Key Components Development | Updated
25 | 9 | ER | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 6. PAGNI (BEN) | Greece | EU/AC | No | 3 | 4 | 2. Requirements & Platform Design | Active
26 | 9 | ER | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 9 | 4 | 4. Key Components Development | Active
27 | 9 | ER | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 4. STS (BEN) | Switzerland | EU/AC | No | 30 | 4 | 5. Platform Integration, Pilots, and Validation | Active
28 | 10 | ER | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 4. STS (BEN) | Switzerland | EU/AC | No | 11 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
29 | 10 | ER | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 31 | 4 | 4. Key Components Development | Active
30 | 10 | ER | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 6. PAGNI (BEN) | Greece | EU/AC | No | 45 | 4 | 5. Platform Integration, Pilots, and Validation | Active
31 | 11 | ER | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 4. STS (BEN) | Switzerland | EU/AC | No | 15 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
32 | 11 | ER | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 33 | 4 | 5. Platform Integration, Pilots, and Validation | Active
33 | 11 | ER | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 6. PAGNI (BEN) | Greece | EU/AC | No | 37 | 4 | 4. Key Components Development | Active
34 | 12 | ESR | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 4. STS (BEN) | Switzerland | EU/AC | No | 9 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
35 | 12 | ESR | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 6. PAGNI (BEN) | Greece | EU/AC | No | 20 | 4 | 4. Key Components Development | Active
36 | 12 | ESR | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 29 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
37 | 13 | ER | 4. STS (BEN) | Switzerland | EU/AC | No | 8. TSI (BEN) | Greece | EU/AC | Yes | 13 | 4 | 2. Requirements & Platform Design | Updated
38 | 13 | ER | 4. STS (BEN) | Switzerland | EU/AC | No | 1. UMIL (BEN) | Italy | EU/AC | Yes | 26 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
39 | 13 | ER | 4. STS (BEN) | Switzerland | EU/AC | No | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 37 | 4 | 4. Key Components Development | Active
40 | 14 | ER | 4. STS (BEN) | Switzerland | EU/AC | No | 7. UPAT (BEN) | Greece | EU/AC | Yes | 6 | 4 | 2. Requirements & Platform Design | Active
41 | 14 | ER | 4. STS (BEN) | Switzerland | EU/AC | No | 8. TSI (BEN) | Greece | EU/AC | Yes | 16 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Updated
42 | 14 | ER | 4. STS (BEN) | Switzerland | EU/AC | No | 1. UMIL (BEN) | Italy | EU/AC | Yes | 25 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
43 | 15 | ER | 4. STS (BEN) | Switzerland | EU/AC | No | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 14 | 4 | 4. Key Components Development | Active
44 | 15 | ER | 4. STS (BEN) | Switzerland | EU/AC | No | 8. TSI (BEN) | Greece | EU/AC | Yes | 32 | 4 | 5. Platform Integration, Pilots, and Validation | Updated
45 | 15 | ER | 4. STS (BEN) | Switzerland | EU/AC | No | 7. UPAT (BEN) | Greece | EU/AC | Yes | 39 | 4 | 5. Platform Integration, Pilots, and Validation | Active
46 | 16 | ESR | 4. STS (BEN) | Switzerland | EU/AC | No | 1. UMIL (BEN) | Italy | EU/AC | Yes | 20 | 4 | 4. Key Components Development | Active
47 | 16 | ESR | 4. STS (BEN) | Switzerland | EU/AC | No | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 26 | 4 | 4. Key Components Development | Active
48 | 16 | ESR | 4. STS (BEN) | Switzerland | EU/AC | No | 7. UPAT (BEN) | Greece | EU/AC | Yes | 37 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
49 | 17 | ER | 5. AEGIS (BEN) | Germany | EU/AC | No | 7. UPAT (BEN) | Greece | EU/AC | Yes | 1 | 4 | 2. Requirements & Platform Design | Active
50 | 17 | ER | 5. AEGIS (BEN) | Germany | EU/AC | No | 8. TSI (BEN) | Greece | EU/AC | Yes | 15 | 4 | 4. Key Components Development | Updated
51 | 17 | ER | 5. AEGIS (BEN) | Germany | EU/AC | No | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 25 | 4 | 4. Key Components Development | Active
52 | 18 | ESR | 4. STS (BEN) | Switzerland | EU/AC | No | 1. UMIL (BEN) | Italy | EU/AC | Yes | 9 | 4 | 4. Key Components Development | Active
53 | 18 | ESR | 4. STS (BEN) | Switzerland | EU/AC | No | 7. UPAT (BEN) | Greece | EU/AC | Yes | 21 | 4 | 5. Platform Integration, Pilots, and Validation | Active
54 | 18 | ESR | 4. STS (BEN) | Switzerland | EU/AC | No | 8. TSI (BEN) | Greece | EU/AC | Yes | 29 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Updated
55 | 19 | ESR | 5. AEGIS (BEN) | Germany | EU/AC | No | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 24 | 4 | 5. Platform Integration, Pilots, and Validation | Active
56 | 19 | ESR | 5. AEGIS (BEN) | Germany | EU/AC | No | 1. UMIL (BEN) | Italy | EU/AC | Yes | 31 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
57 | 19 | ESR | 5. AEGIS (BEN) | Germany | EU/AC | No | 7. UPAT (BEN) | Greece | EU/AC | Yes | 45 | 4 | 5. Platform Integration, Pilots, and Validation | Active
58 | 20 | ER | 6. PAGNI (BEN) | Greece | EU/AC | No | 1. UMIL (BEN) | Italy | EU/AC | Yes | 1 | 4 | 2. Requirements & Platform Design | Active
59 | 20 | ER | 6. PAGNI (BEN) | Greece | EU/AC | No | 1. UMIL (BEN) | Italy | EU/AC | Yes | 21 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Updated
60 | 20 | ER | 6. PAGNI (BEN) | Greece | EU/AC | No | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 31 | 4 | 4. Key Components Development | Active
61 | 21 | ER | 6. PAGNI (BEN) | Greece | EU/AC | No | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 3 | 4 | 2. Requirements & Platform Design | Updated
62 | 21 | ER | 6. PAGNI (BEN) | Greece | EU/AC | No | 1. UMIL (BEN) | Italy | EU/AC | Yes | 9 | 4 | 4. Key Components Development | Active
63 | 21 | ER | 6. PAGNI (BEN) | Greece | EU/AC | No | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 30 | 4 | 4. Key Components Development | Active
64 | 22 | ESR | 6. PAGNI (BEN) | Greece | EU/AC | No | 1. UMIL (BEN) | Italy | EU/AC | Yes | 23 | 4 | 4. Key Components Development | Active
65 | 22 | ESR | 6. PAGNI (BEN) | Greece | EU/AC | No | 1. UMIL (BEN) | Italy | EU/AC | Yes | 32 | 4 | 4. Key Components Development | Updated
66 | 22 | ESR | 6. PAGNI (BEN) | Greece | EU/AC | No | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 37 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
67 | 23 | ESR | 6. PAGNI (BEN) | Greece | EU/AC | No | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 26 | 4 | 5. Platform Integration, Pilots, and Validation | Active
68 | 23 | ESR | 6. PAGNI (BEN) | Greece | EU/AC | No | 1. UMIL (BEN) | Italy | EU/AC | Yes | 33 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
69 | 23 | ESR | 6. PAGNI (BEN) | Greece | EU/AC | No | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 40 | 4 | 5. Platform Integration, Pilots, and Validation | Updated
70 | 24 | ER | 7. UPAT (BEN) | Greece | EU/AC | Yes | 4. STS (BEN) | Switzerland | EU/AC | No | 3 | 4 | 2. Requirements & Platform Design | Active
71 | 24 | ER | 7. UPAT (BEN) | Greece | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 33 | 4 | 5. Platform Integration, Pilots, and Validation | Active
72 | 24 | ER | 7. UPAT (BEN) | Greece | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 37 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
73 | 25 | ER | 7. UPAT (BEN) | Greece | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 27 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
74 | 25 | ER | 7. UPAT (BEN) | Greece | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 31 | 4 | 5. Platform Integration, Pilots, and Validation | Active
75 | 25 | ER | 7. UPAT (BEN) | Greece | EU/AC | Yes | 4. STS (BEN) | Switzerland | EU/AC | No | 37 | 4 | 4. Key Components Development | Active
76 | 26 | ER | 7. UPAT (BEN) | Greece | EU/AC | Yes | 4. STS (BEN) | Switzerland | EU/AC | No | 21 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
77 | 26 | ER | 7. UPAT (BEN) | Greece | EU/AC | Yes | 4. STS (BEN) | Switzerland | EU/AC | No | 32 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
78 | 26 | ER | 7. UPAT (BEN) | Greece | EU/AC | Yes | 4. STS (BEN) | Switzerland | EU/AC | No | 37 | 4 | 4. Key Components Development | Active

## +12 Mo
Secondment No. | Researcher No. | Researcher Category | Sending Partner | Sending Country | Sending Country Group | Sending Sector Academic | Seconded to Partner | Seconded to Country | Seconded Country Group | Seconded Sector Academic | Starting Month | Duration | Work Package | Status
1 | 1 | ER | 1. UMIL (BEN) | Italy | EU/AC | Yes | 4. STS (BEN) | Switzerland | EU/AC | No | 11 | 4 | 2. Requirements & Platform Design | Active
2 | 1 | ER | 1. UMIL (BEN) | Italy | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 20 | 4 | 4. Key Components Development | Active
3 | 1 | ER | 1. UMIL (BEN) | Italy | EU/AC | Yes | 6. PAGNI (BEN) | Greece | EU/AC | No | 35 | 4 | 4. Key Components Development | Active
4 | 2 | ER | 1. UMIL (BEN) | Italy | EU/AC | Yes | 6. PAGNI (BEN) | Greece | EU/AC | No | 13 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
5 | 2 | ER | 1. UMIL (BEN) | Italy | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 19 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
6 | 2 | ER | 1. UMIL (BEN) | Italy | EU/AC | Yes | 4. STS (BEN) | Switzerland | EU/AC | No | 28 | 4 | 5. Platform Integration, Pilots, and Validation | Active
7 | 3 | ER | 1. UMIL (BEN) | Italy | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 10 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
8 | 3 | ER | 1. UMIL (BEN) | Italy | EU/AC | Yes | 6. PAGNI (BEN) | Greece | EU/AC | No | 24 | 4 | 4. Key Components Development | Active
9 | 3 | ER | 1. UMIL (BEN) | Italy | EU/AC | Yes | 4. STS (BEN) | Switzerland | EU/AC | No | 36 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
10 | 4 | ESR | 1. UMIL (BEN) | Italy | EU/AC | Yes | 4. STS (BEN) | Switzerland | EU/AC | No | 18 | 4 | 4. Key Components Development | Active
11 | 4 | ESR | 1. UMIL (BEN) | Italy | EU/AC | Yes | 6. PAGNI (BEN) | Greece | EU/AC | No | 28 | 4 | 5. Platform Integration, Pilots, and Validation | Active
12 | 4 | ESR | 1. UMIL (BEN) | Italy | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 32 | 4 | 5. Platform Integration, Pilots, and Validation | Active
13 | 5 | ER | 8. TSI (BEN) | Greece | EU/AC | Yes | 4. STS (BEN) | Switzerland | EU/AC | No | 17 | 4 | 2. Requirements & Platform Design | Updated
14 | 5 | ER | 8. TSI (BEN) | Greece | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 23 | 4 | 4. Key Components Development | Updated
15 | 5 | ER | 8. TSI (BEN) | Greece | EU/AC | Yes | 4. STS (BEN) | Switzerland | EU/AC | No | 31 | 4 | 5. Platform Integration, Pilots, and Validation | Updated
16 | 6 | ER | 8. TSI (BEN) | Greece | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 19 | 4 | 4. Key Components Development | Updated
17 | 6 | ER | 8. TSI (BEN) | Greece | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 32 | 4 | 5. Platform Integration, Pilots, and Validation | Updated
18 | 6 | ER | 8. TSI (BEN) | Greece | EU/AC | Yes | 4. STS (BEN) | Switzerland | EU/AC | No | 44 | 4 | 5. Platform Integration, Pilots, and Validation | Updated
19 | 7 | ER | 8. TSI (BEN) | Greece | EU/AC | Yes | 4. STS (BEN) | Switzerland | EU/AC | No | 17 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Updated
20 | 7 | ER | 8. TSI (BEN) | Greece | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 24 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Updated
21 | 7 | ER | 8. TSI (BEN) | Greece | EU/AC | Yes | 4. STS (BEN) | Switzerland | EU/AC | No | 41 | 4 | 4. Key Components Development | Updated
22 | 8 | ER | 8. TSI (BEN) | Greece | EU/AC | Yes | 4. STS (BEN) | Switzerland | EU/AC | No | 17 | 4 | 4. Key Components Development | Updated
23 | 8 | ER | 8. TSI (BEN) | Greece | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 23 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Updated
24 | 8 | ER | 8. TSI (BEN) | Greece | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 29 | 4 | 4. Key Components Development | Updated
25 | 9 | ER | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 6. PAGNI (BEN) | Greece | EU/AC | No | 3 | 4 | 2. Requirements & Platform Design | Active
26 | 9 | ER | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 9 | 4 | 4. Key Components Development | Active
27 | 9 | ER | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 4. STS (BEN) | Switzerland | EU/AC | No | 34 | 4 | 5. Platform Integration, Pilots, and Validation | Active
28 | 10 | ER | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 4. STS (BEN) | Switzerland | EU/AC | No | 15 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
29 | 10 | ER | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 31 | 4 | 4. Key Components Development | Active
30 | 10 | ER | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 6. PAGNI (BEN) | Greece | EU/AC | No | 45 | 4 | 5. Platform Integration, Pilots, and Validation | Active
31 | 11 | ER | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 4. STS (BEN) | Switzerland | EU/AC | No | 19 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
32 | 11 | ER | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 33 | 4 | 5. Platform Integration, Pilots, and Validation | Active
33 | 11 | ER | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 6. PAGNI (BEN) | Greece | EU/AC | No | 37 | 4 | 4. Key Components Development | Active
34 | 12 | ESR | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 4. STS (BEN) | Switzerland | EU/AC | No | 13 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
35 | 12 | ESR | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 6. PAGNI (BEN) | Greece | EU/AC | No | 24 | 4 | 4. Key Components Development | Active
36 | 12 | ESR | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 33 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
37 | 13 | ER | 4. STS (BEN) | Switzerland | EU/AC | No | 8. TSI (BEN) | Greece | EU/AC | Yes | 17 | 4 | 2. Requirements & Platform Design | Updated
38 | 13 | ER | 4. STS (BEN) | Switzerland | EU/AC | No | 1. UMIL (BEN) | Italy | EU/AC | Yes | 30 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
39 | 13 | ER | 4. STS (BEN) | Switzerland | EU/AC | No | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 41 | 4 | 4. Key Components Development | Active
40 | 14 | ER | 4. STS (BEN) | Switzerland | EU/AC | No | 7. UPAT (BEN) | Greece | EU/AC | Yes | 10 | 4 | 2. Requirements & Platform Design | Active
41 | 14 | ER | 4. STS (BEN) | Switzerland | EU/AC | No | 8. TSI (BEN) | Greece | EU/AC | Yes | 20 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Updated
42 | 14 | ER | 4. STS (BEN) | Switzerland | EU/AC | No | 1. UMIL (BEN) | Italy | EU/AC | Yes | 29 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
43 | 15 | ER | 4. STS (BEN) | Switzerland | EU/AC | No | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 18 | 4 | 4. Key Components Development | Active
44 | 15 | ER | 4. STS (BEN) | Switzerland | EU/AC | No | 8. TSI (BEN) | Greece | EU/AC | Yes | 36 | 4 | 5. Platform Integration, Pilots, and Validation | Updated
45 | 15 | ER | 4. STS (BEN) | Switzerland | EU/AC | No | 7. UPAT (BEN) | Greece | EU/AC | Yes | 43 | 4 | 5. Platform Integration, Pilots, and Validation | Active
46 | 16 | ESR | 4. STS (BEN) | Switzerland | EU/AC | No | 1. UMIL (BEN) | Italy | EU/AC | Yes | 24 | 4 | 4. Key Components Development | Active
47 | 16 | ESR | 4. STS (BEN) | Switzerland | EU/AC | No | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 30 | 4 | 4. Key Components Development | Active
48 | 16 | ESR | 4. STS (BEN) | Switzerland | EU/AC | No | 7. UPAT (BEN) | Greece | EU/AC | Yes | 41 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
49 | 17 | ER | 5. AEGIS (BEN) | Germany | EU/AC | No | 7. UPAT (BEN) | Greece | EU/AC | Yes | 5 | 4 | 2. Requirements & Platform Design | Active
50 | 17 | ER | 5. AEGIS (BEN) | Germany | EU/AC | No | 8. TSI (BEN) | Greece | EU/AC | Yes | 19 | 4 | 4. Key Components Development | Updated
51 | 17 | ER | 5. AEGIS (BEN) | Germany | EU/AC | No | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 29 | 4 | 4. Key Components Development | Active
52 | 18 | ESR | 4. STS (BEN) | Switzerland | EU/AC | No | 1. UMIL (BEN) | Italy | EU/AC | Yes | 13 | 4 | 4. Key Components Development | Active
53 | 18 | ESR | 4. STS (BEN) | Switzerland | EU/AC | No | 7. UPAT (BEN) | Greece | EU/AC | Yes | 25 | 4 | 5. Platform Integration, Pilots, and Validation | Active
54 | 18 | ESR | 4. STS (BEN) | Switzerland | EU/AC | No | 8. TSI (BEN) | Greece | EU/AC | Yes | 33 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Updated
55 | 19 | ESR | 5. AEGIS (BEN) | Germany | EU/AC | No | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 28 | 4 | 5. Platform Integration, Pilots, and Validation | Active
56 | 19 | ESR | 5. AEGIS (BEN) | Germany | EU/AC | No | 1. UMIL (BEN) | Italy | EU/AC | Yes | 35 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
57 | 19 | ESR | 5. AEGIS (BEN) | Germany | EU/AC | No | 7. UPAT (BEN) | Greece | EU/AC | Yes | 49 | 4 | 5. Platform Integration, Pilots, and Validation | Active
58 | 20 | ER | 6. PAGNI (BEN) | Greece | EU/AC | No | 1. UMIL (BEN) | Italy | EU/AC | Yes | 5 | 4 | 2. Requirements & Platform Design | Active
59 | 20 | ER | 6. PAGNI (BEN) | Greece | EU/AC | No | 1. UMIL (BEN) | Italy | EU/AC | Yes | 25 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Updated
60 | 20 | ER | 6. PAGNI (BEN) | Greece | EU/AC | No | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 35 | 4 | 4. Key Components Development | Active
61 | 21 | ER | 6. PAGNI (BEN) | Greece | EU/AC | No | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 7 | 4 | 2. Requirements & Platform Design | Updated
62 | 21 | ER | 6. PAGNI (BEN) | Greece | EU/AC | No | 1. UMIL (BEN) | Italy | EU/AC | Yes | 13 | 4 | 4. Key Components Development | Active
63 | 21 | ER | 6. PAGNI (BEN) | Greece | EU/AC | No | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 34 | 4 | 4. Key Components Development | Active
64 | 22 | ESR | 6. PAGNI (BEN) | Greece | EU/AC | No | 1. UMIL (BEN) | Italy | EU/AC | Yes | 27 | 4 | 4. Key Components Development | Active
65 | 22 | ESR | 6. PAGNI (BEN) | Greece | EU/AC | No | 1. UMIL (BEN) | Italy | EU/AC | Yes | 36 | 4 | 4. Key Components Development | Updated
66 | 22 | ESR | 6. PAGNI (BEN) | Greece | EU/AC | No | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 41 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
67 | 23 | ESR | 6. PAGNI (BEN) | Greece | EU/AC | No | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 30 | 4 | 5. Platform Integration, Pilots, and Validation | Active
68 | 23 | ESR | 6. PAGNI (BEN) | Greece | EU/AC | No | 1. UMIL (BEN) | Italy | EU/AC | Yes | 37 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
69 | 23 | ESR | 6. PAGNI (BEN) | Greece | EU/AC | No | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 44 | 4 | 5. Platform Integration, Pilots, and Validation | Updated
70 | 24 | ER | 7. UPAT (BEN) | Greece | EU/AC | Yes | 4. STS (BEN) | Switzerland | EU/AC | No | 7 | 4 | 2. Requirements & Platform Design | Active | 31
71 | 24 | ER | 7. UPAT (BEN) | Greece | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 37 | 4 | 5. Platform Integration, Pilots, and Validation | Active
72 | 24 | ER | 7. UPAT (BEN) | Greece | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 41 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
73 | 25 | ER | 7. UPAT (BEN) | Greece | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 31 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active | 22
74 | 25 | ER | 7. UPAT (BEN) | Greece | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 35 | 4 | 5. Platform Integration, Pilots, and Validation | Active
75 | 25 | ER | 7. UPAT (BEN) | Greece | EU/AC | Yes | 4. STS (BEN) | Switzerland | EU/AC | No | 41 | 4 | 4. Key Components Development | Active
76 | 26 | ER | 7. UPAT (BEN) | Greece | EU/AC | Yes | 4. STS (BEN) | Switzerland | EU/AC | No | 25 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
77 | 26 | ER | 7. UPAT (BEN) | Greece | EU/AC | Yes | 4. STS (BEN) | Switzerland | EU/AC | No | 36 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
78 | 26 | ER | 7. UPAT (BEN) | Greece | EU/AC | Yes | 4. STS (BEN) | Switzerland | EU/AC | No | 41 | 4 | 4. Key Components Development | Active

## STS CY
Secondment No. | Researcher No. | Researcher Category | Sending Partner | Sending Country | Sending Country Group | Sending Sector Academic | Seconded to Partner | Seconded to Country | Seconded Country Group | Seconded Sector Academic | Starting Month | Duration | Work Package | Status
1 | 1 | ER | 1. UMIL (BEN) | Italy | EU/AC | Yes | 4. STS (BEN) | Cyprus | EU/AC | No | 11 | 4 | 2. Requirements & Platform Design | Active
2 | 1 | ER | 1. UMIL (BEN) | Italy | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 20 | 4 | 4. Key Components Development | Active
3 | 1 | ER | 1. UMIL (BEN) | Italy | EU/AC | Yes | 6. PAGNI (BEN) | Greece | EU/AC | No | 35 | 4 | 4. Key Components Development | Active
4 | 2 | ER | 1. UMIL (BEN) | Italy | EU/AC | Yes | 6. PAGNI (BEN) | Greece | EU/AC | No | 13 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
5 | 2 | ER | 1. UMIL (BEN) | Italy | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 19 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
6 | 2 | ER | 1. UMIL (BEN) | Italy | EU/AC | Yes | 4. STS (BEN) | Cyprus | EU/AC | No | 28 | 4 | 5. Platform Integration, Pilots, and Validation | Active
7 | 3 | ER | 1. UMIL (BEN) | Italy | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 10 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
8 | 3 | ER | 1. UMIL (BEN) | Italy | EU/AC | Yes | 6. PAGNI (BEN) | Greece | EU/AC | No | 24 | 4 | 4. Key Components Development | Active
9 | 3 | ER | 1. UMIL (BEN) | Italy | EU/AC | Yes | 4. STS (BEN) | Cyprus | EU/AC | No | 36 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
10 | 4 | ESR | 1. UMIL (BEN) | Italy | EU/AC | Yes | 4. STS (BEN) | Cyprus | EU/AC | No | 18 | 4 | 4. Key Components Development | Active
11 | 4 | ESR | 1. UMIL (BEN) | Italy | EU/AC | Yes | 6. PAGNI (BEN) | Greece | EU/AC | No | 28 | 4 | 5. Platform Integration, Pilots, and Validation | Active
12 | 4 | ESR | 1. UMIL (BEN) | Italy | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 32 | 4 | 5. Platform Integration, Pilots, and Validation | Active
13 | 5 | ER | 8. TSI (BEN) | Greece | EU/AC | Yes | 4. STS (BEN) | Cyprus | EU/AC | No | 17 | 4 | 2. Requirements & Platform Design | Updated
14 | 5 | ER | 8. TSI (BEN) | Greece | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 23 | 4 | 4. Key Components Development | Updated
15 | 5 | ER | 8. TSI (BEN) | Greece | EU/AC | Yes | 4. STS (BEN) | Cyprus | EU/AC | No | 31 | 4 | 5. Platform Integration, Pilots, and Validation | Updated
16 | 6 | ER | 8. TSI (BEN) | Greece | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 19 | 4 | 4. Key Components Development | Updated
17 | 6 | ER | 8. TSI (BEN) | Greece | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 32 | 4 | 5. Platform Integration, Pilots, and Validation | Updated
18 | 6 | ER | 8. TSI (BEN) | Greece | EU/AC | Yes | 4. STS (BEN) | Cyprus | EU/AC | No | 44 | 4 | 5. Platform Integration, Pilots, and Validation | Updated
19 | 7 | ER | 8. TSI (BEN) | Greece | EU/AC | Yes | 4. STS (BEN) | Cyprus | EU/AC | No | 17 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Updated
20 | 7 | ER | 8. TSI (BEN) | Greece | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 24 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Updated
21 | 7 | ER | 8. TSI (BEN) | Greece | EU/AC | Yes | 4. STS (BEN) | Cyprus | EU/AC | No | 41 | 4 | 4. Key Components Development | Updated
22 | 8 | ER | 8. TSI (BEN) | Greece | EU/AC | Yes | 4. STS (BEN) | Cyprus | EU/AC | No | 17 | 4 | 4. Key Components Development | Updated
23 | 8 | ER | 8. TSI (BEN) | Greece | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 23 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Updated
24 | 8 | ER | 8. TSI (BEN) | Greece | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 29 | 4 | 4. Key Components Development | Updated
25 | 9 | ER | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 6. PAGNI (BEN) | Greece | EU/AC | No | 3 | 4 | 2. Requirements & Platform Design | Active
26 | 9 | ER | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 9 | 4 | 4. Key Components Development | Active
27 | 9 | ER | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 4. STS (BEN) | Cyprus | EU/AC | No | 34 | 4 | 5. Platform Integration, Pilots, and Validation | Active
28 | 10 | ER | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 4. STS (BEN) | Cyprus | EU/AC | No | 15 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
29 | 10 | ER | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 31 | 4 | 4. Key Components Development | Active
30 | 10 | ER | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 6. PAGNI (BEN) | Greece | EU/AC | No | 45 | 4 | 5. Platform Integration, Pilots, and Validation | Active
31 | 11 | ER | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 4. STS (BEN) | Cyprus | EU/AC | No | 19 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
32 | 11 | ER | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 33 | 4 | 5. Platform Integration, Pilots, and Validation | Active
33 | 11 | ER | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 6. PAGNI (BEN) | Greece | EU/AC | No | 37 | 4 | 4. Key Components Development | Active
34 | 12 | ESR | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 4. STS (BEN) | Cyprus | EU/AC | No | 13 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
35 | 12 | ESR | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 6. PAGNI (BEN) | Greece | EU/AC | No | 24 | 4 | 4. Key Components Development | Active
36 | 12 | ESR | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 33 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
37 | 13 | ER | 4. STS (BEN) | Cyprus | EU/AC | No | 8. TSI (BEN) | Greece | EU/AC | Yes | 17 | 4 | 2. Requirements & Platform Design | Updated
38 | 13 | ER | 4. STS (BEN) | Cyprus | EU/AC | No | 1. UMIL (BEN) | Italy | EU/AC | Yes | 30 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
39 | 13 | ER | 4. STS (BEN) | Cyprus | EU/AC | No | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 41 | 4 | 4. Key Components Development | Active
40 | 14 | ER | 4. STS (BEN) | Cyprus | EU/AC | No | 7. UPAT (BEN) | Greece | EU/AC | Yes | 10 | 4 | 2. Requirements & Platform Design | Active
41 | 14 | ER | 4. STS (BEN) | Cyprus | EU/AC | No | 8. TSI (BEN) | Greece | EU/AC | Yes | 20 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Updated
42 | 14 | ER | 4. STS (BEN) | Cyprus | EU/AC | No | 1. UMIL (BEN) | Italy | EU/AC | Yes | 29 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
43 | 15 | ER | 4. STS (BEN) | Cyprus | EU/AC | No | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 18 | 4 | 4. Key Components Development | Active
44 | 15 | ER | 4. STS (BEN) | Cyprus | EU/AC | No | 8. TSI (BEN) | Greece | EU/AC | Yes | 36 | 4 | 5. Platform Integration, Pilots, and Validation | Updated
45 | 15 | ER | 4. STS (BEN) | Cyprus | EU/AC | No | 7. UPAT (BEN) | Greece | EU/AC | Yes | 43 | 4 | 5. Platform Integration, Pilots, and Validation | Active
46 | 16 | ESR | 4. STS (BEN) | Cyprus | EU/AC | No | 1. UMIL (BEN) | Italy | EU/AC | Yes | 24 | 4 | 4. Key Components Development | Active
47 | 16 | ESR | 4. STS (BEN) | Cyprus | EU/AC | No | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 30 | 4 | 4. Key Components Development | Active
48 | 16 | ESR | 4. STS (BEN) | Cyprus | EU/AC | No | 7. UPAT (BEN) | Greece | EU/AC | Yes | 41 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
49 | 17 | ER | 5. AEGIS (BEN) | Germany | EU/AC | No | 7. UPAT (BEN) | Greece | EU/AC | Yes | 5 | 4 | 2. Requirements & Platform Design | Active
50 | 17 | ER | 5. AEGIS (BEN) | Germany | EU/AC | No | 8. TSI (BEN) | Greece | EU/AC | Yes | 19 | 4 | 4. Key Components Development | Updated
51 | 17 | ER | 5. AEGIS (BEN) | Germany | EU/AC | No | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 29 | 4 | 4. Key Components Development | Active
52 | 18 | ESR | 4. STS (BEN) | Cyprus | EU/AC | No | 1. UMIL (BEN) | Italy | EU/AC | Yes | 13 | 4 | 4. Key Components Development | Active
53 | 18 | ESR | 4. STS (BEN) | Cyprus | EU/AC | No | 7. UPAT (BEN) | Greece | EU/AC | Yes | 25 | 4 | 5. Platform Integration, Pilots, and Validation | Active
54 | 18 | ESR | 4. STS (BEN) | Cyprus | EU/AC | No | 8. TSI (BEN) | Greece | EU/AC | Yes | 33 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Updated
55 | 19 | ESR | 5. AEGIS (BEN) | Germany | EU/AC | No | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 28 | 4 | 5. Platform Integration, Pilots, and Validation | Active
56 | 19 | ESR | 5. AEGIS (BEN) | Germany | EU/AC | No | 1. UMIL (BEN) | Italy | EU/AC | Yes | 35 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
57 | 19 | ESR | 5. AEGIS (BEN) | Germany | EU/AC | No | 7. UPAT (BEN) | Greece | EU/AC | Yes | 49 | 4 | 5. Platform Integration, Pilots, and Validation | Active
58 | 20 | ER | 6. PAGNI (BEN) | Greece | EU/AC | No | 1. UMIL (BEN) | Italy | EU/AC | Yes | 5 | 4 | 2. Requirements & Platform Design | Active
59 | 20 | ER | 6. PAGNI (BEN) | Greece | EU/AC | No | 1. UMIL (BEN) | Italy | EU/AC | Yes | 25 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Updated
60 | 20 | ER | 6. PAGNI (BEN) | Greece | EU/AC | No | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 35 | 4 | 4. Key Components Development | Active
61 | 21 | ER | 6. PAGNI (BEN) | Greece | EU/AC | No | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 7 | 4 | 2. Requirements & Platform Design | Updated
62 | 21 | ER | 6. PAGNI (BEN) | Greece | EU/AC | No | 1. UMIL (BEN) | Italy | EU/AC | Yes | 13 | 4 | 4. Key Components Development | Active
63 | 21 | ER | 6. PAGNI (BEN) | Greece | EU/AC | No | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 34 | 4 | 4. Key Components Development | Active
64 | 22 | ESR | 6. PAGNI (BEN) | Greece | EU/AC | No | 1. UMIL (BEN) | Italy | EU/AC | Yes | 27 | 4 | 4. Key Components Development | Active
65 | 22 | ESR | 6. PAGNI (BEN) | Greece | EU/AC | No | 1. UMIL (BEN) | Italy | EU/AC | Yes | 36 | 4 | 4. Key Components Development | Updated
66 | 22 | ESR | 6. PAGNI (BEN) | Greece | EU/AC | No | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 41 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
67 | 23 | ESR | 6. PAGNI (BEN) | Greece | EU/AC | No | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 30 | 4 | 5. Platform Integration, Pilots, and Validation | Active
68 | 23 | ESR | 6. PAGNI (BEN) | Greece | EU/AC | No | 1. UMIL (BEN) | Italy | EU/AC | Yes | 37 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
69 | 23 | ESR | 6. PAGNI (BEN) | Greece | EU/AC | No | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 44 | 4 | 5. Platform Integration, Pilots, and Validation | Updated
70 | 24 | ER | 7. UPAT (BEN) | Greece | EU/AC | Yes | 4. STS (BEN) | Cyprus | EU/AC | No | 7 | 4 | 2. Requirements & Platform Design | Active
71 | 24 | ER | 7. UPAT (BEN) | Greece | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 37 | 4 | 5. Platform Integration, Pilots, and Validation | Active
72 | 24 | ER | 7. UPAT (BEN) | Greece | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 41 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
73 | 25 | ER | 7. UPAT (BEN) | Greece | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 31 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
74 | 25 | ER | 7. UPAT (BEN) | Greece | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 35 | 4 | 5. Platform Integration, Pilots, and Validation | Active
75 | 25 | ER | 7. UPAT (BEN) | Greece | EU/AC | Yes | 4. STS (BEN) | Cyprus | EU/AC | No | 41 | 4 | 4. Key Components Development | Active
76 | 26 | ER | 7. UPAT (BEN) | Greece | EU/AC | Yes | 4. STS (BEN) | Cyprus | EU/AC | No | 25 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
77 | 26 | ER | 7. UPAT (BEN) | Greece | EU/AC | Yes | 4. STS (BEN) | Cyprus | EU/AC | No | 36 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
78 | 26 | ER | 7. UPAT (BEN) | Greece | EU/AC | Yes | 4. STS (BEN) | Cyprus | EU/AC | No | 41 | 4 | 4. Key Components Development | Active

## proposed
Secondment No. | Researcher No. | Researcher Category | Sending Partner | Sending Country | Sending Country Group | Sending Sector Academic | Seconded to Partner | Seconded to Country | Seconded Country Group | Seconded Sector Academic | Starting Month | Duration | Work Package | Status
1 | 1 | ER | 1. UMIL (BEN) | Italy | EU/AC | Yes | 4. STS (BEN) | Cyprus | EU/AC | No | 11 | 4 | 2. Requirements & Platform Design | Active
2 | 1 | ER | 1. UMIL (BEN) | Italy | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 20 | 4 | 4. Key Components Development | Active
3 | 1 | ER | 1. UMIL (BEN) | Italy | EU/AC | Yes | 6. PAGNI (BEN) | Greece | EU/AC | No | 35 | 4 | 4. Key Components Development | Active
4 | 2 | ER | 1. UMIL (BEN) | Italy | EU/AC | Yes | 6. PAGNI (BEN) | Greece | EU/AC | No | 13 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
5 | 2 | ER | 1. UMIL (BEN) | Italy | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 19 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
6 | 2 | ER | 1. UMIL (BEN) | Italy | EU/AC | Yes | 4. STS (BEN) | Cyprus | EU/AC | No | 28 | 4 | 5. Platform Integration, Pilots, and Validation | Active
7 | 3 | ER | 1. UMIL (BEN) | Italy | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 10 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
8 | 3 | ER | 1. UMIL (BEN) | Italy | EU/AC | Yes | 6. PAGNI (BEN) | Greece | EU/AC | No | 24 | 4 | 4. Key Components Development | Active
9 | 3 | ER | 1. UMIL (BEN) | Italy | EU/AC | Yes | 4. STS (BEN) | Cyprus | EU/AC | No | 36 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
10 | 4 | ESR | 1. UMIL (BEN) | Italy | EU/AC | Yes | 4. STS (BEN) | Cyprus | EU/AC | No | 18 | 4 | 4. Key Components Development | Active
11 | 4 | ESR | 1. UMIL (BEN) | Italy | EU/AC | Yes | 6. PAGNI (BEN) | Greece | EU/AC | No | 28 | 4 | 5. Platform Integration, Pilots, and Validation | Active
12 | 4 | ESR | 1. UMIL (BEN) | Italy | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 32 | 4 | 5. Platform Integration, Pilots, and Validation | Active
13 | 5 | ER | 8. TSI (BEN) | Greece | EU/AC | Yes | 4. STS (BEN) | Cyprus | EU/AC | No | 17 | 4 | 2. Requirements & Platform Design | Updated
14 | 5 | ER | 8. TSI (BEN) | Greece | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 23 | 4 | 4. Key Components Development | Updated
15 | 5 | ER | 8. TSI (BEN) | Greece | EU/AC | Yes | 4. STS (BEN) | Cyprus | EU/AC | No | 31 | 4 | 5. Platform Integration, Pilots, and Validation | Updated
16 | 6 | ER | 8. TSI (BEN) | Greece | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 19 | 4 | 4. Key Components Development | Updated
17 | 6 | ER | 8. TSI (BEN) | Greece | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 32 | 4 | 5. Platform Integration, Pilots, and Validation | Updated
18 | 6 | ER | 8. TSI (BEN) | Greece | EU/AC | Yes | 4. STS (BEN) | Cyprus | EU/AC | No | 44 | 4 | 5. Platform Integration, Pilots, and Validation | Updated
19 | 7 | ER | 8. TSI (BEN) | Greece | EU/AC | Yes | 4. STS (BEN) | Cyprus | EU/AC | No | 17 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Updated
20 | 7 | ER | 8. TSI (BEN) | Greece | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 24 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Updated
21 | 7 | ER | 8. TSI (BEN) | Greece | EU/AC | Yes | 4. STS (BEN) | Cyprus | EU/AC | No | 41 | 4 | 4. Key Components Development | Updated
22 | 8 | ER | 8. TSI (BEN) | Greece | EU/AC | Yes | 4. STS (BEN) | Cyprus | EU/AC | No | 17 | 4 | 4. Key Components Development | Updated
23 | 8 | ER | 8. TSI (BEN) | Greece | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 23 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Updated
24 | 8 | ER | 8. TSI (BEN) | Greece | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 29 | 4 | 4. Key Components Development | Updated
25 | 9 | ER | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 6. PAGNI (BEN) | Greece | EU/AC | No | 3 | 4 | 2. Requirements & Platform Design | Active
26 | 9 | ER | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 9 | 4 | 4. Key Components Development | Active
27 | 9 | ER | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 6. PAGNI (BEN) | Greece | EU/AC | No | 34 | 4 | 5. Platform Integration, Pilots, and Validation | Active
28 | 10 | ER | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 15 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
29 | 10 | ER | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 31 | 4 | 4. Key Components Development | Active
30 | 10 | ER | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 6. PAGNI (BEN) | Greece | EU/AC | No | 45 | 4 | 5. Platform Integration, Pilots, and Validation | Active
31 | 11 | ER | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 6. PAGNI (BEN) | Greece | EU/AC | No | 19 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
32 | 11 | ER | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 33 | 4 | 5. Platform Integration, Pilots, and Validation | Active
33 | 11 | ER | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 6. PAGNI (BEN) | Greece | EU/AC | No | 37 | 4 | 4. Key Components Development | Active
34 | 12 | ESR | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 13 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
35 | 12 | ESR | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 6. PAGNI (BEN) | Greece | EU/AC | No | 24 | 4 | 4. Key Components Development | Active
36 | 12 | ESR | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 33 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
37 | 13 | ER | 4. STS (BEN) | Cyprus | EU/AC | No | 8. TSI (BEN) | Greece | EU/AC | Yes | 17 | 4 | 2. Requirements & Platform Design | Updated
38 | 13 | ER | 4. STS (BEN) | Cyprus | EU/AC | No | 1. UMIL (BEN) | Italy | EU/AC | Yes | 30 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
39 | 13 | ER | 4. STS (BEN) | Cyprus | EU/AC | No | 1. UMIL (BEN) | Cyprus | EU/AC | Yes | 41 | 4 | 4. Key Components Development | Active
40 | 14 | ER | 4. STS (BEN) | Cyprus | EU/AC | No | 7. UPAT (BEN) | Greece | EU/AC | Yes | 10 | 4 | 2. Requirements & Platform Design | Active
41 | 14 | ER | 4. STS (BEN) | Cyprus | EU/AC | No | 8. TSI (BEN) | Greece | EU/AC | Yes | 20 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Updated
42 | 14 | ER | 4. STS (BEN) | Cyprus | EU/AC | No | 1. UMIL (BEN) | Italy | EU/AC | Yes | 29 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
43 | 15 | ER | 4. STS (BEN) | Cyprus | EU/AC | No | 7. UPAT (BEN) | Cyprus | EU/AC | Yes | 18 | 4 | 4. Key Components Development | Active
44 | 15 | ER | 4. STS (BEN) | Cyprus | EU/AC | No | 8. TSI (BEN) | Greece | EU/AC | Yes | 36 | 4 | 5. Platform Integration, Pilots, and Validation | Updated
45 | 15 | ER | 4. STS (BEN) | Cyprus | EU/AC | No | 7. UPAT (BEN) | Greece | EU/AC | Yes | 43 | 4 | 5. Platform Integration, Pilots, and Validation | Active
46 | 16 | ESR | 4. STS (BEN) | Cyprus | EU/AC | No | 1. UMIL (BEN) | Italy | EU/AC | Yes | 24 | 4 | 4. Key Components Development | Active
47 | 16 | ESR | 4. STS (BEN) | Cyprus | EU/AC | No | 8. TSI (BEN) | Cyprus | EU/AC | Yes | 30 | 4 | 4. Key Components Development | Active
48 | 16 | ESR | 4. STS (BEN) | Cyprus | EU/AC | No | 7. UPAT (BEN) | Greece | EU/AC | Yes | 41 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
49 | 17 | ER | 5. AEGIS (BEN) | Germany | EU/AC | No | 7. UPAT (BEN) | Greece | EU/AC | Yes | 5 | 4 | 2. Requirements & Platform Design | Active
50 | 17 | ER | 5. AEGIS (BEN) | Germany | EU/AC | No | 8. TSI (BEN) | Greece | EU/AC | Yes | 19 | 4 | 4. Key Components Development | Updated
51 | 17 | ER | 5. AEGIS (BEN) | Germany | EU/AC | No | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 29 | 4 | 4. Key Components Development | Active
52 | 18 | ESR | 4. STS (BEN) | Cyprus | EU/AC | No | 1. UMIL (BEN) | Italy | EU/AC | Yes | 13 | 4 | 4. Key Components Development | Active
53 | 18 | ESR | 4. STS (BEN) | Cyprus | EU/AC | No | 7. UPAT (BEN) | Greece | EU/AC | Yes | 25 | 4 | 5. Platform Integration, Pilots, and Validation | Active
54 | 18 | ESR | 4. STS (BEN) | Cyprus | EU/AC | No | 8. TSI (BEN) | Greece | EU/AC | Yes | 33 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Updated
55 | 19 | ESR | 5. AEGIS (BEN) | Germany | EU/AC | No | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 28 | 4 | 5. Platform Integration, Pilots, and Validation | Active
56 | 19 | ESR | 5. AEGIS (BEN) | Germany | EU/AC | No | 1. UMIL (BEN) | Italy | EU/AC | Yes | 35 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
57 | 19 | ESR | 5. AEGIS (BEN) | Germany | EU/AC | No | 7. UPAT (BEN) | Greece | EU/AC | Yes | 49 | 4 | 5. Platform Integration, Pilots, and Validation | Active
58 | 20 | ER | 6. PAGNI (BEN) | Greece | EU/AC | No | 1. UMIL (BEN) | Italy | EU/AC | Yes | 5 | 4 | 2. Requirements & Platform Design | Active
59 | 20 | ER | 6. PAGNI (BEN) | Greece | EU/AC | No | 1. UMIL (BEN) | Italy | EU/AC | Yes | 25 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Updated
60 | 20 | ER | 6. PAGNI (BEN) | Greece | EU/AC | No | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 35 | 4 | 4. Key Components Development | Active
61 | 21 | ER | 6. PAGNI (BEN) | Greece | EU/AC | No | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 7 | 4 | 2. Requirements & Platform Design | Updated
62 | 21 | ER | 6. PAGNI (BEN) | Greece | EU/AC | No | 1. UMIL (BEN) | Italy | EU/AC | Yes | 13 | 4 | 4. Key Components Development | Active
63 | 21 | ER | 6. PAGNI (BEN) | Greece | EU/AC | No | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 34 | 4 | 4. Key Components Development | Active
64 | 22 | ESR | 6. PAGNI (BEN) | Greece | EU/AC | No | 1. UMIL (BEN) | Italy | EU/AC | Yes | 27 | 4 | 4. Key Components Development | Active
65 | 22 | ESR | 6. PAGNI (BEN) | Greece | EU/AC | No | 1. UMIL (BEN) | Italy | EU/AC | Yes | 36 | 4 | 4. Key Components Development | Updated
66 | 22 | ESR | 6. PAGNI (BEN) | Greece | EU/AC | No | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 41 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
67 | 23 | ESR | 6. PAGNI (BEN) | Greece | EU/AC | No | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 30 | 4 | 5. Platform Integration, Pilots, and Validation | Active
68 | 23 | ESR | 6. PAGNI (BEN) | Greece | EU/AC | No | 1. UMIL (BEN) | Italy | EU/AC | Yes | 37 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active
69 | 23 | ESR | 6. PAGNI (BEN) | Greece | EU/AC | No | 3. CUT (BEN) | Cyprus | EU/AC | Yes | 44 | 4 | 5. Platform Integration, Pilots, and Validation | Updated
70 | 24 | ER | 7. UPAT (BEN) | Greece | EU/AC | Yes | 4. STS (BEN) | Cyprus | EU/AC | No | 7 | 4 | 2. Requirements & Platform Design | Active | 31 | Proposed for UPAT
71 | 24 | ER | 7. UPAT (BEN) | Greece | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 37 | 4 | 5. Platform Integration, Pilots, and Validation | Active | 37
72 | 24 | ER | 7. UPAT (BEN) | Greece | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 41 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active | 41
73 | 25 | ER | 7. UPAT (BEN) | Greece | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 31 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active | 22
74 | 25 | ER | 7. UPAT (BEN) | Greece | EU/AC | Yes | 5. AEGIS (BEN) | Germany | EU/AC | No | 35 | 4 | 5. Platform Integration, Pilots, and Validation | Active | 35
75 | 25 | ER | 7. UPAT (BEN) | Greece | EU/AC | Yes | 4. STS (BEN) | Cyprus | EU/AC | No | 41 | 4 | 4. Key Components Development | Active | 41
76 | 26 | ER | 7. UPAT (BEN) | Greece | EU/AC | Yes | 4. STS (BEN) | Cyprus | EU/AC | No | 25 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active | 27
77 | 26 | ER | 7. UPAT (BEN) | Greece | EU/AC | Yes | 4. STS (BEN) | Cyprus | EU/AC | No | 36 | 4 | 3. AERAS Models & Model-driven Cyber Range programmes creation | Active | 36
78 | 26 | ER | 7. UPAT (BEN) | Greece | EU/AC | Yes | 4. STS (BEN) | Cyprus | EU/AC | No | 41 | 4 | 4. Key Components Development | Active | 41

## deliverables plan
Deliverables, Ethics, DMP, Other Reports for Project 872735
Deliverables, Ethics, DMP, Other Reports
WP No | Del Rel. No | Del No | Title | Description | Lead Beneficiary | Nature | Dissemination Level | Est. Del. Date (annex I) | Rev. Due Date | Note
WP1 | D1.1 | D1 | Project quality plan | Quality plan defining deliverable reviewing and approval process, ethics compliance procedures and standards/processes for producing project deliverables and publications | UMIL | Report | Confidential, only for members of the consortium (including the Commission Services) | 29 Feb 2020 |  | delivered
WP1 | D1.2 | D2 | Progress Report Year 1 | Report of project’s activities for the first year. | UMIL | Report | Confidential, only for members of the consortium (including the Commission Services) | 31 Dec 2020 | 31 Dec 2021
WP1 | D1.3 | D3 | Progress Report Year 3 | Report of project’s activities for the third year. | UMIL | Report | Confidential, only for members of the consortium (including the Commission Services) | 31 Dec 2022 | 31 Dec 2023
WP1 | D1.4 | D4 | Midterm Meeting | This deliverable reports the activities of the secondments and the progress of the project as presented during the mid-term meeting | UMIL | Report | Confidential, only for members of the consortium (including the Commission Services) | 31 May 2021 | 31 May 2022 | to be agreed with the PO
WP2 | D2.1 | D5 | Healthcare Pilots & Cyber Range Training Requirements Analysis Report | Requirements of the AERAS solution from the perspective of healthcare organisations and actors as arising in the project pilots and the wider domain from Task 2.1, as well as requirements pertaining to cyber range training in the healthcare domain and their relation to existing standards from Task 2.2. | CUT | Report | Public | 31 May 2020 | 28 Febr 2022 | WP2 until november 2022
WP2 | D2.2 | D6 | Platform Requirements and Technology Analysis Report | Platform requirements and an updated state of the art and practice for key technological building blocks. | STS | Report | Public | 31 Aug 2020 | 31 Aug 2022
WP2 | D2.3 | D7 | AERAS Platform Initial Reference Architecture | Initial definition of the AERAS platform. | CUT | Report | Public | 30 Nov 2020 | 30 Nv 2022
WP3 | D3.1 | D8 | CRSA Models and CRSA-driven Cyber Range programme specification language | Describe the specification language of CRSA models used to specify an organisation’s infrastructure layers | STS | Report | Public | 30 Nov 2021 | 30 Nv 2022
WP3 | D3.2 | D9 | AERAS Models and CRSA-driven Cyber Range programme V1 | First version of the AERAS CRSA models (T3.2), and first version of the developed procedures supporting the dynamic and adaptive CRSA models, along with the first version of the hybrid risk analysis models (T3.4). | TSI | Report | Public | 31 Mar 2022 | 31 March 2023
WP3 | D3.3 | D10 | AERAS Models and CRSA-driven Cyber Range programme V2 | Final version of D3.2 | STS | Report | Public | 31 Mar 2023 | 31 March 2024
WP4 | D4.1 | D11 | AERAS Cyber Range Tools – V1 | This document will describe the initial specification and implementation of the AERAS Cyber Range and simulation tools (from Task 4.1) and the visualization components (from Task 4.2). | CUT | Report | Public | 31 Mar 2022 | 31 March 2023
WP4 | D4.2 | D12 | AERAS Monitoring, Assessment and Adaptation mechanisms – V1 | This document will provide the initial design of methods and mechanisms for assessing the performance of the Cyber Range trainees and the CRST evaluation (from Task 4.3). It will also include the initial specification and implementation of the cyber-system, and CSLA monitoring (from Task 4.4), as well as the communication interfaces and adaptation mechanisms that enable the adaptation of the AERAS platform, driven by feedback received from the corresponding internal components (from Task 4.5). | UMIL | Report | Public | 31 Mar 2022 | 31 March 2023
WP4 | D4.3 | D13 | AERAS Cyber Range Tools – V2 | Final version of D4.1. | AEGIS | Report | Public | 31 Mar 2023 | 31 March 2024
WP4 | D4.4 | D14 | AERAS Monitoring, Assessment and Adaptation mechanisms – V2 | Final version of D4.2. | TSI | Report | Public | 31 Mar 2023 | 31 March 2024
WP5 | D5.1 | D15 | Initial Prototype of integrated AERAS platform | Initial version of the integration AERAS platform involving all the components of WP3 and WP4 developed until M30. It will also include the results of the quality assurance and technical testing on the initial prototype of the integrated AERAS platform | UMIL | Report | Public | 30 Sep 2022 | 30 Sep 2023
WP5 | D5.2 | D16 | AERAS Evaluation Framework and Pilot Set Up Guidelines | Define the refined set of KPIs, criteria and methodology to evaluate the AERAS platform. Provide detailed guidelines and documentation to support the piloting phase. Also includes the ethics approval applications. | TSI | Report | Public | 30 Sep 2022 | 30 Sep 2023
WP5 | D5.3 | D17 | AERAS initial prototype pilot validation report | Initial report on the validation of the initial AERAS prototype in the context of each pilot environments covered in the project. | UPAT | Report | Public | 30 Nov 2022 | 30 Nov 2023
WP5 | D5.4 | D18 | Final Prototype of integrated AERAS platform | Final version of the integration AERAS platform involving all the components of WP3 and WP4 developed until M42. It will also include the results of the quality assurance and technical testing on the final prototype of the integrated AERAS platform | UMIL | Report | Public | 31 Jul 2023 | 31 Jul 2024
WP5 | D5.5 | D19 | AERAS final prototype pilot validation report | Final report on the validation of the final AERAS prototype in the context of each pilot environments covered in the project. | PAGNI | Report | Public | 30 Sep 2023 | 30 Sep 2024
WP5 | D5.6 | D20 | Final AERAS evaluation report | Final evaluation report of the AERAS platform, extending the results of the individual pilot evaluations with cross-cutting issues, trends and effectiveness results, spanning all pilots, as well as the applicability of the solution to different critical domains. | UMIL | Report | Public | 30 Nov 2023 | 30 Nov 2024
WP6 | D6.1 | D21 | Dissemination and Communication Plan | Description of the planned dissemination and communication activities and channels | AEGIS | Report | Public | 30 Nov 2020 | 31 Dec 2021
WP7 | D7.1 | D22 | H - Requirement No. 3 | All required opinions/approvals by ethics committees and/or competent authorities for the research with humans must be obtained before starting the relevant activity, kept on file and submitted upon request. | PAGNI | Ethics | Confidential, only for members of the consortium (including the Commission Services) | 30 Nov 2020 | 30 Nov 2021
WP7 | D7.2 | D23 | POPD - Requirement No. 4 | The host institution must confirm that it has appointed a Data Protection Officer (DPO) and the contact details of the DPO are made available to all data subjects involved in the research. For host institutions not required to appoint a DPO under the GDPR a detailed data protection policy for the project must be submitted as a deliverable. | PAGNI | Ethics | Confidential, only for members of the consortium (including the Commission Services) | 31 Dec 2019 |  | delivered
WP7 | D7.3 | D24 | POPD - Requirement No. 9 | The beneficiary must evaluate the ethics risks related to the data processing activities of the project. This includes also an opinion if data protection impact assessment should be conducted under art.35 General Data Protection Regulation 2016/679. The risk evaluation and the opinion must be submitted as a deliverable. | PAGNI | Ethics | Confidential, only for members of the consortium (including the Commission Services) | 31 May 2020 | 31 Dec 2020 | delivered

## WPs
N. | WP Title | Partner | original starting | original ending | Proposed ending
1 | Project Management | UMIL | 1 | 48 | 60
2 | Requirements & Platform Design | CUT | 1 | 12 | 35
3 | AERAS Models & Model-driven Cyber Range programmes creation | STS | 6 | 40 | 52
4 | Key Components Development | CUT | 9 | 40 | 52
5 | Platform Integration, Pilots, and Validation | UMIL | 24 | 48 | 60
6 | Communication, Dissemination, Impact Creation | AEGIS | 1 | 48 | 60
7 | Ethics requirements | UMIL | 1 | 48 | 60