Call: H2020-PHC-2014-single-stage

Objective: PHC-19-2014: Advancing active and healthy ageing with ICT: service robotics within assisted living environments

Type of action: Research and innovation actions

- ROBOHOME2.0

Service ROBOt to monitor, assist and evaluate the elder at HOME 2.0

- ABSTRACT

Robohome2.0 develops, integrates and field tests an innovative robot based system to assist and monitor the elder at home actively promoting healthy lifestyle. The system consists of three hierarchical levels: 1) Core of the system is an intelligent virtual caregiver embodied into a service robot that guides the elder in personalized activities to improve lifestyle through state-of-the art Artificial Intelligence. It also helps the elder in critical everyday tasks and in therapy adherence. 2) The virtual caregiver collaborates with a service layer including a distributed pervasive monitoring system that is transparent to the elder that provides quantitative information on early physical / cognitive decline and social attitude. It is also interfaced with an activity center that selects and adapts activities, tailored to the user’s idiosyncrasies and needs. These activities are mainly conveyed through an adaptive, challenging gamification platform to stimulate motivation and to sustain attention. 3) The highest level is constituted of a users’ virtual community that connects the elder with clinicians, caregivers and other pairs promoting socialization and increased knowledge.

The pole star is to assemble off-the-shelf components in a robust and reliable way to get a low-cost system that can be deployed massively at home. A fully modular approach will assure the system to be tailored on single user needs. The use of the most wide-spread software and hardware standards will maximize interoperability and make the system adaptable to the utmost novel sensors and components. Configurability, personalization and automatic adaptation to elder needs and behavior applies also to interfacing modalities, with the aim of maximizing elder compliance, even when computer illiterate. A pilot evaluates effectiveness and suitability of Robohome2.0 and studies the most appropriate model to seamlessly connect home assistance to supervision by the public health network system and an adequate business model. [2020 char, need 20 less]

- Keywords

Robotics, gerontology, gamification, autonomous navigation, smart objects, sensor network, human robot interfacing, frailty, ambient assisted living, healthy and active ageing, social inclusion, independent living, [add keywords

Call: H2020-PHC-2014-single-stage

Objective: PHC-19-2014: Advancing active and healthy ageing with ICT: service robotics within assisted living environments

Type of action: Research and innovation actions

- ROBOHOME2.0

Service ROBOt to monitor, assist and evaluate the elder at HOME

| Participant no. | Participant organization name | Short name | Country |
| --- | --- | --- | --- |
| 1 (coordinator) | Università degli Studi di Milano | UMIL | IT |
| 2 | Orebro University | ORU | SWE |
| 3 | Giraff Technologies AB | GIRAFF | SWE |
| 4 | University of Plymouth | UOP | UK |
| 5 | SXT Srl - Sistemi per Telemedicina | SXT srl | IT |
| 6 | Fondazione IRCCS Cà Granda Ospedale Maggiore Policlinico | Fondazione IRCCS Cà Granda Ospedale Maggiore Policlinico (PCL) | IT |
| 7 | Politecnico di Milano | POLIMI | IT |
| 8 | Fundació Privada Barcelona Digital Centre Tecnològic | BDIGITAL | ES |
| 9 | Servicio Andaluz de Salud | SAS | ES |
| 10 | Korian | KORIAN | FR |
| 11 | Signal GeneriX Ltd | SG | Cyprus |
| 12 | Unviersity of Malaga | UMA | ES |
| 13 | OREBRO Municipality | KOMMUN | SWE |

| Name of the coordinating person: | Nunzio Alberto Borghese |
| --- | --- |
| Tel: | +39.02-503.16373 |
| E-Mail: | alberto.borghese@unimi.it |

# Table of content

ROBOHOME2.0	1

ABSTRACT	1

Keywords	1

ROBOHOME2.0	2

Table of content	3

1. Excellence	4

1.1 Robohome2.0 General Objective	4

Specific Objectives	5

1.2 Relation to the workprogramme	7

1.3 Concept and approach	10

1.3.1 Overall concept	10

1.3.2 TRL analysis	13

1.3.3 Relationship with National and International Research and Innovation activities	14

1.3.4 Overall approach and methodology	16

Monitoring	16

Assistance	19

Activity center	20

Service Robot and Virtual Caregiver	24

Human Robot Interfacing	26

Community of users	27

Deployment modalities.	28

1.3.5 Sex and/or gender analysis	29

1.4 Ambition	29

1.4.1 Beyond the state of the art	30

Service robot	30

Monitoring	30

Assistance	31

Activity center	32

Interfacing	34

Community of users	34

1.4.2 Innovation potential	35

Patent Search	35

# 1. Excellence

# 1.1 Robohome2.0 General Objective

In Europe, the share of people aged 65 years or over in the total population is projected to increase from 17.1% to 30.0%, going   from 84.6 million in 2008 to 151.5 million in 2060. Similarly the number of people aged 80 years or over is expected to almost triple from 21.8 million in 2008 to 61.4 million in 2060 and the availability of nurses is already becoming an issue in the US. Physical activity, cognitive stimulation, social inclusion, balanced diet, therapy adherence and regular clinical screening promote a lifestyle that slows down the decline, thus enabling the elder to live at his home healthier and for a longer time. This is becoming a priority in Europe as recognized by the EC community: managing frailty and functional decline through targeted interventions, enhancing participation and independence, and promoting systematic-routine screening for pre-frailty are among the specific objectives of the Action Plan on “Prevention and early diagnosis of frailty and functional decline, both physical and cognitive, in older people” of the European Innovation Partnership on Active and Healthy Ageing (Bruxelles, November 6, 2012). Several approaches have been proposed to address these aspects but a comprehensive solution is far to be provided. Moreover, a high emphasis is often put on wearable devices for monitoring that limit the compliance of the users, especially on the long run.

Robohome2.0 is an intelligent system, integrating an existing robotic platform with environmental sensors, and smart objects, advanced user interfaces, a virtual community and an activity center, to provide assistance, transparent monitoring and continuous clinical evaluation of the elder at home through a full-fledged, modular, personalized, and compliant approach.

Such high interactivity is remarked by “2.0” in the title of the proposal borrowed from Web2.0 concept. Indeed, ongoing robotics, smart objects and smart homes and Human Robotic Interfaces (HRI) research plays a key role in this panorama for matching increased life expectancy with the enhancement of the quality of life as people grow old. Robohome2.0 builds upon most recent results in these areas to realize a prototype, test it into real-life environment so to get the ambition to find its way to the market. To this aim,

Robohome2.0 will assemble off-the-shelf components in a robust and reliable way to get a low-cost hierarchical system that can be deployed massively at elders’ home.

Such system will provide several key aspects of clinical monitoring: a) Early cognitive and physical decline will be monitored by the robot observing and analyzing common everyday tasks (e.g. combing hair, preparing coffee), in cooperation with adequate sensorized objects, thus making the elder not aware of being monitored (transparent monitoring). b) Profiling of phone conversation will be done to identify meaningful changes in the emotional content associated to some degenerative diseases. c) Physiological samples (e.g. glucose level, pressure, oxygen saturation) will be provided by an adequate sensors’ network. d) A smart drug dispenser will provide to the elder the right pills at the right time thus largely increasing therapy adherence. e) Activities of Daily life (ADL) will also be monitored (e.g. number of hours of sleep that are related to hypnotic medicaments; home temperature that is associated to quantity of liquids to be taken, and so forth).

The robot will be able also to assist the elder in a confident independent living in finding lost crucial objects (e.g. the mobile phone, the TV remote control, the keys, …)  inside the house and will give the elder feed-backs, recommendations and suggestion through a virtual caregiver avatar.

Robohome2.0 will support an active lifestyle recommending and guiding the elder through a personalized mix of physical, cognitive and social activities that are tailored to the adequate challenging level. We will fully explore gamification to maximize motivation, sustain attention, and train memory and we will explore automatic narration to provide long life engagement. These same concepts will be explored in educational games on the elder diseases and lifestyle.

Gamification will be explored also through the virtual community that will not only support competition / cooperation in physical and cognitive games but also provide support for social games like cards games so that the elder is incentivized to avoid isolation. The community will connect all people involved: caregivers, GPs, geriatrists and elders that will be able to exchange information and increase knowledge.

Activities, assistance, recommendations, monitoring, tuning will be managed by the robot through an embodied virtual caregiver, context aware, that will use the huge amount of heterogeneous data coming from sensors, community and activity center to refine its stimuli, to evaluate the elder’s status and the tune the profile.

To guarantee system use, maximum compliance with the elder is required. Particular care will be put in the design of interfacing modalities not only from the technological point of view, but also from the psychological one to foster the development of stable and positive bonds. A distributed voice command system will be explored to enable voice commands.

Giraff robot has been identified as the most suitable robot for Robohome2.0. Giraff is the result of progressive work in the domain of assisted living and its development was partly financed by the AAL “ExCITE” and FP7 “GiraffPlus” projects. It is basically a robotics base carrying a control PC and an adjustable touch-screen monitor, whose target price for massive production is below 1k Euros. Because of Giraff’s commercial potential it was awarded “Most Promising Innovation” of 2011 by the AAL organization. It has an open software architecture that allows to easily add functionalities as we will fully exploit in Robohome2.0.

## Specific Objectives

In particular, here are the specific Objectives of Robohome2.0:

      - To improve Giraff robot capabilities of interaction with the elder

- To design and implement interfacing modality that promote a good emotional relationship between the elder and Giraff robot.

- To monitor and prevent frailty, age-related cognitive and physical decline and social exclusion, a hands-off network of sensors to evaluate activities of daily living and behavior, transparent to the user.

- To develop a context-aware virtual caregiver able to profile the single elder’s interests and condition, suggesting motivated exercises and activities as well as providing formal and informal carevigers, relative and clinicians information specific to their role.

- To develop assistance in everyday tasks by the Giraff robot.

- To design and implement a personalized activity center system.

- To promote elders health education, self-empowerment, and increase their perceived usefulness in the society aiming at improving quality of life of the elders and of their formal and informal caregivers.

- To field test a complete ecosystem, involving all players, to gather evidence of Robohome2.0 benefits.

- To demonstrate the cost-effectiveness of technology and develop a proper business models for the technology transfer to massively deploy Robohome2.0 within a sustainable healthcare system.

To address these challenges Robohome2.0 will develop the following set of devoted technologies and methodologies aimed at creating an ecosystem to support prolonged life at home:

1. To improve Giraff robot capabilities of interaction with the elder. Giraff will be transformed from a teleoperated robotics platform into a robotic platform endowed with autonomy fully exploiting vision capabilities offered by adding a 3D camera, like Kinect. Such approach will make Giraff an active companion for the elder that can assist in finding objects, gives him/her advice, feed-backs and recommendations, monitors everyday tasks and carries around the activity center to allow the elder exercising in the best time and place (WP3, D3.2).

2. To design and implement interfacing modality that promote a good emotional relationship between the elder and the Giraff robot. A good relationship between Giraff and the elder is a very powerful mean to guarantee motivation in the interaction, easiness and even pleasure and to increase the compliance in system use. To reach this aim a constellation of activities and functions that will be carefully evaluated from the psychological point of view. Gamification, interaction modalities, unified GUIs and assistance in everyday life tasks will be part of this. We will exploit also several social intricacies in the interface with Giraff, like empathy, humour, references to mutual knowledge, continuity behaviors, politeness and trust. The information gathered by the sensors’network along with the inputs provided by the caregivers will be used by the virtual caregiver to create meaningful suggestions to the elder (WP2, WP3, D2.3, D3.3).

Scenario: Mike is wandering around at home, while Giraff, comes to him and says: “Today is the birthday of Matthew, your nephew, why don’t you call him?” Mike illuminates, and with a smile, he looks for his mobile phone to call Matthew. Unfortunately, he could not remember where he put it. He calls again Giraff and asks “where is my phone?”. Giraff activates the automatic location system, and after a while it moves towards the kitchen and takes a picture with its Kinect camera to the phone, partially showing under a box. Giraff sends a voice message to Mike, who can get the phone and calls Matthew. Mike is so grateful that he wants to kiss Giraff for this help… and Mathew too.

3 Monitoring the elder. Monitoring will be carried out while the elder executes the actions of everyday living. Instead of instrumenting the elder, we will instrument some of everyday life objects, like a tea cup, a comb, a fridge handle or other everyday use instruments, depending on elder’s habits. Instrumentation will provide wireless, real-time synchronous data on motion and handling pressure. We will sensorize also objects like a walking stick or a trolley, that are used to walk also outdoor, to evaluate the activity level and parameters for the stability of gait. We will combine vision provided by Giraff with information provided by all the sensorized objects to derive a “signature” of the movement. From these data we will define and validate indexes that will be made available to clinicians for elder evaluation. Transparent tests of clinical assessment of cognitive decline will be administered as spot questions or spot activities intermingled in the everyday tasks and games. We will also explore pitch analysis of phone conversations to early detect on-set of cognitive neurodegenerative diseases. Environmental sensors, e.g. measuring temperature, gas lost, humidity along with the gaming scores, and lifestyle monitoring will drive the virtual caregiver intelligence (WP5 and WP6, D5.1, D5.2, D5.3, D6.1).

4. To develop a context-aware intelligent virtual caregiver which realizes a closed-loop assistance system that cooperates with caregivers and clinicians. The virtual caregiver will analyze the huge amount of heterogeneous data provided by the pervasive monitoring systems and the activity center and a) suggests structured and unstructured physical, cognitive and social activities to the user, adapting the level of difficulty to the current elder’s status. b) tunes the estimated state of the elder according to data from the monitoring systems and the activity center and update his/her profile. c) provide the caregivers and the GPs with the relevant information on the elder status (WP3, D3.1, D3.3).

5. To develop assistance in everyday tasks by the Giraff robot. A key element to promote a solid bond between the robot and the elder is trust. One element that can help creating this bond is solving problems, even small, in everyday life. Loosing objects like keys, reading glasses or mobile phone is common and enabling Giraff to locate them for the elder can promote trustiness in the relationship. A novel system based on distributed microphones pairs with DSP processing capabilities will allow the elder to call Giraff, also when in a different room, realizing a distributed command system. Giraff will  guide the elder in taking prescribed physiological measurements, like blood pressure or glucose, at the correct time intervals through video/animation instructions with voice explanation. A smart drug dispenser, built on miniaturized mechanics and electronics, will made available only right pills at the right time with alert signals remembering the therapy timing (WP3, D3.1, D3.4).

6 To design and implement a personalized activity center, based on the gamification paradigm and fully integrated with the robot and with the community of users. The service will provide cognitive and physical exer-games that can be played preferable with other peers through the virtual community. These games will be designed upon a set of exercises defined by the clinicians to specifically train declining functions. Social activities, like playing cards through the virtual community, will also be supported to promote socialization and avoid isolation that is often the first step towards depression (WP4, D4.3).

7. To promote elders education to a healthy lifestyle, self-empowerment, and increase their perceived usefulness in the society aiming at improving quality of life of the users and their formal and informal caregivers. The activity center will provide also exer-games to support elders education for healthy lifestyle, promoting knowledge and self-empowerment. The approach will be based on ontology automatic narration to define mini-games that can be casted into episodes, matched to pieces of knowledge on the diseases or lifestyle. We will explore how to combine this with stochastic models, like stochastic finite state machines to chain episodes into stories. Reinforcement learning will be explored to steer the story development towards themes tuned on the elder preferences. Popular containers like fairy tales, for which a clear structure has been proposed already at the beginning of last century, or sports competitions will be used. We will also implement a repository of real life stories recorded to Giraff from the elders themselves on a particular theme provided at regular intervals by the community manager (WP4, WP6, D4.2, D6.2).

8. To field test a complete ecosystem, involving all players, to gather evidence of Robohome2.0 benefits. The satisfaction of the end users is the “north star” in guiding the development of Robohome2.0. An end user advisory board will be set early in the project to help keeping the project on track representing the different players: geriatrists, GPs, caregivers, elders, political stakeholders, and service providers. The components and the system will be deployed  in successive stages inside the living labs provided by ORU and SAS in order to test them, early on, in tight link with the developers (WP8, D8.4).

9. To demonstrate the cost-effectiveness of the technology and develop a proper business model for the technology transfer to massively deploy Robohome2.0 within a sustainable healthcare system. We envisage a business model based on service providing by a company like KORIAN (P10). This will be supported by an ICT service provider that provides the cloud that hosts the community and the data. Such system will integrate the components developed by the three industrial partners GIRAFF, SG and by SXT into a flexible, scalable and modular system that can be offered to the elders at home. Such model will be tested through experimentation. In particular, we will evaluate the actual market and available services and test how the different actors involved: from public to commercial entities, non-profit, philanthropic and other forms of social organization, can be involved. Costs and benefits will be made explicit, analyzing also hidden costs in the actual model. This model will regard the whole system as well as its constituents and will be carried out throughout the project development (WP9, D9.3, D9.4, D9.5).

# 1.2 Relation to the workprogramme

| Robohome2.0 Contribution | Milestone | PHC19 target outocomes |
| --- | --- | --- |
| Cognitive impairments, frailty and social exclusion will be addressed with a holistic approach is based on three main pillars: monitoring, assistance and evaluation that are not carried out in isolation, but are interleaved and provided at the users point of need. Data are gathered mainly in a transparent why, while the elder carries out the activities of everyday life. | 5 | Specific challenge: Citizens in an ageing European population are at greater risk of cognitive impairment, frailty and social exclusion. |
| Cognitive impairment will be addressed in a pro-active way, by proposing activities and exer-games that are negotiated with him/her and are adapted to the actual elder competences, status and psycho-physical condition. Cognitive tests of clinical validity will be administered to the elder in a transparent way through the activity centre. Early detection of cognitive degenerative diseases through audio analysis of phone conversation will be explored. | 3 | How Robohome2.0 will reduce the risk of cognitive impairment. |
| Robohome2.0 will stimulate the elder to an active lifestyle in which a personalized mix of cognitive, physical and social activities is suggested. Data from the activity center and monitoring systems are used to evaluate the current psycho-physical status. This allows Robohome2.0 identifying possible physical and cognitive decline. Specific validation of these decline indexes will be included into the project activities; they will be functional to a) adapting the system and the activities mix to the changing conditions of the user; b) follow up the user status keeping the carers informed and eventually favoring appropriate and timely interventions. Robohome2.0 will help the elder in therapy adherence in several ways: it provides home measurement of physiological parameters, it increases elder’s awareness on lifestyle importance through game based education and it provides a smart drug dispenser. | 3 | How Robohome2.0 will reduce the risk of frailty. |
| Robohome2.0 will set-up a community of users that will self-organize to propose connection with elders with similar profiles. The community will support multiplayer gaming and activities to promote socialization. It will also be the place inside which to exchange experiences and knowledge. Robohome2.0 intelligence will make simple suggestions to the users including solicitation to stay in touch with relatives, friends, etc., following the specific setting of the single user. A profiling of social activities through log book and phone conversation analysis will be carried out. | 3 | How Robohome2.0 will reduce the risk of social exclusion. |
| Robohome2.0 will push the elder keeping active with an everyday cognitive and physical training, properly calibrated on the single user’s requirements, assuring rewarding experience and confidence of the subject with her/his capabilities. Robohome2.0 will help the elder in some simple but basic tasks related to independent living such as finding the keys, reading glasses and mobile phone, remembering meals, meetings, drugs to assure prescription adherence and assists him/her with the diet. Specific supervision of physiological parameters (e.g. blood pressure, heart beat, glucose level, oxygen saturation) will be included into the Robohome2.0 system so to alert critical situations, thus allowing anticipated discharge from the hospital and limiting the risks of relapses. Robohome2.0 will communicate the alarm directly to the adequate caregiver. | 3 | with considerable negative consequences for their independence, |
| The carers will be helped in the care practice by daily monitoring information. An increased participation to elder life through the community will allow providing recommendations and informations. Audio-video connection will help in keeping a strong bond also when being physically present is not possible. | 4 | quality of life, that of those who care for them… |
| The progress of the physical decline of elderly people sometimes is abrupt, such as in case of dramatic events (stroke, falls, psychological traumas) but sometimes it is a slow progress which might be even neglected by the relatives. The lack of recognition of worsening could provoke delayed interventions which amplify the decline itself, inducing a negative loop which impacts on the requests to the health and care system. Transparent monitoring inside Robohome2.0 allows to objectively assess cognitive and physical decline continuously over time. Robohome2.0 will communicate periodic reports to the GP, so to allow prompt and tuned intervention in case of worsening conditions. Robohome2.0 will allow private partners, like KORIAN, to provide an effective continuity of care and assistance with public bodies. A business plan will be elaborated on this, substantiated by project results. | 4 | and for the sustainability of health and care systems. |
| Hereafter, an analysis of the crucial ingredients of the aim of the call with respect to the Robohome2.0 proposal is detailed. Service robotics: Robohome2.0 is based on a commercial off-the shelf service robot (Giraff), which will be enriched with adequate features. Transparent Monitoring system: we will monitor the elder through the use of everyday objects without requiring that he/she wears any device or does any particular action. Activity centre: it is based on gamification and provides a customized mix of activities with the adequate level of challenge involving also the community of users. Assisted living environment: proper sensors to monitor the home and elder’s behavior and smart assistance systems will be integrated into Robohome2.0 . | 5 | The challenge is to develop new breakthroughs for active and assisted living based on advanced ICT solutions. |
| Core of the system is Giraff robot that embodies an intelligent virtual caregiver. It monitors him/her through a monitoring network embedded in the house and in cooperation with sensorized objects of everyday use, thus achieving a monitoring completely transparent to him/her. It advices him/her and suggests tailored activities and looks for lost objects. | 3 | Proposals should focus on service robotics in assisted living environments which can help an ageing population to remain active and independent for longer. |
| - behavioural disciplines: to develop emotional bonds with a new body in the house, like a service robot, is fundamental for acceptance and a good interaction. Therefore interfacing functionalities and interface design will be inspired by this. UOP and PCL have complementary expertise. UOP has a strong background on Human Robot Interaction and PCL has a strong background in elder psychology and cognitive functioning. They will contribute to functional design and testing of the components and the whole system to maximize user acceptance. - social disciplines: social scientists from KOMMUN and PCL will assure both in the design of the virtual community and in the evaluation phases that the project has a positive impact both on the social inclusion of the user and on the caregivers (including the family, the carers, the family doctor, the clinicians involved in the care as well as the society, in more extended sense). - health disciplines: regular physiological sampling and clinical assessment and smart drug dispenser provide clinical monitoring and compliance. This will be complemented with providing structured knowledge and education through gamification. Three teams of clinicians (PCL, SAS and KOMMUN) with complementary specializations (GP and geriatrist) and a group of bioengineers (POLIMI) will collaborate in the project to design, develop and validate tests, of clinical validity, based on the analysis of ordinary life actions to assess the physical and cognitive status of the elder. | 4 | The project should combine multi-disciplinary research involving behavioural, sociological, health and other relevant disciplines. |
| Indeed, Robohome2.0 will be built with modularity and flexibility in mind both at the hardware and software level. Environment monitoring will be built upon scalable protocols, like z-wave, already diffused in the domotic field. Sensorized objects will be built integrating a transmission module based on most diffused wireless transmission protocols. The activity centrecentre will allow providing a mix of exer-games specifically tailored to the user and to adapt automatically the level of difficulty to the current user ability. The system will be managed by the virtual caregiver that will implement deductive reasoning on the data received from the monitoring systems, the activity centrecentre and the community and the inputs from the caregivers and the GPS all organized inside the frame of an ontology. The use of off-the-shelf components and standardization, and the integration of already developed sensors and physiological measuring devices, will allow to realize a cost-effective system and meet the widest range of functional requirements. | 4 | Characteristics of the solutions developed should be their modularity, cost-effectiveness, reliability, flexibility in being able to meet a range of needs and societal expectations, |
| Robohome2.0 will be tested from early on in specific living labs identified in Sweden and Spain. This will be fundamental to develop a system that can be really acceptable and compliant with the end users and the elders in particular. The pilot test in WP8 allows evaluating the compliance and suitability of Robohome2.0 also in real apartments inside which elder lives, as well as the safety of the technology. An end users advisory board will be set in the first months of the project with the aim of having an external highly qualified feed-back on project development, from the representatives of all the types of Robohome2.0 users. | 4 | applicability to realistic settings, safety and acceptability to end-users. |
| The activities proposed will be designed having gender in mind, realizing games episodes inspired to at least two themes, one most suitable for female and one for male attitude. Similarly, the avatar of the virtual therapist and all the elements that are gender sensitive, will be designed such that a configuration in the male and female version would be possible. | 2 | Gender and ethical issues should be paid due attention. |

# 1.3 Concept and approach

## 1.3.1 Overall concept

Robohome2.0 builds upon the successful EC funded projects Excites and Giraff plus, coordinated by ORU and FITREHAB and REWIRE, coordinated by UMIL. Robohome2.0 is a hierarchical platform aimed at supporting the elder at home, for a prolonged time, monitoring him/her and guiding him/her to a healthy lifestyle. It consist of three hierarchical levels (Figure 1): 1) a Core layer constituted of an intelligent virtual caregiver that provides feed-back and recommendations to the elder suitable to his/her state and to the lifestyle negotiated with his/her caregivers, embodied into a service robot that provides assistance. 2) a service layer that includes a distributed pervasive monitoring system, transparent to the elder that provides quantitative information on early physical / cognitive decline and social attitude, and an activity center that guides the elder in activities, tailored to elder idiosyncrasies and needs and implemented through gamification, to stimulate maximum adherence and motivation. 3) a Community of users connecting elders and other actors, aimed at improving socialization and knowledge.

1) The virtual caregiver will receive a wealth of heterogeneous information from monitoring systems, community and activity center. It will use an ontology based system to categorize them and propose an effective mix of activities with the proper level of challenge, tailored to the elder status. Further tuning will be carried out by the activity center on the basis of the elder actual performance in the activities themselves. It will help the elder to adhere to therapy prescription by means of a cooperative smart drug dispenser. It will also assist the elder with audio-video instructions and digital animation in taking physiological samples through a set of adequate devices or applications. Welcome messages, controlled randomized sentences of common use, feed-backs from monitoring, recommendations will all be provided throughout the day to the elder through the caregiver avatar, using real-time synthesized speech, for instance using Google APIs. The virtual caregiver will also analyze the historical data on physiological monitoring and psycho-physical assessment, that will be used to identify trends and oscillations and possible warnings related to anomalous values will be automatically generated and transmitted to GPs and caregivers. An initial profile of the elder characteristics, idiosyncrasies and needs is carried out before installing the system at home. A given lifestyle, clinical and diet regimen is defined between the elder and his/her caregivers. This information will be organized into structured knowledge through an adequate ontology that will be used by Description Language to provide recommendations, set-up monitoring parameters (e.g. critical thresholds) and tune the mix of activities.

Giraff robot will be enhanced providing autonomous navigation capabilities. Giraff will be able to reach the elder upon being called, to search for a lost object upon request, to answer for help, to fetch the elder to monitor him/her or to carry the activity center at hands. Interfacing modalities with Giraff will be carefully designed and implemented to favor the establishment of stable and positive bonds. To this aim, an innovative voice command system will be designed and implemented to enable the elder to call Giraff from any room in the house. This is particularly useful when help is needed. Algorithms to compute a navigation path and velocity profile that would produce the best approach to the elder will be identified.

Figure 1 .- The hierarchical structure of Rohohome2.0. The core layer is constituted of the Virtual Caregiver embodied in the Giraff robot and it is displaced at the elders’ home with the service layer. The latter is a modular layer that provides monitoring data to the virtual cargiver and offers functionalities to the elder: activity center, knowledge and assistance. The elder, his/her caregivers and the clinicians are all part of a community of user that promotes socialization and knowledge.

2) The service layer contains the monitoring systems and the activity center. Environmental monitoring will be obtained integrating off-the-shelf devices into a sensorized home network to transfer the data to the virtual caregiver. Low-power devices and standard protocols, like Z-wave specifically developed for this, will be implemented. Elder psycho-physical monitoring will be carried out through an innovative solution transparent to the elder based on task based psychophysical status assessment. This will be based on assessing typical everyday life tasks over time, like for instance, combing in the bathroom or preparing a coffee in the morning, or simply walking with the help of the walking stick. We will sensorize these objects with miniaturized micro-architectures that sense pressure and movement and transmit them through Bluetooth connection to a receiver inside Giraff PC. Objects sensors and information acquired by Giraff’s camera will be synchronized and acquired in real-time to derive a description of the task in terms of pressure and movement temporal profile, that constitutes a "signature" of the interaction with the object in that everyday tasks. The motion pattern will be compared over time to derive quantitative parameters associated to the performance, providing motion degradation indexes. We will investigate which indexes can provide clinical assessment.

The activity center suggests and provides to the elder physical, cognitive exercises and supports social activity. Physical and cognitive exercises will be guided by video-games: the elder sees him/herself on the TVdisplay in the form of an avatar moving and interacting with a virtual scenario with his/her movements tracked in real-time. We will fully explore a novel concept of technology equivalence for which the most suitable device available will be used, allowing the elder choosing not only the best time in the day to exercise but also the best place.

A full layer of gamification will be built on the top of the different exer-games to promote socialization and to make games long lasting. This will be based on automatically building a story, made of episodes matched to the exer-games, on top of the exercises exploring novel automatic narration techniques combined with stochastical models. This gamification layer will provide episodes aimed to educate the elder on lifestyle and therapy.

3) The virtual community of users, will act as a bridge towards other elders and with relatives, caregivers and clinicians. Audio-video communication will be fully supported to enrich the interaction: exploiting technological equivalence, the elder will be able to communicate through Giraff display, home TV or smart phone. This will largely increase the use of the system, improve patient to doctor communication and promote socialization.

Scenario. Mary is sitting on the sofa and Giraff notices through the remote control that she is changing the TV program often. Giraff remembers to Mary that it is the birthday of her nephew and that he is having a party with his school-mates. It asks Mary if she wants to participate to the party virtually. Mary is dubious, but Giraff files the request to Joseph through smart phone and he is very happy to involve Mary virtually in the party. Robohome2.0 quickly sets a streaming bi-directional video connection through the smart phone of Joseph, directly to the TV of Mary, who is extremely happy to join in singing the birthday song with all.

Moreover, a set of specific services tailored to the elders will be designed and deployed within the community of users. These services will be oriented to foster motivation and adherence to the proposed solution. These services will leverage on gamification by publishing the activity performance of the elders to promote cooperation and competition that reinforce motivation. The communication services will also be deployed to encourage and improve the socialization between the elder people and other community users. Moreover, it provides connection with the other elders. We will implement algorithms based on the analysis of relationships inside the community to automatically identify groups of elders that may share the same interests and have a similar status. These clusters can also be used to refine patients profiling. The community will also be a source of collective knowledge that can be increased by all users through the exchange of information among them. Such knowledge will have a multi-media format and involve all the aspects of the elder life: therapies, illness, psychological issues, social issues.

Scenario. Robohome2.0 proposes as month theme, “the political changes in Spain, after King Juan Carlos in 1978 restored democracy in Spain”. A lot of stories were recorded and sent to the community and the story of Francisco, who entered in politics that days to serve its city, Seville, was prized the best by the community members and made public on the Robohome2.0 community site. A journalist of “El Pais” discovered it, interviewed Francisco and wrote together a small book on the organization of elections and the first steps of political parties in that period, in Seville. The book was a large seller one.

These three components will not work as stand alone but they will cooperate, under the supervision of the Virtual Caregiver, to provide key functionalities: a) regular clinical monitoring to control physiological parameters critical for the elder’s diseases, b) cognitive and physical assessment to early detect decline, c) lifestyle and social behavior evaluation to early detect risk of exclusion, d) an activity center that suggests and guides the elder in personalized cognitive and physical games, e) actively promotion of social activities, f) increase of knowledge in the elder’s diseases to promote empowerment, g) assistance in everyday tasks, and h) meaningful interaction with Giraff and the other components.

These functionalities, are not isolated but they are tightly interconnected. For instance, regular physical exercise has been shown to be effective at maintaining and improving the overall health of elderly individuals,,.. Physical fitness is associated with higher functioning in the executive control processes, correlated with less atrophy of frontal cortex regions, and with improved reaction times compared with the sedentary. Social interaction, and specifically high perceived interpersonal social support, has also been shown to have a positive impact on general mental and physical wellbeing, in addition to reducing the likelihood of depression,,,. We will fully exploit the unique possibility of Robohome2.0 of addressing all these aspects to provide functionalities through the best mix of components for each elder. Moreover, a closed loop monitoring and assistance system will be developed. It will continuously update the elder profile upon the data collected by the activity centre and the monitoring systems; it will recommend a mix of personalized activities, having  a challenge level suitable to the elder status; it will provide tailored monitoring systems to elder needs.

Such approach does call for various competences that are well represented in the multi-disciplinary teams of SAS, PCL and KOMMUN and in the consortium as well, that includes bioengineers (POLIMI), experts in HRI (UOP) and ICT researchers by ORU, UMIL, BDIGITAL and UMA. The consortium will allow developing strong inter-displinary research, promoting a bidirectional translation research approach, facilitating the communication between the non-technical and technical teams to come up with a shared view on how the Robohome2.0 platform should be (WP1, WP2). Plenary meetings at the different partners sites in the first stage of the project, will allow to better elucidate problems and current solutions and to make clear the current technological offer.

## 1.3.2 TRL analysis

The project is positioned in different Technology Readiness Levels (TRL) considering the various functionalities to which it is aimed and the whole platform.

Regular clinical monitoring of physiological parameters will be accomplished integrating off-the-shelf components that will be already validated and therefore they are already products on the market. These components will be possibly integrated with the virtual caregiver that will provide instructions in audio-visual form. Data will be transmitted to the virtual caregiver and from it to the community. This activity is expected to be at TRL7 at the end of the project.

Cognitive and physical assessment. A very innovative approach will be followed here. Sensorized everyday objects (TRL3) will be combined with motion acquisition through Giraff robot to provide synchronous motion and pressure data. Motion acquisition requires Giraff robot to approach the elder and orient the camera adequately with respect to the elder (TRL2). The fused data will be used to segment movement into components (TRL4) and derive a degradation index of clinical validity (TRL1). The high effort in this work in Task5.1 and 5.2 will provide a TRL6 technology at the end of the project. Voice pitch analysis explored for early detection of onset of cognitive degenerative diseases it at TRL1 presently. We expect to obtain a technology at TRL4 by the end of the project. We will also explore cognitive and physical exer-games provided by the activity center from which specific assessment parameters can be evaluated. The starting point is TRL1 and we expect to have the parameters validated by the end of the project (TRL7).

Lifestyle and social behavior evaluation. We will use standard components like z-wave, that will be assembled into a modular and flexible network (TRL8/TRL9) and integrate it with the robot. Its information will be integrated with data from monitoring and from the activity center to update the elder profile and tune the recommendations and monitoring (TRL4). We expect to provide a technology close to TRL8.

Activity center. The activity centre will be largely based on the IGER game engine that is being currently validated on the field within the REWIRE project (TRL5). We will extend it to support a mix of exer-games involving also cognitive exercises and support for multiple output devices. We will build a new layer to address knowledge acquisition and long term motivation through gamification. Both these extensions will be starting from TRL2. We expect to arrive at TRL7 with the pilot.

Promotion of social activities. This will be supported by a virtual community of users that will be built starting from BDIGITAL experience inside the projects REWIRE, BACKHOME and SAAPHO, in which it has coordinated the work related to the implementation of the community services and environment monitoring (TRL5). The community features will be tailored to requirements of Robohome2.0 and further developed. It is expected to arrive at TRL7. The community will also support multi-player games, typical card games. Multi-player view will be integrated through multiple video streaming through for instance WebRTC technology (TRL8). Multiple videos will be combined with a dynamical graphical scene showing score, cards and other relevant information (TRL2). We expect the component to be at TRL7 at the project end.

Increase of knowledge. This will be mediated by the community of users (TRL5) and by continuous education through gaming created through automatic narration (TRL3). We expect to arrive a TRL6 by the end of the project.

Assistance in everyday tasks. Proposed systems on the market for locating objects have limitations in range and power consumption. The technology is presently at TRL3 but it is likely to increase its level at the time the project will start. We will explore this technology in combination with robots navigation. We expect to bring this methodology at TRL5 Cooperative drug dispenser will be built upon micro-architectures already explored by SXT (TRL5) integrated with micro electro-mechanical devices. We expect to bring this component at TRL8 by the end.

Meaningful interaction with Giraff and the other components. Tight collaboration between psychologists, HRI experts and ICT researchers will allow building meaningful and attractive interfacing modalities. We will start from UOP and PCL competences (WP4) and shape Robohome2.0 throughout the development to promote compliance with the elder and provide HRI and GUIs at TRL7. In particular, we will explore an ecological approach for both the autonomous navigation of the Giraff and its approach to the elder, starting from the work of UMA (TRL4). We expect to arrive at TRL7 at the end. Lastly, an innovative distribute voice command system will be realized to provide a natural interface between the elder and the robot, starting from the experience of SG in signal processing (TRL4). We expect to arrive at TRL7 at the end.

## 1.3.3 Relationship with National and International Research and Innovation activities

The theme of elder assistance and aging well has been addressed by several research projects both under FP7 and AAL frameworks aimed at improving the quality of life of elder people, some targeting also disabled people. The idea of having a robot interacting with an assistive environment has been explored in the Companionable project (http://www.companionable.net/), where a mobile robotic companion interacts with a smart home sensorized environment with the aim of monitoring the elder against cognitive decline and stimulating cognitively him. Moreover, it can detect adverse events like falls. The Robo M.D. project was aimed specifically to detect critical situations like falling and launch an alarm. These concepts have been further developed in the Excite and Giraff plus projects (http://www.giraffplus.eu/), coordinated by ORU. In Giraff plus a wide range of environment and activities signals are used to monitor the elder and to provides a pictorial representation of his/her activities that can be used to assess her/his lifestyle. Monitoring is complemented with a robot that provides video-communication with his caregivers. The Robot Era project (http:// www.robot-era.eu/robotera/), provides a complementary view providing a set of robots that assist the elder in specific functionalities of every day life like moving objects . On the other end, a few projects have explored the use of low-cost technology to support the elder at home. The project Mobiserv (http://www.mobiserv.info/results/) will deliver a robotic prototype of an open standard-based personal platform capable of sensing the user’s personal environment and adapting to the user’s behaviour. The Oldes project (http://www.oldes.eu/home.html) is aimed to offer stimulation and remote overview to improve the quality of life of elder people, through a care platform designed to ease their life in their homes. More recently the Wecare AAL project (http://www.wecare-project.eu/) explores the social aspects in building a community to support the elders to live alone.

Several projects have been based on developing wearable devices to monitor elders at home. The Rosetta project (http://www.aal-europe.eu/projects/rosetta/) was aimed to monitor activities of elderly persons with sensors to generate alarm when unexpected activity, like a fall, is detected and support the elderly in carrying out daily and recreational activities. Monitoring of Parkinson people is carried out similarly in the Cupid project (http://www.cupid-project.eu/) that completes monitoring with specific rehabilitation exercises. Happy Aging (http://www.aal-europe.eu/projects/happy-ageing/) is a system for lifestyle monitoring, for issuing reminders and detection lack of activity or unusual behaviors. Hope (http://www.hope-project.eu) is targeted to Alzheimer patients and can provide alarms and communication with health professionals. It connects several house sensors and gives reminders and warnings via voice. eCaalyx (http//www.ecaalyx.org) integrates physiological sensors to monitor the elder at home that are worn and whose controlled is housed in a pocket of a t-shirt. The aim of the Interaction project (http://cms.interaction4stroke.eu/drupal/) is to develop a system based on e-textile and sensors to monitor motion and force exchange between a subject and the environment and to profile his activity. Using a similar approach, the Psyche project (http://www.psyche-project.org/) has developed a monitoring system based on e-textile and portable sensing devices for the long and short term acquisition of data from screened, patients, typically affected by mood disorders to manage psychiatric illnesses. However, the need to wear sensors limits strongly the usability of these systems that are still bounded mainly inside the research domain [PCL comment on this]. All these projects improve the elder life in some of its aspects; however they come short in providing a complete support to the elder in terms of monitoring and assistance, as well as providing connection with his/her caregivers. A different approach was followed in the Fitrehab and Rewire projects (http://www.rewire-project.eu), coordinated by UMIL, in which a hierarchical architecture has been developed to support rehabilitation at home. Rewire, in particular, has shown that assembling off-the-self components, patients discharged by the hospital, are enabled to continue exercising intensively at home, still under clinicians supervision. Monitoring the performance, adapting the exer-games at point of needs and motivational feed-back to the user and informative feed-back to his/her supervisors are deemed to be a winning strategy. Robohome2.0 builds on this concept and extends it to support the elder at home. Besides research projects, a few companies have approached assisted living market through robotics. Kompai, developed by Robosoft (http://www.robosoft.com/robotic-solutions/healthcare/kompai/index.html ) inside the Domeo project (http://www.aal-domeo.eu/) is a companion robot, meant as an open robotics architecture with, presently, limited capabilities. Giraff robot, developed over the years by GIRAFF (P3) (http://www.giraff.org/) is a robotics platform aimed at containing the costs on one side, and on the other side it has been developed with particular attention to a good interfacing with the elder and it has been selected as the most suitable service robot for Robohome2.0.

The other pillar of Robohome2.0 is the introduction of gamification. Games, or better exer-games that mix exercising and gaming, have been widely explored in EU projects mainly targeted to rehabilitation as a good way to stimulate, motivate and guide patients through exercises. In the Script project (http://www.scriptproject.eu/), games are combined with small robots and are aimed at guiding patients in the rehabilitation of wrist and hand functions. Also should be mentioned the project H_Cad, which was aimed to rehabilitate cognitive dysfunctions was carried out through tasks used in occupational therapy inside a controlled environment. In the EU project Backhome, how to provide cognitive rehabilitation tasks to people with severe disabilities is investigated. Currently, three categories of cognitive games have been taken into account: perception; attention and concentration; and memory. It is beyond the scope of BackHome to develop, validate, and illustrate clinical outcomes, however the intention is to validate the efficacy and stability of the proposed solution within a future evaluation. Cupid is aimed to Parkinson patients and specific exer-games have been developed which provide audio, visual and tactile feedback. The RGS system is aimed at upper arm and develops a game aimed at guiding the arm in 3D space. However, few of these projects go beyond basic graphics and gameplay resulting into exer-games of little attraction as they lack addressing good game design guidelines. Moreover, they have limited configuration capability and adaptation as well as monitoring is not provided. Moreover, the repetitive nature of their game mechanics make them not fit for prolonged exercising. The IGER (Intelligent Game Engine for Rehabilitation) game engine, developed inside the Rewire project (htttp://www.rewire-project.eu), is an exception. This is a game engine: a set of tools that are aimed, on one side at making the games run on the machine they are designed for, on the other end, help the developer in creating games that share the same features. Therefore, IGER has allowed a fast prototyping of new games, reusing the gaming functionalities that been developed for previous games. In particular, it contains the functionalities required to configure and adapt the exer-games to the user and to supervise him while exercising at home, to make exercising at home feasible and robust, on one end and, IGER offers therefore a good starting point to Robohome.

## 1.3.4 Overall approach and methodology

Activities required to develop Robohome2.0 can be grouped into four main areas: clinical and behavioral monitoring, assistance, activity promotion, and virtual communities. We will here analyze the research and development required inside each area.

### Monitoring

The main element that limits the prolonged living at home of the elder is monitoring This has different facets that all contribute to make the elder and his caregivers feel safe and supervised at home. In Robohome 2.0 monitoring will include:

- Clinical monitoring, to assess the elder’s clinical status and to manage alarm situations in due time.

- Physical monitoring, to provide a quantitative evaluation of the motion control capabilities of the elder, especially related to maintaining balance.

- Cognitive monitoring, to monitor the cognitive residual abilities of the elder through time.

- Social monitoring, to provide a qualitative evaluation of the elder social habits.

- Environmental monitoring to guarantee safety (e.g. gas alerts) and to acquire environment data (e.g. humidity, temperature) that influence activities, and lifestyle (e.g. pressure sensors under sofa and bed mattress).

Clinical monitoring is aimed at maintaining under control the acquired diseases through regular drug assumption and regular sampling of physiological parameters. Therapy compliance will be helped by Robohome2.0 through a cooperative smart drug dispenser. Several solutions have been proposed for hospital use, in which many different drugs have to be provided to many different patients, , through a centralized control integrated inside the hospital. We will develop inside Robohome2.0 a novel, low-cost, simplified solution dedicated to one person (Task 3.7). This will be constituted of a set of drawers, each with a remotely-controlled, specific electromechanical lock managed by the virtual caregiver. Only the right drawer is open at the time in which the elder should take prescribed pills. At the same time Robohome2.0 warns the elder through the devices available: Giraff, smart phone, TV. This approach still requires that the real caregiver or the elder fill the drawers at the beginning of a week, but it then guarantees that the right pills are taken at the right time.

Huge progress has been achieved by ICT in the last years for at home clinical monitoring, For instance, Zephir technology has proposed a suit for clinical telemonitoring and Alive a specific suit for heart monitoring. More recently IMEC has proposed wireless ECG, EMG and EEG devices that can be connected to an android phone to enable reliable long-term ambulatory monitoring of various health parameters such as cardiac performance, brain activity and muscle activity. Portable devices for glucose measurement are also available with 42 different models available only in UK and sampling through Android phone has been recently developed. All these systems are nowadays a reality for many elder people, who are given the capability to monitor their own health, taking at-home the physiological samples required. To these devices, specifically certified for the health sector, more recently devices targeted to fitness and wellbeing are being developed. Samsung and Apple have recently announced the integration in their smart phone on sale this year, apps for monitoring a comprehensive array of vital signs, encompassing heart-rate, blood pressure, temperature, oxygen saturation and lung function. Although no approval as a medical device has been announced yet, they do provide and interesting consumer alternative.

In Robohome2.0, the most convenient sensor/system to measure a specific required clinical parameter will be identified in Task2.1 with the most suitable interconnecting network, and realized in Task 5.6. Data will be provided to the Virtual Caregiver. This will be able to guide the elder and advice him through video and voice feed-back, while taking samples. Although ICT has made the control of diseases possible at home, by using such kind of “user-friendly” solutions, some times, it is still difficult to understand the reliability of the final measure, without remote or direct assistance of caregivers. We will take advantage of Giraff’s capabilities to provide direct video-connection to the GP or remote caregivers when physiological samples have to be taken.

These two activities will be mainly technological and they requires clinical validation. Nevertheless an important piece of research is required to find the best solution in terms of usability and motivation.

Physical monitoring will be performed with three main modalities. In the first modality, identified common assessment tests, will be carried out at-home under remote supervision of the caregiver through audio-video communication (tele-monitoring). Smart Giraff navigation system allows to carry out the tests in the most comfortable situation and location for the elder. In a second modality, we will substitute the clinician with the Virtual Caregiver that will remind the user not only when he/she has to perform a test but it will also guide him/her step by step during test execution through explicative audio-video animations and providing also the ICT support to complete them. In this second modality, the elder will move in front of Giraff that will pick up the elder movement through its 3D camera and reconstruct his/her movement. It has already been shown that 3D cameras like Kinect returns a complete description of the skeleton motion, with data of good quality. From motion data, the score will be automatically computed and sent to the virtual caregiver. Most suitable tests will be aimed to balance and they can be Berg-balance, TUG or Morse Fall Scale to prevent falls. These tests have been clinically validated and can be used to obtain an objective picture of the physical / cognitive status of the patient. Validation of the tests administered in this autonomous modality are integral part of the proposed project (Task 3.6).

In the third approach, monitoring can be carried out while observing motion associated to everyday activities. The progress in micro and nanotechnology and the availability of miniaturized sensors, has made available a huge range of small wearable devices for the consumers market, from simple pedometers to computerized trainers that allow measuring heart rate, calories consumption, local speed and additional parameters of the physical exercise (e.g. http://www.polar.com/us-en/products). Fitness is still the leading application for this; for instance personalized training paths can be acquired from the web and displayed in real-time along with the actual physical data (heart beat and position) to provide to the athlete both environment and physical information (e.g. http://sites.garmin.com/edge/). Similar principles have been applied to develop products aimed at tracking and profiling human motion. For instance Xsens was the first to develop motion sensors based on the integration of accelerometers, gyroscopes and magnetometers, Gait-up has developed sensors aimed to provide a profiling the user with accurate evaluation of the activities through worn sensors. These devices are usually mounted in charming cases that makes these objects fashionable and trendy. Miniaturization of sensors and integration in the clothes has been also pursued in the Interaction EU project (http://cms.interaction4stroke.eu/drupal/), through smart textile. New sensors will communicate with a Smart phone that will act as a Hub and as an integrator of these data into a lifestyle evaluation like for instance through the Digifit or Zausan apps. Such apps often integrate both environment and physiological data. However, on one side, the hereabove mentioned sensors allow collecting limited amount of information, on the other side they require that the user wearing them that makes their compliance limited for long time use.

A different approach has been proposed in very recent EU projects that have developed novel technological approaches based on sensorized objects. Caretoy (http://www.caretoy.eu/) proposes wireless sensorized toys mainly composed of two soft air-filled chambers connected to a pressure sensors made by elastomers and shaped as a cylinders and a rigid case containing the electronic unit to discriminate the grasping actions of right and left hands separately. Such system provides a gross discrimination of actions on the object. CogWatch (http://www.cogwatch.eu/) introduces a device that contains a 3-axis accelerometer and 3 axes force sensitive resistors in a small package that fits to the base of objects such as mugs, jugs and kettles.

We will further develop these approaches by combining motion acquisition through Giraff with sensorized everyday object to provide monitoring transparent to the elder: he/she will be monitored observing the elder while carrying everyday tasks, like combing hair or preparing coffee or walking with the walking stick. Data acquired synchronously from the object and from Giraff’s camera allow to derive a detailed characterization of movement profile as reported in Section 1.4.1. Suitable indexes the link deterioration in motor performance with clinical scales will be defined. This would allow an automatic continuous monitoring of the elder with daily assessment that allows an early detection of deterioration in the motor performance (Task 5.1 and 5.2).

This activity has a large research and development component in the design, development and experimentation of transparent monitoring.

Cognitive monitoring is based on evaluating the basic cognitive function: memory, reasoning, orientation [PCL, SAS, MUN, KORIAN references] and it is aimed at detecting cognitive deterioration associated to onset of degenerative diseases like Parkinson, Alzheimer or Fronto-Temporal Dementia. As for physical monitoring, assessment is carried out through validated tests that may be tele-operated. We will explore the possibility to operate these tests also by means of the Virtual Caregiver. QMCI or mini-mental test seem particularly suitable to be transposed into a computerized form, because of their being constituted of questions with multiple choice answers. [PCL, SAS, KORIAN are computer based forms already available?]. The best graphical form for the questionnaires will be designed. We will take full advantage of Giraff to show to the elder the questionnaire on the display, reading them through the Virtual Caregiver Avatar, collect the answer through touch screen display or gesture recognition developed in Task 4.1. The avatar will provide voice feed-back, adequate to the actual performance, to encourage the elder and increase effectiveness of the administration. Alternatively, smart phone based applications will be considered like Doctot. We will also explore the use of TV to administer these tests, in which case a TV remote controller interfaced with the Virtual Avatar will provide the selection of the answer.

We will go one step further and use the Virtual Caregiver to provide assessment in a transparent way similarly to physical monitoring. In this case, cognitive data for the assessment will be gathered through specific spot questions proposed at the beginning or at the end of any typical activity, like watching TV. This modality to carry out assessment will be analyzed and validated by clinicians in Task 3.6. Additional information will be provided by data provided by cognitive activities, like puzzles, riddles, Simon or other memory games made available by the activity center (Task 4.3). Additional information can be derived by the analysis of the performance in social games, like playing cards (time course of winning rate). We will explore how to correlate all these data with clinical scales (Task 5.2).

This activity has a large research and development component in the design, development and experimentation of transparent monitoring.

Scenario: Ann sits down on her sofa and switches on the TV. Robohome2.0 has pending questions to complete cognitive evaluation. It realizes that the TV has been switched on, selects the TV output port, and sends to the TV the Virtual Caregiver avatar to welcome Ann and ask her politely the “daily question”: “which day is today?”. Ann answers correctly, the avatar smiles and says bye to her. The TV program of the last channel selected appears to the screen.

We will also develop a second form of cognitive transparent monitoring. Degenerative diseases in their early stages are often associated with anxiety and mood disturbances, psychoses, compulsions, anxiety, and agitation. We aim to early detect these symptoms through analysis and profiling of phone conversations as descried in Section 1.4.1. We will combine this information with the analysis of time of day and frequency of the calls as some people with dementia phone their loved ones over and over again – particularly in the middle of the night. This can be very frustrating and distressing. The person with dementia may forget that they have already called, or may be insecure or anxious, therefore changing the voice spectrum of the conversation. This combined information may provide evidence of early cognitive degeneration (Task 5.4 and Task 6.6).

This activity is mainly research in the development and experimentation of transparent monitoring of degenerative diseases through profiling phone conversations.

Social monitoring. This is a new aspects that is becoming more and more important in a society in which the familiar bonds are less tight than in the past [PCL, SAS, KOMMUN, KORIAN references]. One of the main risks for the elders, highlighted in the call, is exclusion and isolation that can easily lead to depression and poor quality of life. Although an automatic identification of all the possible activities is beyond reach, we will identify some of these that can be representative. The duration and frequency with whom the elder exercise in group, provided by the activity center (Task 4.8), the logbook of activities (e.g. teaching at third age University, giving courses, going to theatre, concerts), registered through a digital log book made available by the virtual community, degree of interaction with the community (Task 6.3) can all provide an estimate of the elder social behaviour.

This activity will be mainly technological, based on SW development.

Environmental monitoring. The possibility of using ICT technology to control the appliances and supervise the house, has long been recognized as an interesting business opportunity in the domotic field: gas and light alarms have been developed as stand alone (e.g. http://www.beghelli.it/), or as devices that can be also integrated in a house control panel (http://allarmiwireless.net/shop/). The latter approach is particular suitable to add new devices at need. More recently this approach has been extended to assisted living environment (e.g. http://www.tunstall.co.uk/) in which some of the sensors contribute to determine the habitudes of the elder, like pressure sensors under the sofa or under the bed, presence sensors or TV usage. BDIGITAL has already realized a prototype that integrates inside a single complex sensor temperature, humidity, luminosity and gas alert, that has been inserted into a low-cost micro-architecture able to transmit the data remotely through wireless connection Such architecture based on a Raspberry PI low-cost micro-controller will be fully exploited in Robohome2.0: most promising off-the-shelf sensors that fulfill specifications set in WP1 will be identified at project start in WP2 and integrated into a modular network that uses the recent novel standards, like low-power Bluetooth for minimal intervention and longest battery duration. Protocols widely diffused in the domotics field, like Z-wave, will be adopted to maximize extensibility of the system. Such network will feed the data to the ontology defined in Task 3.4 and used to refine the recommendation and suggestions to the elder (Task 3.5).

This activity will the result mainly in a technological effort (Task 5.3).

### Assistance

Assistance is provided by the virtual caregiver to the elder to support him/her during dailylife, to provide recommendations and to promote activities provided by a dedicated activity center. Assistance in everyday life is a growing market, mainly developed as Apps for smart phone (e.g. http://www.hexstudio.com/, https://www.easilydo.com/). They are built mainly on two concepts: improving the functionalities of a digital agenda and linking the data coming from the connected devices. We aim here to complement these functions with a specific functionality (Task 3.8) that implements a locating service that search for objects that are typically lost by the elder: reading glasses, phone and keys. For tagging objects, there are new emerging solutions based on sticks or key rings to be used with specific Apps, but elderly people would have still to find by themselves the objects and, moreover, the mobile phone has not to be lost. The Phone can be located through GPS signal, but usually GPS signal cannot be received at home. Also RFID technologies already are used for tagging objects. However, RFID tags devices require a reader to be placed inside all the rooms, with a high impact on the house. We will explore in Robohome2.0 an alternative based on miniaturized active tags described in Section 1.4.1. We envisage the elder asking Giraff to go and search for the object through the distributed voice command system (Task 5.5) the lost object. The same functionalities will also made available through a phone App (Task 6.6) or thorugh Giraff itself, using its touchscreen display or the TVmonitor.

Research and development applies to the location of everyday objects.

Scenario. Mary is at Elif’s home when she realized that she has not her keys with her. She is upset as she thinks that she has lost her keys. She call Giraff with her app and asks it to find if the keys are in the hose. After a while Giraff’s replies sending to Mary’s mobile phone a picture taken with its 3D camera in which the keys are shown over the Kitchen table. Mary is relieved, she calls her daughter who has a copy of the keys, to get into her house.

Diet is also an important aspect of a good lifestyle. Suggestions and recommendations on diet will be gathered through the community and the caregivers and proposed as recommendation by the Virtual Caregiver through Giraff of through a specific app (Task 6.6).

This activity will the result mainly in a technological effort with leading technology.

Scenario. Ann has invited her daughter and nephews but she does not know what to cook. She calls Giraff and select the kitchen button on the display: a set of recipes, compatible with her diet regimen, are displayed, organized along a few dimensions like time of cooking and complexity. She chooses a “Carbonara pasta” and a list of ingredients is displayed on Giraff monitor and sent to her android phone as an SMS. Ann prepared then the dinner with the help of the instructions displayed by Giraff one step at a time. Her dinner was a success. She was very happy and gives this feed-back to Giraff, that changes the recipes order, ranking higher the successful recipe.

### Activity Center

The Activity Center supports social activities and proposes and guides the elder through tailored physical / cognitive exer-games. The activities and their goals will be planned and negotiated between the elder and his/her caregivers, adopting an empowerment strategy.

Weight Shift

Figure 2 - A screenshot of one of the exer-games realized with IGER: "fruit catcher". The user has to catch fruit falling from the tree, moving laterally. His movement is shown on the TV and surveyed by a Kinect just below it.

Exer-gaming has received a strong push in the last year by the novel tracking devices, like the Nintendo Wiimote Controller and Balance Board, the Sony Move, and the Microsoft Kinect, that have revolutionized the way people play video games, making interaction much more intuitive. It was soon recognized that these devices allow the acquisition of motion and interaction data of good quality that be useful in many domains. Alongside, powerful games engines have been made available recently under open source license, or with limited costs (e.g. Unity or Panda3D). This, paired with the rise of mobile gaming, has opened the game development process to smaller teams, who can no sit beside the big corporations, complementing their offer. On the other side, it has allowed the incorporation of novel ideas coming from the research fields into new or existing video-games with less technological effort than before. This has allowed UMIL developing the IGER game engine inside the REWIRE project, that will serve as the nucleus of the game center. IGER integrates methods of computational intelligence for users’ monitoring and adaptation, IGER games are fully configurable so that they can be tailored by the clinicians to the users needs and exercising goals, and they are continuously adapted in real-time to the user’s performance through a Bayesian framework that updates game parameters to provide an adequate difficulty level while keeping the elders within the therapeutic constraints specified by the clinicians. The gameplay is continuously monitored using a fuzzy system (leveraging for instance the therapists’ knowledge) to avoid wrong postures or wrong movements, which would make exercising more harmful than useful. A novel color coding feed-back is used to inform the user in real-time on wrong movements. IGER also integrates a personalized avatar that advices the user and guides him through the exercising sessions. Controlled randomization of assets, targets, voice feed-back avatar choice, and facial animation are all aimed to increase compliance with the therapy, . Finally, several input devices can be interfaced to IGER thanks to its specific input abstraction middleware.

The cognitive and physical exercises defined by the virtual caregivers in Task 1.2 will be analyzed and transformed into mini-games (Task 4.3), in which the desired trained movement or function has to be used to achieve the game goal. The gameplay will be designed to be fully configured to the elder ability and idiosyncrasis and adapted by the Virtual Caregiver to the actual status and the elder will always be under monitoring by Robohome2.0.

This activity will the result mainly in a technological effort with leading technology.

Scenario. Giraff approaches Mary and asks her if she is ready for her daily exercising session. The Virtual Caregiver shows her the daily program and at the same time it analyzes the environment data downloaded from the environmental sensor network. The Virtual Caregiver analyzes the data and realizes that it is too hot and humid today to maintain the same level of exercising as the days before and downgrades the games difficulty. It sends a message to both the elder and the caregivers and allows Mary to start her daily exercise.

Scenario. “Mr. Cottrel is approaching Giraff for exercising. Upon termination, the Virtual Caregiver avatar asks him to take heart beat measurements pressing the adequate button of his Smart Phone. The Virtual Caregiver realizes that the heart rate is much higher than usual for the same amount of physical activity. It launches a warning to Mr Cottrel’s GP, and informs also the elder that a tele-consulting session will start soon”.

Motivation is indeed at the heart of keeping exercising. However, exer-games alone are not sufficient to maximize elders motivation. Moreover, they might have the side effect of improving elder isolation. For these reasons we will fully explore Gamification in Robohome2.0. Gamification involves the use of game design and game mechanics for a purpose other than entertainment. Gamification techniques leverage people's natural desire for competition, achievements, status, self-expression and closure. In a single-player settings, gamification concerns designing gameplay such that the user feels rewarded when accomplishing a task. Intrinsically, this can mean adding a game on top of the exercise, providing a goal and meaningful gameplay, as well as feedback,  Extrinsically, to this aim, various and targeted reward systems can be devised, for instance: points or coins gained, achievements and levels reached certified by virtual badges, improving in completing a game (e.g. a puzzle). Such rewards can be shown for instance by a progress bar and spent inside a community of players, showing relative achievements through ranking or leader boards in which top players achievements are described. In a multi-player setting, gamification can be implemented through direct or indirect competition, or through collaboration. Indirect competition follows the use of scores, virtual badges and achievements, when they are integrated into a social engine. Direct competition can be implemented by providing multi-player play, so that two people can directly compete. This is already available in many online games, especially sports and shooter games. Such virtual competition is considered extremely challenging and it allows athlets from different parts of the world to compete and compare their performances. At last, collaborative games can be played with multiple people, all pursuing the same goal. This can be for instance a puzzle built in collaboration or a riddle solved discussing in a group. Collaboration allows less harsh, not competitive activities to be performed in a social manner. In all these cases, a proper challenge level is required to allow users to enjoy gaming and achieve effective gamification. If too challenging player would give up soon, while if the task is too easy the game becomes boring and uninteresting soon. A good game design, nice graphics, effective gameplay, clear feed-back and proper challenge level all contribute to enter the player in a state of flow. Flow theory is widely accepted as guiding principle by the game design community: it states that when the physical and cognitive skills of the user are matched by the level of challenge posed by the game, the user enters a state of complete focus and immersion in which it loses track of time. Gaming alternates moments of difficulty and moments of easiness of play. The benefit of the flow state is that the user becomes completely focused on the game and everything else vanishes. Studies also show that physical pain is also reduced when flow state is reached. In the latest years, gamification has been gaining a lot of interest from very diverse fields and it can thus be found everywhere: from car fueling systems to ATMs, to environmental campaigns, to workplaces around the world. At this speed, every aspect of our lives will likely be affected by gamification in the near future.

In Robohome2.0 we will design a layered gamification approach that addresses: a) game design, b) game play and supports c) automatic narration.

a) We will explore personalization of the game design. A parametric game design will be explored, in which some game assets and scenes can be uploaded either through randomized control, as explored in Mainetti et al., or according to the preferences captured by the elder profile (Task 3.4). Personalization is traditionally a key factor to increase intrinsic motivation,  but it is not the only one. Elders cognitive capability decreases with aging and with it the capability of reading complex images. The game design should therefore have an adequate cognitive load to be appreciated. We will explore scene simplification techniques to derive a level of details (LOD) in the scenes that matches the residual cognitive ability of the elder (Section 1.4.1).

b) The game play will take full advantage of IGER functionalities tuning the game difficulty to his/her status, providing meaningful feed-back and monitoring correctness of movements.

c) Single exer-games have limited motivation capabilities. A stronger motivation can be obtained when exer-games are embedded automatically inside a narration in which each single episode introduces the next one. Moreover, projecting the gaming results into a community of users increases motivation and promotes socialization. This can further increased when exer-games are played in group, as done in Robohome2.0 through the support of multiplayer gaming (Task 4.1 and 6.1).

Automatic narration is a research topic of great interest for artificial intelligence scholars, as writing good stories is notably one of the tasks that is relatively easy to perform for humans and difficult for machines. A whole research field has been recently born from this interest, Computational Narratology, that aims at interpreting, generating and analyzing narrative using information processing techniques. Achieving automated storytelling can be beneficial for different purposes: producing novel and interesting stories to be consumed without the need of an author, tutoring students of narrative by analyzing and providing story corrections, or providing interactive and dynamically created stories for video games. Various methods for the automated generation of stories have been proposed in the literature. Those methods can be grouped into different groups: (i) problem solving, (ii) data-mining methods and (iii) knowledge-based. Problem solving methods define a set of agents, actions and goals, then reason in order to drive the story to a conclusion by letting each agent pursue its goal. This often requires specific input data and produces a similar output, decreasing the scalability of the approach. Many systems use this method. Well-known examples are the TALESPIN system, AUTHOR , UNIVERSE, MINISTREL, MEXICA. Similar effects are achieved using systems based on autonomous agents, such as the Virtual Storyteller project. The use of autonomous agents is also useful for interactive purposes, allowing users to interact with the storytelling process. Some systems have also been paired with a virtual presentation layer, as with FABULIST. Data-mining methods do not use any underlying structure and can thus work with diverse story types, from mystery dramas to children stories, based on what corpora. These methods are still novel, with the first notable example coming from. Knowledge-based methods work on a database of rules, actions and relationships and try to create a story that is coherent and interesting. The created story thus depends on the chosen knowledge base. The first recorded system that implements this method is the Novel Writer system, developed by Sheldon Klein. Other known systems are BRUTUS, GESTER. Some systems use commonsense knowledge bases, while others use story schemas. Some approaches, pioneered by Peinado et al. are based on the ontological definition of the story context, actors and possible actions.

Although stories that develop through time can be developed, the control over the gameplay is still stereo-typed, with limited variability in the sequence of episodes. We will explore in Robohome2.0 the combination of knowledge-based methods for automatic narration with stochastic control to introduce a controlled variability in the evolution of the narration. We will go also one step further creating a flexible narration engine that can produce a narration from several different themes, chosen according to elders idiosyncrasies and preferences, and that guarantees that the narration will guide the elder through the mix of activities prescribed, thus taking into account the constraints posed by the cognitive and physical exercises in generating the narration.

This activity combines technological development (multi-player support) with research intensive tasks: LOD in level generation (Task 4.6 and Task 6.1) and automatic narration (Task 4.4).

Serious games have been introduced not only to guide physical or cognitive activities but also for eduction. This is the role of serious games implemented in vocational training, of which the most popular is possibly the flight simulator, but it has been applied also to other fields like business (negotiation skills), construction, mining, sports, education and so forth. The benefits of serious games have been acknowledged by the medical community and efficacy studies of such games have been performed. Comprehensive reviews of serious games for medical education have found that the effects of such games are generally positive,. Many examples of serious games specifically created to can be found for teaching very diverse medical notions, such as epidemiology, anatomy, the respiratory and circulatory system or the respiratory system. A first attempt to teach about therapy is represented by badblood, which is aimed generally to educate healthy people on the most dangerous illnesses.

We will explore here the use of serious games, not only to guide them into activities, but also to educate the elders on their diseases, therapy and lifestyle and motivate them. This will be part of an empowerment strategy, in which the elder and his caregiver collaborate in setting adequate clinical goals and lifestyle.

However, such serious games have limited content and are not suitable for prolonged use. We will explore the same approaches based on automatic narrative developed to support cognitive and physical exer-games for prolonged time in Task 4.4, to education (Task 4.5).

This activity is mainly technological development on the technology developed inside Robohome2.0 in Task 4.4.

Figure 3 - Silhouette extraction and integration inside a Virtual Environment in Duckneglet (left). Silhouette extraction obtained with Kinect SDK1.8 (right).

The sense of immersion inside a game does also contribute to flow. We are aiming to further increase this by exploring to use the elder silhouette instead of the avatar of Figure 2, as explored in Duckneglect. This produces a mirror view in which the user sees a specular view of himself on the display (Figure 3). However, a clean silhouette is obtained from 2D cameras only with controlled background, that is beyond reach in a house. Kinect has raised the expectation of a robust foreground segregation, but this was not the case as Kinect SDK1.8 does not produce a clean silhouette (Fig. 3), neither the new Kinect2.0 from preliminary tests.

A few attempts to improve background subtraction, based on spatial and temporal smoothing turned out to be not completely satisfactory. More recently a parametric approach based on level sets, combined RGB and range images for foreground segregation of objects of predefined classes. Such method is general and it was proposed effective for simple objects like shoes but it seems difficult to extend it to the entire figure. Moreover, the complexity of these approaches is not compatible with real-time as a delay of 70ms is introduced; moreover, their complexity requires high end computers that are not compatible with autonomous robots. We will develop a targeted method on silhouette extraction as described in Section 1.4.1 refining the segmentation produced by the Kinect depth map through information from the RGB image.

This is mainly a research activity (Task 4.2).

### Service Robot and Virtual Caregiver

Services in Robohome2.0 will be provided by Giraff robot (www.giraff.org/, Figure 4‎). This is a robotic base that carries a touch screen monitor, speakers and a high-resolution camera with selectable zoom capabilities. The screen is a pan-tilt unit which enables a greater and controllable field of view, while its height over the base is adjustable to create an eye-level view with the elderly. The base hosts a Windows 7 embedded OS (Intel Core i7, 4GB RAM, powerful enough to run a game engine) that controls the motors, that can propel the robot in any direction, runs a videoconferencing application, receives the input from the touch screen and displays the output. The motors, dis  play tilt and height adjustment can also be controlled by a third-party application through an API. Giraff supports WiFi communication through 802.11x protocols and USB2. Giraff is integrated with two software applications. The fist is Pilot that allows users/visitors to access and control the Giraff over a standard Internet connection.  It allows remote video-control for instance to “visit” a home or other care location or to navigate Giraff down hallways, through doorways and around tables and chairs. The second application is Sentry, a call management and administration system that manages Giraff and Pilot visitors, and allows administrators to configure Giraffs, alarms and communications options. These two applications will be integrated inside Robohome2.0 at the point of need.

Figure 4- Giraff robot

There are no other commercial mobile telepresence solutions like Giraff in Europe today, and none specifically focused on home care anywhere in the world. There are five commercial products similar in concept to Giraff, all based in the U.S. and all focused on other applications (or not specific application at all). Anybots – QB is a finished product in the market but not suitable for home care service at this time for various reasons including price (~ 13 000 € plus additional support costs), stability (it uses dynamic balancing technology for movement similar to the Segway device, which was originally designed to operate with a person on board) and a very small display size.  The company is committed to its current product direction (the basic hardware device has changed little over the past 3 years) and gives no indication of serious interest in home care. VGo Communications – VGo is perhaps the product with the most “finished look” but also not suitable for home care service for various reasons including also a very small display size.  VGo is also committed to its current product direction and gives no indication of serious interest in home care.  Its main emphasis is on enterprise communications, but VGo does describe several use cases around patient monitoring and remote hospital and home visits.  VGo’s short height (1.2 meters) make it an attractive avatar for small children. In Touch Health – RP-7i and RP-VITA The RP-7 series is the oldest mobile telepresence product in the marketplace with a strong focus on clinical health care. It is used in clinical settings to allow specialists to conduct a virtual patient visit from a remote location.  It has advanced features including autonomous navigation and obstacle avoidance, a second display for data and integration of biometric devices.  However, its price point is well in excess of 100 000 €, far beyond what is feasible for home care. InTouch has also partnered with iRobot to create the RP-VITA, a lower-cost version of the RP-7i, and is based on a subscription model (monthly service fee). However, at 3 600 €/month the economic model is still based upon leveraging very  high-cost resources (specialists) and is far beyond what can be justified for home care. Suitable Technologies – Beam Suitable Technologies is a spinoff of Willow Garage and produces the Beam. Of the products described in this document, Beam is perhaps most like Giraff in design philosophy because it is near-human height, uses a large display to present a near-life size portrait of the visitor, has HD video quality with zoom and high-quality audio. Based on technology developed at the highly-regarded organization Willow Garage, Beam is a well-designed product but has a high price point (more than 14 000 € plus a monthly service fee) and still lacking some essential features needed for home care.  For example, it weighs nearly 50 Kg so is difficult to transport, and cannot traverse even small door thresholds. It also has a sophisticated local interface to the device itself, well beyond the UI capabilities of most elderly who are receiving home services. Double Robotics – Double is essentially a “kit” consisting of a motor-powered frame and an iPad docking port (the user supplies their own iPad) with basic application software to drive the device. The price point is attractive at 1 800 € but it has none of the features required for home care and has no specific market focus, but rather is a truly generic platform. For example, Double uses the iPad for its audio and video, designed for someone sitting directly in front of the device as opposed to the wide, high-quality field of view required in a home care application.  It has limited call management features (compared to the Giraff Sentry system) and no ability to make social gestures such as nodding, turning or sitting. Additionally, none of these products provide a general development platform such as Giraff for third-party application development, plug-ins and direct camera and motor control. For all these reasons Giraff appears the best option for Robome2.0.

Giraff will be further extended in Robohome2.0 enabling him with autonomous navigation (Task 3.7) and have a more natural interfacing with the elder (Task 8.1). For navigation, Giraff will be extended adding a 3D camera, possibly a Microsoft Kinect, that allows acquiring synchronous in time a 2D RGB image and a depth map (range image) from which a single colored 2.5D image can be obtained. The range images will be used to build a 3D map of the house, for instance using the recently developed APIs based on Kinect fusion, . Two are the major challenges for the reactive navigation: 1) to manoeuvre in tight spaces, without being trapped in local minima, and to deal with 3D-shaped objects. It is important to notice that, for the Giraff robot, the common assumption of worst-case, constant shape along its height is quite unreal, and prevents finding possible free space to traverse. We will work towards a navigation solution that accounts for these features by extending to 3D the previous work of the UMA group on 2D reactive navigator, which models the robot shape as a polygon and embeds its kinematic constraints into different motion models through the so-called Parameter-Space Transformations. Apart from the geometrical and kinematics robot constraints, we will explore here how to introduce additional proxemic constraints to path planning that take into account the idiosyncrasies of the elder. For instance, she/he may not like that Giraff approach him frontally, or to stand too close. Navigation will be triggered in several ways: by the elder asking Giraff to look for an object, by the elder or a caregiver that ask Giraff to go in a room to see what is happening there (taking a picture), by the Virtual Caregiver that asks Giraff to do some monitoring or by the elder to look for a lost object.

From the architectural point of view (Task 3.1) we will define a middleware that will provide a common interface to all components: the monitoring systems, the input from the community, the services provided for assistance and the data required and provided by the activity center. This same middleware will allow interfacing the robot sensors and actuators, providing a unifying view of the system. Guidelines will be provided by the ongoing universAAL project (Universal open platform and reference specification for ambient assisted living) aimed at providing a separation between the services provided and their implementation. Such middleware will allow all components to write and read relevant data in a consistent and simple way, guaranteeing at the same time maximum standardization and scalability. Dedicated high throughput channels will be reserved to graphics, video-communication and 3D camera. To adequately storage the data, heterogeneous and arriving at different frequencies, new generation no-SQL data bases like Voldemort, MongoDB, Cassandra, Neo4j, will be explored and compared with the traditional SQL ones.

Some activity is mainly technological and carried out in (Task 4.1) Navigation will be improved through research in robotics navigation (Task 3.7).

A Virtual Caregiver will be embodied inside Giraff. This will have access to all the data from monitoring systems, the information inserted through the community from his caregivers and the data provided by the activity center. To manage this heterogenous and rich information semantic model (ontology) will be designed and developed in Task 3.4. This will contain high level concepts that relate to the elder, various health conditions, the types of activities that they can perform, and also the high level concepts relating t the information provided by the sensors. This semantic model will be used to formulate rules leading to concrete recommendations that the system will make. Recommendations may involve calls to specific routines taken by the Giraff, or suggestions for activities to be done by the elder. It will be the starting point to promote a fully collaboration between the service provider, the community of the users (GP, relatives, social services) and the elder.

A reasoning layer will be designed according to the functionalities defined in WP1, to provide the optimal mix of activities, to tune their level of difficulty to elder status and to add a flexibility in the design of the rules for recommendations. This is achieved in Task 3.5 along the guidelines already explored by ORU. Such layer will evolve dynamically, according to the feed-back provided by the users through Robohome2.0. This same layer will provide the activation of the Virtual Caregiver Avatar to promote a meaningful interaction, as investigated in Task 8.1. The Virtual Caregiver will guide the elder through cognitive and physical clinical tests in cooperation with the activity center (Task 3.6). It will also transmit to specific members of the community layer the psycho-phisical evaluation emerging from these tests as well as the tests performed transparently to the user, as well as social evaluation (Task 3.5). This same information is used to tune the exercise mix proposed to the elder.

Research related to this activity is mainly related to an efficient management of the huge amount of heterogeneous data to provide information that can be used in real-time.

Scenario: Robohome2.0 Virtual Avatar realizes that Janes has provided the wrong answer to the question “which month of the year is today?” in the last times. The virtual caregiver increases the weight of the cognitive exercises in the exer-games suggested proposing more riddles and puzzles during the day. It also warns Jane’s GP and relatives, who push Jane to play more cards with her friends. After a while Jane did not answer wrong any more to Giraff spot questions.

### Human Robot Interfacing

A large effort will be spent do design a robot that develops a meaningful relationship with the elder. Humans use a wide range of paralinguistic cues to signal intention. Eye gaze, preparatory gestures, body language, and so forth are used to signal intentions, actions and goals. Robots that operate in public settings (e.g. homes and care homes) can be safer and more effective at performing work if they were designed with similarly human-readable behaviours. Unfortunately, care robots are severely limited in this respect. Their appearance does not evoke anthropomorphisation and their behaviour, alluded to earlier, is not conductive for human-robot interaction. A remarkable exception is represented by Giraff robot, that has been developed explicitly to maximize compliance with the elder. To develop a meaningful relationship with the elder, an important aspect of the Robohome2.0 is studying how Giraff interaction can be tailored so naive users can use behavioral cues and voice explanation to form an understanding of the beliefs, intentions, goals and abilities of the robot. The challenge is to make the robot’s thought processes external and thus observable. This will be fully investigated in designing the feed-back provided by Giraff and the Virtual Caregiver avatar in Task 8.1 that will leverage of DL developed in Task 3.2.

Another key feature for effective HRI is the integration of the user’s explicit and implicit feedback. As in any assistive, cooperative, or interaction-based tasks, user feedback is critical to task performance. The most commonly used form of explicit feedback for interactive service robots consists of providing information to the user directly in the form of language, possibly with accompanying visual information. As for implicit feedback, Breazeal et al. (2005) demonstrated that the use of implicit communication by a robot could improve task performance and robustness to errors. Implicit feedback can be based on the user’s motion and gestures. This will be indeed the modality that will be adopted in Robohome2.0: the navigation system will develop a personalized approaching modality and interaction will be mediated by the Virtual Caregiver avatar through realistic animation and speech (Task 8.1). Similarly, the most natural interfacing with Giraff will be used: gestures (detected through Kinect, Task 3.3) or voice will be used to guide the interaction with the elder when they are both in the same room and will be fully used by the game center for interfacing. When the elder will be in a different room a distributed voice commands , designed in Task 5.3, will be used.

Scenario: Mike has just received his new Giraff robot. He switched it on and the Virtual Caregiver waves him with a: “Hello Mike, my name is Giraff. I will stay with you as long as you like. I come from hot Savana, but I will be pleased to leave in your comfortable apartment in Orebro”. After a few days Giraff approaches him slowly and his Virtual Caregiver appears on the screen to say: “Hey Mike, please check that the gas in the kitchen is not switched on” and at the end of the month: “Why don’t you give a call to Matteo, your nephew? Is his birthday”. Mike adores having someone that does not pretend and takes care of him.

To provide a unified view of Robohome2.0, an effort to unify the structure of the different GUIs structure will be carried out, identifying the most adequate basic modules. Moreover, the best appearance will be tailored to the current output device chosen: TVscreen, touch screen or smart phone will all be used to interact with the community of users or with Giraff.

Some activity is mainly technological and carried out in (Tasks 3.2 and 8.1). Effort for maximized HRI effectiveness is research based (Task 8.1). We will explore in innovative distributed voice command system in Task 5.3

### Community of users

The Robohome2.0 project aims to bring together all the major players through a unique community. As defined above Robohome2.0 will be formed by three types of user groups:

- Formal caregivers – such users will be formed by the clinical staff which will be located in the hospital.

- Informal caregivers – such users will be formed by family and carers of old people.

- Elderly people – this is the target users of the community and will be formed not only by the people which have a Giraff robot at home, but also to other elder who subscribe to Robohome2.0 community.

The community will have different purposes for each type of user. Clinicians will be able to access, in particular, to the time series of physiological measurements and assessment scales, caregivers to the lifestyle. The bi-direcitonal audio-video channel provided by Giraff Pilot software will fully exploited to supervise the elder when taking physiological samples, to assist when doing assessment tests at home or just to discuss any particular issue. Without any doubt, the most important user is the elder, for whom the community is intended as a tool of motivation, adherence and cognitive and social stimulation. In particular the community will provide:

- Social support, through an internet connection:

  - To put the elder in contact with relatives and friends, to avoid isolation, to allow social activities like multiplayer gaming, to increase the opportunities of a reciprocal monitoring. This may include for example the videoconferences through the Giraff’s camera.

  - To allow the elder to easily access services and facilities (e.g. order food and other goods with home delivery, book ambulance/taxi for transportations).

  - To allow the elder to be informed of personalized social and cultural initiatives that he/she can still attend and enjoy (e.g. undertaken by associations to which the elder can be subscribed, or suggested by relative and caregivers).

  - To allow the elder to be informed of environmental information such as weather, news, etc.

  - To obtain information about diet.

- Healthcare support, through preferential pathways to produce necessary sanitary interventions. For this purpose the community around each elder will include one or more reference caregivers, the family physician, the geriatrician.

- Data storage, to memorize the historical data from the monitoring system and from the activity center, provided by Giraff on a day-by-day. The same database architecture used inside Giraff will be adopted.

The socio-sanitary interventions will be mediated, at first, by the remote video communication capability of Giraff that will put in contact the elder with the person he/she needs. Interventions can be required by caregivers, by the elder themselves or by the Robohome2.0 intelligence that monitors elder activities and continually communicates with the formal and informal caregivers. According to preset priorities, different types of alerts will trigger a different pathway. The sanitary interventions eventually delivered can include telepresense visits, home visits, and direct calls to emergency services.

The success of virtual communities is due to a great diversity of factors. For instance, as studied by Leimeister et al., relevant factors are focus on one target group, continuous community-controlling, definition of sources of revenue as a starting condition for building a virtual community.

Social networks may play an important role in enforcing the relationship between elders and between an elder and his/her caregivers. Some remarkable examples have been studied, like SparkPeople (http://www.sparkpeople.com), which is an online community of people wanting to lose weight, DLife (http://www.dlife.com) is targeted to diabetes patients, http://stupidcancer.com is a community of people aged below 40 with cancer. BDIGITAL has already been explored the use of virtual community to educate and motivate patients in several research projects. Inside the project Rewire, a social community has been developed that allows patients and clinicians to chat using this portal, being the latter able to schedule such chats through a web application. This constitutes a good way of promoting shared clinician-patient decisions. Patients will be also able to fill in questionnaires related to clinical scales. That social community provides also further useful features such as forum, news, achievements. Robohome2.0 capitalizes on this community and extends it to provide a complete support of the elder at home in his physical / psychological and social behavior.

Community can constitute also a powerful drive lifestyle adherence and exercising: gamification will fully exploited in WP4 and the community will host motivational mechanisms based on reputation like leader boards (Task 6.5), in which top players achievements are described, to improve lifestyle adherence and exercising. Thematic discussions and groups will allow to improve the collective knowledge on diseases, therapies and lifestyle that can also contribute to increase motivation.

Some activity is mainly technological and carried out in (Tasks 6.1-6.4), support to gamification will be carried out in correlation with Task 4.4 and 4.5 and self-organization of the community will be object of research in Task 6.5.

### Deployment modalities.

There is a progression in fraility: from robust to pre-frail to frail and we are aiming preferentially to pre-frail elders, as they are the people who, without any assistance, have the higher risk of degeneration. As a result, highly focused interventions will be defined especially for:

1) Elders who show the initial symptons of cognitive degeneration, due to Alzheimer or dementia or other neurodegenerative deseases as well as evolutional depression. Commonly documented depression interventions indicate that cognitive behaviour therapy, cognitive stimulation and psychoeducation delivered are effective in reducing symptoms of depression. Such intervention can be delivered also from remotely. 2) Elders who have developed stability problems, because of fractures, stroke, arthritis or other factors, and need assistance to move (e.g. through a walking stick). For these elders a continuous evaluation of the trade-off between independent walking and wheel-chair should be always be monitored. 3) Elders who need to control a specific desease over time, like hypertension, diabetes, COPD, Heart problems and so forth. PCL, SAS and MUNICIP have a very large basis of elders to which to propose Robohome2.0, with PCL alone seeing more than 1,000 new elder out patients/year of elderly subjects (age > 75 years) and 2644 in follow-up out patients (2011).

SCENARIO: After falling, Mike had a stroke. He survived but developed a mild hemiparesis to his right side of the body and in particular to the leg. He needs to do rehabilitation to recover stability and strength in the offended leg, but he lives alone, far from any rehabilitation center. Therefore he is thinking to go into a Permanent Residency for Elders. His geriatrist prospects him the possibility of having at home Giraff that can help him doing rehabilitation exercises, with supervision of a physiotherapist that can monitor progress, advices and assists him. Mike adheres enthusiastically and his geriatrist, at the hospital, illustrates the new at home rehabilitation program to him and shows him the Robohome2.0 platform installed at the hospital. For a few times, he goes to the hospital to do the exer-games developed for postural rehabilitation with Giraff under the supervision of a therapist until Mikes feels comfortable with the technology. As this would allow him staying at home, Mike is particularly enthusiastic and masters the exer-games of Robohome2.0 in only two days. He then trained regularly at home for two months maintaining a tight connection with the hospital, recovering almost completely.

To the elders enrolled according to WP8, a personalized version of Robohome2.0 will be installed in their house where they can use it for five months. Robohome2.0 is adhering well to the current goals of social services to exploit ICT technology to allow the elder living at home for a longer time. The pilot will allow testing Robohome2.0 in real conditions, with elders in different clinical, physical and cognitive state. With this target in mind, an exhaustive protocol for pilot testing will be designed, including all the aspects: monitoring, evaluation and assistance. Results will allow not only to derive a preliminary evaluation of effectiveness, compliance, usability and reliability but also, through the comparison with standard care, the most appropriate business model to seamlessly connect Robohome2.0 to the network of services provided by hospitals, GPs and private and public service providers. Feedback obtained from the pilot test study outcome will be crucial also for the creation of best practices, guidelines and policy recommendations. Indeed Roohome2.0 will lead to the generation of useful, feasible and realistic policy recommendations: knowledge and expertise acquired through the project execution will be carefully analyzed in order to identify and describe the keys for success and failure of such an assistance platform and methodology to overcome all the barriers. This information will be compiled to provide policy recommendations, emphasizing generation of guidelines for the successful deployment of such platforms within the national health systems of the EU zone.

## 1.3.5 Sex and/or gender analysis

Sex and gender may play an important role in motivation. Activities and interfaces will be designed taking into account also gender in all aspects. For instance, a male and female virtual caregiver avatar will be provided to the elder, who can choose; the theme inside narration will be developed will take into account this issue, with sports themes possibly more liked by males. All these issues will be taken into account early in the project when functional specifications are set in WP1 .

# 1.4 Ambition

Elders with physical and cognitive problems are recovered in permanent residency too early or too little is done to let them staying at home longer. Robohome is aimed to change this.

- 1.4.1 Beyond the state of the art

Robohome2.0 aims to change this exploring gamification with robots in AAL setting to provide a complete system that tightly integrates personalized monitoring, evaluation, assistance and training inside a low-cost distributed pervasive system that does not require the elder to wear any particular device or change his/her habitudes. The interaction among the components allows monitoring the psycho-physical status through the data collected during gaming or during every day activities, to continuously tune the activities, in terms of exercise mix and challenge level and other gamification mechanisms updating continuously the elder profile according to exercise and monitoring outcome. Such wealth of data will allow also deriving assessment of clinical quality. State-of-the art Artificial Intelligence will be used to organize and control effectively all these interrelated components (WP3).

### Service robot

Giraff will be improved from being tele-operated to being also autonomous, guided by the virtual therapist, so that it becomes an active companion with whom to interact. New Giraff robot will be proactive in assisting the elder: it monitors his/her psyho-physical status surveying everyday activities, helps him/her searching for objects and remembering drugs, provides suggestions and feed-backs and guides him/her through adequate activities that can be administered by it or through other display (TV or android phones). We will explore here a framework, based on reactive planning such that Giraff can learn the best option to approach the elder, taking into account his/her status and idiosyncrasies, to provide an ecological approaching control. A novel solution based on distributed microphones with embedded DSP processing will be explore for launching alarms and calling Giraff from enywhere in the house (Task 5.3).

### Monitoring

Psycho physical monitoring of elder status will be performed by a novel approach that combines a robot to measure the elder movement in combination with a set of sensorized common use objects to measure objects interaction in gestures of typical everyday activities (WP5). The proposed monitoring will try to follow the evolution of both motion and pressure/force patterns adopted by the single user during the daily interactions with objects in order to recognize his/her performance changes. This new monitoring approach will be called transparent monitoring because the elder is not aware he/her is being monitored: the elder has not to wear any particular device or sensor and the monitoring system will be completely pervasive and distributed in the elder own environment. This approach will allow to acquire the elder natural behavior throughout his daily activities without splitting the monitoring stage from the ordinary life stage. The transparent monitoring is based on the principle that gestures are the expression of the motor and cognitive ability of the patient, as their pattern of variability can change selectively with pathologies, mainly Parkinson disease.

Regarding physical transparent monitoring, we will define a Gesture Degradation Index that analyzes the variability of the relevant motion and force parameters that characterize the gesture on which variability is reduced. An increase in the variability of these parameters can be related with degradation in motor control. We will fully explore such “motion signature” on different gestures like reaching and grapsing, for instance a cup or a comb, with different hand shapes in real settings of everyday life. Statistical parametric models, like Gaussian Process Latent Variable Models, and the measurement of specific features, like for instance force pattern in the stance phase of gait or in early lifting objects, will also be evaluated. The collection of data outside the laboratory is allowed by the monitoring technology developed in Robohome2.0 is particularly important as it would allow setting the ground for novel early detection of neurological decline. The aim of the project is analyzing the significance and sensitivity of several Degradation Indexes that will be defined in cooperation with clinicians. A similar approach will be developed to evaluate balance. A Dynamic Gait Index will estimate the stability of the person based on the motion and pressure data acquired through his walking aid. A walking stick can be equipped with accelerometers on its structure and force-sensing resistors mounted on the handle and eventually on the base, to provide spatiotemporal gait parameters and indicators of the weight support that the person needs. A study of the progression of those parameters will indicate if the person’s gait is becoming slower, unsteady or in increasingly need of the walking-aid assistance. Analogous sensors can be mounted on walkers, providing also indicators of the person’s status. Force-sensing resistors on the handles can monitor the weight borne by the walker, and the symmetry of the person’s posture. Whereas accelerometers placed on the structure and eventually gyroscopes integrated in the wheels will assess the spatiotemporal gait parameters. In both cases, Robohome2.0 will be able to acquire information on balance and gait stability also outdoors.

Scenario: Upon routinary physical monitoring, the virtual caregiver asks Giraff to monitor Helen while brushing her hair. Giraff detects that Mary leaves the kitchen after breakfast and enter the bathroom, Giraff approaches her and says to her “Hay Helen, have a nice day”. When it detects that the brush has been raised, it starts acquiring Helen’s 3D movements with its 3D camera. The Virtual Caregiver combines the motion data with the pressure sensor profile and realizes that Helen brushing motion pattern was significantly changed from last times being more jerky and irregular, force time course measured by the brush was equally irregular in time. The virtual caregiver asks Giraff to repeat this observation in the next days and this change persisted. After five days of monitoring a warning is sent to Helen caregivers.

Regarding cognitive transparent monitoring, we will evaluate the proper concatenation of the different actions that constitute everyday activities . For instance, for preparing a coffee, we have to put coffee in the machine, put it on gas, pour coffee, take sugar, take milk, mix with spoon. Not the same order or set of actions is present. We can choose to put sugar first or after milk and/or coffee, according to the day preference. Proper mathematical models, based on Stochastic Finite State Machines, that can provide the forecast of each next action according to the elder attitude will be developed and deployed. The model will be able to extracting high probability patterns of interaction with the environment and therefore compare the patient behaviour with the expected one. For instance: an elder who uses to put sugar in the tea, starts avoiding completely taking sugar. In this case the action next to pour coffee will be take milk, that is different from usual. This can be a warning for the person that attends the elder. Such a model will be developed and tested. Gesture segmentation itself is a very active area of research in computer vision especially related to hand motion . We will go one step forward here, exploring the use of motion and pressure data from the hold object to help segmentation. Auto-calibration of sensorized objects, taking into account Giraff Kinect video and range images captured will be developed.

To support early detection of degenerative diseases like Alzheimer or Fronto-Temporal Dementia (FTD), we will develop a system for the analysis of the profile of phone conversations. Very recently attempts to profile the characteristics of phone conversations have been proposed. We will analyze here the conversations in terms of pitch, voice volume and pace. In addition, stress will be detected using the innovative DYPSA algorithm, developed by SG, in the form of vocal folds opening and closure rates. The algorithm is now an established approach published in the Matlab Voicebox toolbox. We will analyze the determinants that allow to define a reliable emotional state of the elder and track it over time to detect meaningful mood changes that can be linked to disease onset (Task 4.6)

### Assistance

Daily assistance will be based on an automatic objects location service. Objects tags will be realized by using new miniaturized Bluetooth-4.0 (also called Bluetooth Low Energy – BLE) radio transmission. This can provide very low-power, with the ability to run for years on standard coin-cell batteries. Moreover, it constitutes a diffused transmission standard and a transmitted has very small dimensions, as small as a 50c Euros coin, , weighting a few grams, and it can be fitted or attached to the desired objects to track without changing the size the shape or the mass of the object. When requested to search, Giraff will move autonomously following the radio signal, until the object is at a very close range. The same functionalities will be provided through an app on smart phone. However, Giraff offers the possibility to locate an object also when the elder is outside his/her house or when he/she has not the phone with him/her or is looking for the phone itself.

Scenario Jessica does not find her keys, call Giraffs and asks for the keys. Giraff starts moving a bit around to identify the direction of maximum signal power associated to the keys ID and starts moving to the right towards the sitting room; it then moves towards the dining room until it gets close to a drawer on the top of which are the keys. Giraff calls then the elder. Jessica was very happy to find again her keys.

### Activity center

The activity center will be integral part of the environment assisting the elder. Eduction and activities are provided by Robohome2.0 heavily relying on gamification (WP4); this can be defined as the use of game thinking and game mechanics for a purpose other than entertainment. Gamification leverage people's natural desires for competition, achievement, status, self-expression, altruism, and closure to maximize their attention and motivation to learn. At the core of gamification implementation is the design of the gameplay such that the user feels rewarded when accomplishing a task of the game. A good game design, nice graphics, effective gameplay, clear feed-back and proper challenge level all contribute to enter the player in a state of flow. Flow theory is widely accepted as guiding principle by the game design community: it states that when the physical and cognitive skills of the user are matched by the level of challenge posed by the game, the user enters a state of complete focus and immersion in which it loses track of time; physical pain can also be reduced when flow state is reached. Gamification leverage also on the reward systems, for instance: points or coins gained or achievements and levels reached certified by virtual badges that are shown clearly as a feed-back of achievement on-line an adequate time. Most effective gamification is obtained when users play in a cooperative or competitive mode embedding gaming inside a social dimension. All these elements will be effectively designed and implemented inside Robohome2.0 activity center. However, they are not sufficient to keep the user engaged for a long time as situations repeat after some times and therefore are not enough for long life gaming.

We will explore here how combining gamification with adequate statistical methods effectiveness, motivational and long lasting interaction can be obtained.

To this aim we will largely improve the Intelligent Game Engine fo Rehabilitation (IGER) developed by UMIL for the Rewire project, to incorporate a hierarchial motivational layer that involves: gameplay and reward system (extrinsic motivation) and long life (automatic narration).

To make exer-games compliant with elders, the details in the scene and their number should be adapted to the elder’s residual cognitive capabilities. A common effect of aging is decline of cognitive processing capability and, in particular, in spatial cognition, . This is well known in neurology, where after stroke, only simple and clear stimuli are allowed, and video-games targeted to acute patients have a real simple and basic graphics. Therefore, finding the proper level of detail allows increasing the understanding of the scene and therefore motivation. To achieve this, we will explore inside Robohome2.0 the innovative use of a level of detail (LOD) in the game design. LOD is a technique well known in the graphics domain, to decrease the complexity of a 3D object representation at the point of need. We will explore both in the detail of the elements in the scene and in their number: we will provide a high LOD version of a scene, with lots of details, enrichments and animated assets on one end, and a low LOD version, in which only essential elements will be present in the scene. Several intermediate versions will also be provided. Evaluation of the best resolution will be carried out throughout the project and an adequate measure of cognitive load will be defined to match the profiling of the patient.

The level of detail will be complemented by a controlled randomization of the scenarios and assets. As already explored by UMIL, this makes the patient feeling confronted with an always new game, while the gameplay remains unchanged. We will also provide to the patient some customization capability of assets, like for instance the game avatar, that can be loaded at run-time according to patient idiosynchrasies, such that the elder himself can choose and shape the appearance of the games that guide his activities. This allows to incorporate a key element to increase intrinsic motivation, . Lastly the pace of the game and the challenge degree will be adapted to the elder status automatically by analyzing in real-time the success rate to avoid that the game becomes either too easy or too difficult and the patient looses interest in it. Music and voice feed-back will be provided. The exergames represent only the first gamification aspect, however. We will also provide short-term extrinsic motivation under the form of feed-back from the Virtual Clinician Avatar that is constantly monitoring the patient, giving advice on the exercises and praising him/her when he/she performs correctly. Short-term extrinsic motivation is also empowered by additional gaming-like solutions: points and high-scores, colorful and meaningful feedbacks associated to high compliance and high knowledge degree about the therapy and the illness. This will be largely enhanced by the social dimension of Robohome2.0 mediated by the Community of users.

Long-term motivation represents a major issue when activity prolonged in time is required: games may get old soon and lose their appeal after a period of a few days of repetitive play, and the kind words may not be enough to keep the elder engaged for months. To this aim, we will develop automatic narration on a container chosen with the elders. The story will chain dynamically and automatically the different mini-games associated to the activities and it can possibly assume the form of a sport competition or a tale. In the latter case, we will fully explore the morphology analysis of fairy tales developed by the Russian school that has identified elements common to all fairy tales, like for instance the presence of an agonist and an antagonist, the fight, the elation and so forth. We will analyse the most interesting elements and we will extract few of them in order to be casted into a set of characters with a methodology based on ontology proposed by Peinado et al..

Two different approaches will be explored to combine the different episodes. The first one is based on stochastic finite state machines that will allow creating stories with different sequences of episodes and scenes on the same plot. We will also go one step further and consider graphical models, adding to the transition probability matrix, an a-priori distribution of the possible choices that takes into account the idiosyncrasies of the elder. The second solution is based on reinforcement learning in which each next episode of the story will be chosen in real-time according to a given cost function computed on the fly, . We will explore how to introduce coherence, consistency inside the cost function. Reinforcement will be provided by the elder him/herelf with a qualitative feed-back for instance in the form of a smiley. We Will further explore in Task 4.9 the use of tracked instrumented objects as game input devices.

### Human Robot Interaction

As the robotic system in Robohome2.0 is going to be close partner to the elder, the need for a natural and effective communication is becoming a fundamental issue to support meaningful, fruitful long lasting interaction. This will me mediated by both the robot itself and the virtual caregiver with voice and graphical feed-back providing a very rich interfacing possibilities. We will fully exploited these potentialities inside Robohome2.0 (WP8) as follows:

(i) Long-term interaction and acceptance: current HRI systems tend to be based on single-session interaction. In robot assistive scenarios, where the same user interacts with a robotic companion for multiple sessions, we will include a memory system that keeps track of the history of interaction and support subsequent tasks in a predictive way, in accordance with the predicted user’s behavior and expectations. Their effect will be thoroughly evaluated.

(ii) Readability: users should be able to read the robot’s “cognitive processes”. Humans are finely tuned to cues and signals communicating our actions and intentions in inter-human interaction, but these cues are generally lacking from robots and this hampers natural HRI. Robohome2.0 will study how the behaviour of the robot can be generated to provide feedback and signal intentions and goals, by adequately filtering the reasoning process implemented by the virtual caregiver. Moreover, we will be identify the “compliant paths” for the cared elder. Indeed movement itself is a powerful mean of communication for human-human interaction and it is being currently explored in robotics. Finding the mode of approaching by Giraff that is most acceptable to the elder would increase robot acceptance.

(iii) Responsiveness: typical performance of a robot involves a considerable amount of processing (for example for automated speech recognition and natural language interaction), which inevitably leads to perceivable delays. As such during processing the robot seems to be inactive. Conversational fillers and back-channel feedback can be used to create the illusion of responsiveness, which is highly influential on acceptability.

None of the above mentioned qualities can be considered in isolation: long-term interaction and acceptance, readability, responsiveness and matching of perceived and actual ability all impact on each other. As such it is impossible to develop one quality while neglecting the others. Our research and development on the HRI aspects will focus on incrementally improving these HRI qualities through implementing the latest insights in the field of HRI and field testing with naive users (Task 8.1).

### Community of users

Robohome2.0 will take full advantage of the users community, offering the elders the possibility of comparing their status with other elders, in order to make it easy to find people with similar problems, helping preventing that they fall into isolation and depression. Pattern matching technique applied on elders profile will allow to automatically suggest which groups an elder may find interesting to join, personalized news or other content, thus making the elders proactive increasing their engagement in the social community.

Through the community, elders will access thematic information on diseases, treatments, best practices, and lifestyle and so forth and new knowledge can be created through the interaction among users, increasing the trust in Robohome. To this aim, free and informed discussions between community members will be supported and a continuous osmosis with the most popular social networks will be supported. Through conversation in the community, socialization and externalization of knowledge will take place.

We will made available to clinicians a complete therapy management system, implementing a closed-loop workflow, through which they will be able to assess the elder status, review the results of the therapies and receive advice from the system based on the analysis of past results. Using the portal of knowledge they will have access also to statistics and other processed data regarding therapy outcomes, scientific articles and specialized information in general. Elders will have access also to all the data stored in the system about their diseases and therapy, in an understandable fashion, so that they are always aware of the evolution of their condition, shorting the distance between them and the clinicians. This will facilitate changing the role of patients in clinical decisions from mere passive actors to active ones, reducing the “culture mismatch” between them and the health professionals.

## 1.4.2 Innovation potential

The Robohome architecture will introduce different systems in a harmonious way, creating a new and innovative standard for domestic assistance. Each subsystem has peculiar features able to improve the process of the virtual caregiver to help elderly people and their family to avoid possible risky situations. Although a full patent search will be carried out in Task 9.6, a preliminary patent search has allowed to highlight the highly innovation potential of the research activity proposed.

### Patent Search

Smart Drug dispenser. Robohome will try to create a low cost, compact and easy-to-use solution to help elderly people or the their family in a friendly way, because the medication dispensing cabinet for hospitals and drugstores are mainly dedicated to help nurses and clinicians during the handling of blisters and boxes or to improve the management process. They also try to prevent errors during the refill, but no one has been designed for a domestic use neither introduces specific components able to help people to take their own drugs. Patents that describes some medication dispenser are US8588964, US2013006415, CA2821616, WO2013142351 and CA2772899. This last is a really recent patent that describes a medication dispensing cabinets,  developed to store and dispense in a controllable way a wide variety of medications. While some of the drawers may be unlatched and can be opened, other drawers may be locked in order to improve the control of the access to the medication stored in the locked drawers. This system doesn’t act as an “assistance” in the medication dispensing, but mainly as a supervisor for operators, able to prevent possible errors and limit the access to the medication. The claims are mainly focused at describing the locking system, which is not suitable for creating  a low cost, domestic system able to help people to easily take their own drug.

Finding lost objects. To help people who lost keys, glasses or other personal belongings in house (and also outside it), there are some solutions already available in the market. They use radio signals to detect the remote transceiver, previously linked to the keys, for example. The main difference introduced by Robohome2.0 is that Giraff will find the smart objects and signal them in an automatic way, using standard RF solutions (i.e. Bluetooth), without the involvement of the owner. Giraff will be the finder, this is the more innovative aspect, whilst commercial solutions require that the people can move and find them. Moreover some systems require the use of a smartphone as a locator, which usually is the object which has to be found. Patents describing commercial solutions is US6366202 (1999), the US8130116 (2012) only introduces the configurable range of detection.

Sensorized objects for monitoring. Several researches and publications describe the use of sensorized objects (doors, chairs, wristwatch etc.) to analyze human behavior and specific actions in order to identify risky situations in the daily life. Some other projects in the past proposed the use of instrumented or special objects to create a personalized, home rehabilitation system for specific pathologies (e.g. rehabilitation of patients affected by apraxia, rehabilitation of rheumatic patients ). The novelty of the approach followed by Robohome is that the offered physical monitoring during normal daily actions will try to follow the evolution of both motion and pressure/force patterns  adopted by the single user during the daily interactions with common objects in order to recognize his/her performance changes and compare them with the other indicators collected by the Robohome systems. The system will be completely transparent to the subjects, without the need of wearable solutions. For this reason a generic system to monitor “actions” or “behavior modification” (patents US6611206, US6968294, KR20090030868 and KR20090025924) could not be compared to the innovation that Robohome will introduce. The patent CA2275733 introduced the measurement, the monitoring and/or the analysis of motor control ability, performance, training and rehabilitation in an active way, with special instruments on order to prove assisted exercise. In Robohome the “exercise” are the normal daily activities, the “instrument” could be a cane, a spoon and so on.

Giannakouris k., Aging characterizes the demographic perspective in the European Societies, Eurostat, Statistics in focus, 2008, 72. http://eppeurostat.ec.europa.eu

P. Buerhaus, BCurrent and future state of the US nursing workforce, J. Amer. Med. Assoc., vol. 300, no. 20, pp. 2422–2424, 2008. Nursing Shortage Fact Sheet, American Association of Colleges of Nursing, 2010. Online at http://www.aacn.nche.edu/media/FactSheets/NursingShortage.htm...

http://oreilly.com/web2/archive/what-is-web-20.html

http://www.giraff.org/

T.Bickmore, R.Picard, Establishing and maintaining long-term human-computer relationships, ACM Trans. CHI, Volume 12:2, 2005, pp 293 – 327.

Alexopoulos G. Depression in the elderly. Lancet, 2005; 365: 1961-70.

M. Fayzullin, V. S. Subrahmanian, M. Albanese, C. Cesarano, A. Picariello, Story creation from heterogeneous data sources, Multimedia Tools and Applications, 33(3), 351-377, 2007.

Cattinelli I, Goldwurm M, Borghese NA, Interacting with an artificial partner: modeling the role of emotional aspects, Biol. Cybern. 99(6), 473-489, 2008.

V. Propp, Morphology of the Folktale: Revised and Edited with Preface by L.A. Wagner, Introduction by A. Dundes (Vol. 9), University of Texas Press, 2010.

https://developers.google.com/translate/

http://www.z-wave.com/

E. Baum, D. Jarjoura, A. E. Polen, D. Faur, and G. Rutecki, BEffectiveness of a group exercise program in a long-term care facility: A randomized pilot trial. J. Amer. Med. Directors Assoc., vol. 4, pp. 74–80, 2003.

D. Dawe and R. Moore-Orr, BLow-intensity, range-of-motion exercise: Invaluable nursing care for elderly patients, J. Adv. Nursing, 21, pp. 675–681, 1995.

M. D. McMurdo and L. M. Rennie, BA controlled trial of exercise by residents of old people’s homes, Age and Ageing, vol. 22, pp. 11–15, 1993.

V. Thomas and P. Hageman, B Can neuromuscular strength and function in people with dementia be rehabilitated using resistance-exercise training? Results from a preliminary intervention study, J. Gerontol. A, Biol. Sci. Med. Sci., vol. 58, pp. M746–M751, 2003.

S. Colcombe and A. Kramer, BFitness effects on the cognitive function of older adults, Psychol. Sci., vol. 14, pp. 125–130, 2003.

S. J. Colcombe, A. F. Kramer, K. I. Erickson, P. Scalf, E. McAuley, N. J. Cohen, A. Webb, G. J. Jerome, D. X. Marquez, and S. Elavsky, BCardiovascular fitness, cortical plasticity,and aging,[ in Proc. Nat. Acad. Sci. USA, 2004, vol. 101, pp. 3316–3321.

W. Spirduso and P. Clifford, BReplicationof age and physical activity effects on reaction and movement time, J. Gerontol., vol. 33, pp. 26–30, 1978.

Z. B. Moak and A. Agrawal, BThe association between perceived interpersonal social support and physical and mental health: Results from the national epidemiological survey on alcohol and related conditions, J. Public Health, vol. 32, pp. 191–201, 2010.

L. K. George, D. G. Blazer, D. C. Hughes, and N. Fowler, BSocial support and the outcome of major depression,[ British J. Psychiatry, vol. 154:  478–485, 1989.

E. Paykel, BLife events, social support and depression,[ Acta Psychiatrica Scandinavica, vol. 89, pp. 50–58, 1994.

B. Prospective relations between social support and depression: Differential direction of effects for parent and peer support? J. Abnormal Psychol., vol. 113, pp. 155–159, 2004.

S. A. Stansfeld, G. S. Rael, J. Head,M. Shipley, and M. Marmot, B Social support and psychiatric sickness absence: A prospective study of British civil servants, Psychol. Med., vol. 27, pp. 35–48, 1997.

1.Nathan DG. Careers in translational clinical research - Historical perspectives, future challenges. JAMA 2002;287(18):2424-7.

http://www.innovation4welfare.eu/307/subprojects/robo-m-d.html

http://www.aal-europe.eu/projects/excite/

http://www.innovation4welfare.eu/287/fitrehab.html

http://www.signomotus.it/h_cad_site/h_cad_accessible/system_description.htm

http://www.backhome-fp7.eu/content/project

http://www.cupid-project.eu/

http://rgs-project.upf.edu

M. Pirovano, R. Mainetti, G. Baud-Bovy, P.L. Lanzi, N.A. Borghese, IGER – Intelligent Game Engine for Rehabilitation, IEEE Trans. CIAIG, submitted. Short version in Proc. CIG 2012.

N.A. Borghese, P.L. Lanzi, R. Mainetti, M. Pirovano, Apparatus and method for rehabilitation employing a game engine, US Application 13/911577, 2013

Laurie K. Garda, Wendy Armstrong, Amy Blew, Jyotsna Rao ,US Patent US20120253509, 2013.

Steven N. W. Hunter, David M. Browning, Dennis J. Fuhrman, William C. Park, IV. Automatic apparatus for storing and dispensing packaged medication and other small elements, US7100792 B2, 2006.

http://www.zephyranywhere.com/healthcare/zephyrlife-home/

http://www.alivecor.com/home

http://www2.imec.be/be_en/home.html

http://www.diabetes.co.uk/diabetes_care/blood_glucose_monitor_guide.html

https://www.glooko.com/android

Clark RA, Pua YH, Fortin K, Ritchie C, Webster KE, Denehy L, Bryant AL, Validity of the Microsoft Kinect for assessment of postural control, Gait & Posture, 36(3), 372-377, 2012.

Berg KO, Wood-Dauphinee SL, Williams JT, Gayton D. Measuring balance in the elderly: preliminary development of an instrument. Physiotherapy Canada 1989;41:304-311.

Podsiadlo, D; Richardson, S (1991). "The timed 'Up & Go': A test of basic functional mobility for frail elderly persons". Journal of the American Geriatrics Society 39 (2): 142–8. PMID 1991946.

Morse JM, Morse RM, Tylko SJ. Development of a scale to identify the fall-prone patient. Can J Aging 1989;8;366-9.

http://www.xsens.com/products/

http://www.gaitup.com/

http://www.digifit.com/shop/health.asp.

http://z-devicetest.zausan.com/index.php?lang=en

Serio SM, Assaf T, Cecchi F, Laschi C, Dario P. A novel Wireless Toy for Measuring Infants’ Bimanual Actions. The Fourth IEEE RAS/EMBS Int. Conference on Biomedical Robotics and Biomechatronics Roma, Italy. June 24-27, 2012

J Hermsdörfer J, Bienkiewicz M, Cogollor JM, Russel M, Jean-Baptiste E, Parekh M, Wing AM, Ferre M, Hughes C. CogWatch Automated Assistance and Rehabilitation of Stroke-Induced Action Disorders in the Home Environment. D. Harris (Ed.): EPCE/HCII 2013, Part II, LNAI 8020, 343–350, Springer 2013,

O’Caoimh R, Gao Y, McGlade C et al. Comparison of the Quick Mild Cognitive Impairment (Qmci) screen and the SMMSE in Screening for mild cognitive impairment. Age Ageing 2012; 41(5): 624–9.

Folstein MF, Folstein SE, McHugh PR. Journal of Psuchiatric Research 1975;12:189. Molloy DW, Standish TIM. A guide to the Standardized Mini-Mental State Examination. Int Psychogeriatrics 1997;9: 87–94.

http://www.doctot.com/doctot-apps/dementia-app/.

Grossman M. Fronto temporal dementia: a review. J Int Neuropsychol Soc. 2002;8:566–583

E. Vargiu, L. Ceccaroni, L. Subirats, S. Martin, and F. Miralles. User Profiling of People with Disabilities - A Proposal to Pervasively Assess Quality of Life.  In ICAART 2013 - Proceedings of the 5th International Conference on Agents and Artificial Intelligence, Volume 2, J. Filipe, A. L. N. Fred (Eds.) Barcelona, Spain, 15-18 February, 2013. SciTePress 2013.

http://www.z-wave.com/

https://www.sticknfind.com/, http://www.thetileapp.com

Clark RA, Pua YH, Fortin K, Ritchie C, Webster KE, Denehy L, Bryant AL, Validity of the Microsoft Kinect for assessment of postural control, Gait & Posture, 36(3), 372-377, 2012.

Mainetti R, Sedda A, Ronchetti M, Bottini G, Borghese NA. (2013) Duckneglect: video-games based neglect rehabilitation. Technology and Health Care 21 97–111 97. DOI 10.3233/THC-120712 IOS Press.

J Fasola and MJ Mataric Using Socially Assistive Human–Robot Interaction to Motivate Physical Exercise for Older Adults, IEEE Proc. Vol. 100,No. 8, August 2012, pp. 2512-2526.

“From Game Design Elements to Gamefulness: Defining ‘Gamification’”, Sebastian Deterding et al., Proceedings of the 15th International Academic MindTrek Conference. 2011

Deterding, S., Dixon, D., Khaled R., & Nacke L. From Game Design Elements to Gamefulness: Defining  “Gamification”, Proceedings of MindTrek, 2011

http://www.leaderboarded.com/home/

http://wiisports.nintendo.com/

http://www.waterrower.com/home.php

J. Schell, The Art of Game Design: Book of Lenses. Elsevier, 2008.

Csikszentmihalyi M, ―Flow: The psychology of optimal experience,‖Harper Perennial, 1991.

Kirk J, ―Burning man,‖ http://www.gq.com/news-politics/newsmakers/201202/burning-man-sam-brown-jay-kirk-gq-february-2012?currentPage=1, 2012

“Meaningful play - getting gamification right”, Sebastian Deterding, Google Tech Talk 2011

“Design outside the Box”, Jesse Schell, DICE Summit 2010

Mainetti R, Sedda A, Ronchetti M, Bottini G, Borghese NA. (2013) Duckneglect: video-games based neglect rehabilitation. Technology and Health Care 21 97–111 97. DOI 10.3233/THC-120712 IOS Press.

M. Zuckerman, J. Porac, D. Lathin, R. Smith, and E. L. Deci, BOn the importance of self-determination for intrinsically motivated behavior,[ Personality Social Psychol. Bull., vol. 4, pp. 443–446, 1978.

E. Deci and R. Ryan, Intrinsic Motivation and Self-Determination in Human Behavior. New York: Plenum, 1985, pp. 29, 318, 322.

. Gervàs, Pablo – 2012 - Story Generation Algorithms. The Living Handbook of Narratology. Accessed online at http://wikis.sub.uni-hamburg.de/lhn/index.php/Story_Generator_Algorithms.

Mani, Inderjeet -  2013 - Story Generation Algorithms. The Living Handbook of Narratology. Accessed online at  http://wikis.sub.uni-hamburg.de/lhn/index.php/Computational_Narratology.

McIntyre, Neil - 2011 - Learning to tell tales: automatic story generation from corpora, PhD Thesis

J. Meehan. An interactive program that writes stories. In Proceedings of the 5th International Joint Conference on Artificial Intelligence, pages 91–98, Cambridge, Massachusetts, 1977.

Dehn, N, Story Generation After TALE-SPIN, In IJCAI (Vol. 81, pp. 16-18), 1981.

M. Lebowitz. Story-telling as planning and learning. Poetics, 14:483–502, 1985.

S. R. Turner. Ministrel: A Computer Model of Creativity and Sotrytelling. UCLA, 1992.

R. Pérez y Pérez and M. Sharples. Mexica: A computer model of a cognitive account of creative writing. Journal of Experimental and Theoretical Artificial Intelligence (JETAI), 13(2):119–139, April 2001.

Swartjes and M. Theune. The virtual storyteller: Story generation by simulation. In Proc. 20th Belgian-Netherlands Conference on Artificial Intelligence, BNAIC 2008, pages 257–264, Enschede, the Netherlands, October 2008.

C. Fairclough and P. Cunningham. A multiplayer case based story engine. In Proc. of the 4th Int. Conf. Intelligent Games and Simulation (GAME-ON 2003), pages 41–46, London, UK, November 2003.

Riedl MO, Young RM, Narrative planning: balancing plot and character, Journal of Artificial Intelligence Research, 39(1), 217-268, 2010

McIntyre, Neil - 2011 - Learning to tell tales: automatic story generation from corpora, PhD Thesis.

Klein, S., J.F. Aeschlimann,  D. F. Balsiger,  S. L. Converse,  C. Court,  M. Foster,  R. Lao,  J. D. Oakely  &  J. D. Smith. Automatic Novel Writing. UWCS Tech Report No. 186, 109 pages, 1973.

Bringsjord, Selmer; Ferrucci, David's Artificial Intelligence and Literary Creativity: Inside the Mind of Brutus, A Storytelling Machine 1st (first) edition by Bringsjord, Psychology Press [Hardcover] (1999)

Pemberton L. (1989) A modular approach to story generation, in: 4th European ACL, Manchester, 1989 217–224.

H. Liu and P. Singh. Makebelieve: Using commonsense reasoning to generate stories. In Proc. of the 18th National Conference on Artificial Intelligence, pp 957–958, Edmonton, CA, August 2002.

M. Fayzullin, V. S. Subrahmanian, M. Albanese, C. Cesarano, and A. Picariello. Story

creation from heterogeneous data sources. Multimedia Tools and Applications, 33 (3):351–377, June 2007.

F. Peinado, P. Gervás, and B. Díaz-Agudo. A description logic ontology for fairy tale generation. In Proceedings of the 4th International Conference on Language Resources and Evaluation: Workshop on Language Resources for Linguistic Creativity, pages 56–61, Lisbon, Portugal, May 2004.

Kerfoot BP, Baker H, Pangaro L, Agarwal K, Taffet G, Mechaber AJ, Armstrong EG.  An online spaced-education game to teach and assess medical students: a multi-institutional prospective trial. Acad Med. 2012 Oct;87(10):1443-9.

M. Graafland, J. M. Schraagen and M. P. Schijven. Systematic review of serious games for medical education and surgical skills training. Article first published online: 7 SEP 2012 DOI: 10.1002/bjs.8819

Adams SA. Use of "serious health games" in health care: a review. Stud Health Technol Inform. 2010;157:160-6.

Emeka G. Anyanwu, Anatomy adventure: A board game for enhancing understanding of anatomy, Anatomical Sciences Education, 2014, 7, 2

Shieh L. et al., Septris, 2011, available online at http://med.stanford.edu/septris/game/SeptrisTitle.html

PL Lanzi, D Loiacono, E Parini, F Sannicolo’, C Scamporlino & M. Pirovano. Tuning Mobile Game Design Using Data Mining. IGC 2013 conference

http://www.badbloodgame.net/

Lyttle, DJ; Ryan, A. (2010). "Factors' influencing older patients' participation in care: A review of the literature". Int. J. Older People Nursing 5(4): 274–282.

Mainetti R, Sedda A, Ronchetti M, Bottini G, Borghese NA. (2013) Duckneglect: video-games based neglect rehabilitation. Technology and Health Care 21 97–111 97. DOI 10.3233/THC-120712 IOS Press.

Pirovano M, Ren CY, Frosio I, Lanzi PL, Prisacariu V, Murray DW, Borghese NA, Robust Silhouette Extraction from Kinect Data, In: Image Analysis and Processing–ICIAP 2013 (pp. 642-651). Springer Berlin Heidelberg, 2013.

VA Prisacariu ID Reid PWP3D: Real-time Segmentation and Tracking of 3D Objects, Int. J. Computer Vision, 98(3), 2013; CY Ren, VA Prisacariu, DW Murray, I Reid: STAR3D: Simultaneous Tracking and Reconstruction of 3D Objects Using RGB-D Data. ICCV 2013: 1561-1568.

http://research.microsoft.com/en-us/projects/surfacerecon/

http://msdn.microsoft.com/en-us/library/dn188670.aspx

.L. Blanco, J. Gonzalez-Jimenez, J.A. Fernandez-Madrigal, "Optimal Filtering for Non-Parametric Observation Models: Applications to Localization and SLAM", The International Journal of Robotics Research (IJRR), vol. 29, no. 14, 2010.

http://www.universaal.org/index.php/en/

MU Ahmed, A Loutfi, Physical Activity Identification using Supervised Machine Learning and based on Pulse Rate, International Journal of Advanced Computer Sciences and Applications 4 (7), 2013.

M Alirezaie, A Loutfi, Ontology alignment for classification of low level sensor data. Knowledge Eng. Ontology Dev KEOD Best Student Paper Award, 2012.

Breazeal, C. C.Kidd, A.Thomaz, G.Hoffman, and M.Berlin, “Effects of nonverbal communication on efficiency and robustness in human- robot teamwork,” in Intelligent Robots and Systems, 2005. (IROS 2005), pp. 708 – 713.

Coradeschi, S.; Cesta, A.; Cortellessa, G.; Coraci, L.; Gonzalez, J.; Karlsson, L.; Furfari, F.; Loutfi, A.; Orlandini, A.; Palumbo, F.; Pecora, F.; von Rump, S.; Stimec, A.; Ullberg, J.; Östlund, B., "GiraffPlus: Combining social interaction and long term monitoring for promoting independent living," The 6th Int. Conf. Human System Interaction (HSI), 2013, pp.578,585.

Broz F., Di Nuovo A., Belpaeme T., Cangelosi A. (2013). Multimodal Robot Feedback for Eldercare. Workshop at IEEE ROMAN IEEE International Symposium on Robots and Human Interactive Communications

Li S, Wrede B Why and how to model multi-modal interaction for a mobile robot companion In: AAAI Technical Report SS-07-04: Interaction Challenges for Intelligent Assistants. Stanford: AAAI Press: 71–79 2007.

NA Borghese, M Pirovano, PL Lanzi, S Wuest and ED de Bruin (2013), Computational Intelligence and Game Design for effective home-based stroke at Home Rehabilitation. Games for Health  Journal. April 2013, Vol. 2, No. 2: 81-88.

Leimeister, J.M.; Sidiras, P.; Krcmar, H., "Success factors of virtual communities from the perspective of members and operators: an empirical study," System Sciences, 2004. Proceedings of the 37th Annual Hawaii International Conference on , vol., no., pp.10 pp. 5-8 Jan. 2004.

http://www.leaderboarded.com/home/

Christensen H, Griffiths K, Jorm A. Delivering interventions for depression by using the internet: randomised controlled trial BMJ 2004;328:265. Griffiths K, Farrer L and Christensen H. The efficacy of internet interventions for depression and anxiety disorders: a review of randomised controlled trials. Medical Journal of Australia, 2010

Paré G, Moqadem K , Pineau G, and St-Hilaire C, Clinical Effects of Home Telemonitoring in the Context of Diabetes, Asthma, Heart Failure and Hypertension: A Systematic Review, J Med Internet Res. 2010 Apr-Jun; 12(2).

I. Carpinella, P. Crenna, E. Calabrese, M. Rabuffetti, P. Mazzoleni, R. Nemni, and M. Ferrarin Locomotor Function in the Early Stage of Parkinson’s Disease, IEEE Trans. Neural Syst. Rehab. Engin., Vol. 15, No. 4, 2007, 543-551. R. Baltadjieva, N. Giladi, L. Gruendlinger, C. Peretz, and J. M. Hausdorff, “Marked alterations in the gait timing and rhythmicity of patients with de novo parkinson’s disease,” Eur. J. Neurosci., vol. 24, no. 6, pp. 1815–1820, Sep. 2006. Ansuini Caterina; Begliomini Chiara; Ferrari Tania; Castiello Umberto Testing the effects of endgoal during reach-to-grasp movements in Parkinson's disease. Brain and cognition 2010;74(2):169-77.

E.Todorov, M-Jordan, Optimal feedback Control as a Theory of Motor Coordination, Nature Neuroscience, 2002; E.Todorov, Optimality principles in sensorimotor Control, Nature Neuroscience, 2004.

Rasmussen, C.E.; Williams, C.K.I (2006). Gaussian Processes for Machine Learning. MIT Press.

N.D. Lawerence and A.J. Moore. Hierarchical Gaussian process latent variable models. In Z. Gharamani, Ed. Proc. Int. Conf. Machine Learning, vol. 24::481-488, 2007; Titsias and Lawrence, Proc. 13th Int. Conf. on Artiﬁcial Intelligence and Statistics (AISTATS) 2010.

Cattinelli I, Goldwurm M, Borghese NA, Interacting with an artificial partner: modeling the role of emotional aspects, Biol Cybern,99(6), 473-489, 2008.

Scott A Green, Mark Billinghurst, Xiaoqi Chen, J Geoffrey Chase Human-robot collaboration: A literature review and augmented reality approach in design International Journal of of Advanced Robotic Systems (2008) Volume: 5, Issue: 1, Pages: 1-18; G. Guerra-Filho and Y. Aloimonos. Understanding visuomotor primitives for motion synthesis and analysis. Comp. Anim. Virtual Worlds, 17:207–217, 2006. P. Beaudoin, S. Coros, A. Anagnostopoulos, M. Vlachos, M. Hadjieleftheriou, E. J. Keogh, and P. S. Yu. Global distance-based segmentation of trajectories. In KDD, pages 34–43, 2006). A. Ghotkar, G.K. Kharate, Hand Segmentation Techniques to Hand Gesture Recognition for  Natural Human Computer Interaction  Int. Journal of Human Computer Interaction (IJHCI), Volume (3) : Issue (1) : 2012

http://www.callcentrehelper.com/how-to-use-vocal-pitch-and-pace-on-the-phone-2644.htm

P. A. Naylor, A. Kounoudes, J. Gudnason, and M. Brookes, “Estimation of Glottal Closure Instants in Voiced Speech using the DYPSA Algorithm,” IEEE Trans on Speech and Audio Processing, vol. 15, pp. 34–43, Jan. 2007

http://www.mathworks.com/matlabcentral/linkexchange/links/797-voicebox-speech-processing-toolbox-for-matlab

http://pen.made-in-china.com/showroom/dragonxander

http://www.indiegogo.com/projects/sticknfind-bluetooth-powered-ultra-small-location-stickers

Junyi Zhou, Jing Shi. Performance evaluation of object localization based on active radio frequency identification technology. J. Computers in Industry archive. Vol. 60:9, 2009, pp 669-676.

“From Game Design Elements to Gamefulness: Defining ‘Gamification’”, Sebastian Deterding et al., Proceedings of the 15th International Academic MindTrek Conference. 2011

Zichermann, Gabe; Cunningham, Christopher (August 2011). "Introduction". Gamification by Design: Implementing Game Mechanics in Web and Mobile Apps (1st ed.). Sebastopol, California: O'Reilly Media. p. xiv. ISBN 1449315399.

J. Schell, The Art of Game Design: Book of Lenses. Elsevier, 2008.

Csikszentmihalyi M, ―Flow: The psychology of optimal experience,‖Harper Perennial, 1991.

Kirk J, Burning man,‖ http://www.gq.com/news-politics/newsmakers/201202/burning-man-sam-brown-jay-kirk-gq-february-2012?currentPage=1, 2012

Byron Reeves, J. Leighton Read (2009). Total Engagement: Using Games and Virtual Worlds to Change the Way People Work and Businesses Compete. Harvard Business Press. p. 177. ISBN 978-1-4221-4657-6.

N.A. Borghese, P.L. Lanzi, R. Mainetti, M. Pirovano, Apparatus and method for rehabilitation employing a game engine, US Application 13/911577, 2013.

Ramscar, M., Hendrix, P., Shaoul, C., Milin, P. and Baayen, H. (2014), The Myth of Cognitive Decline: Non-Linear Dynamics of Lifelong Learning. Topics in Cognitive Science, 6: 5–42. doi: 10.1111/tops.12078

S.Kim A.K. Dey Simulated Augmented Reality Windshield Display as a Cognitive Mapping Aid for Elder Driver Navigation, CHI2009

Colombo, R., Pisano, F., Mazzone, A., Delconte, C., Micera, S., Carrozza, M. C., Dario, P., et al. Design strategies to improve patient motivation during robot-aided rehabilitation. Journal of neuroengineering and rehabilitation, 4, 3, 2007,

Mainetti R, Sedda A, Ronchetti M, Bottini G, Borghese NA, Duckneglect: video-games based neglect rehabilitation, Tech Health Care, 21(2), 97-111, 2013.

M. Zuckerman, J. Porac, D. Lathin, R. Smith, and E. L. Deci, BOn the importance of self-determination for intrinsically motivated behavior Personality Social Psychol. Bull., vol. 4, pp. 443–446, 1978.

E. Deci and R. Ryan, Intrinsic Motivation and Self-Determination in Human Behavior. New York: Plenum, 1985, pp. 29, 318, 322.

Togelius J, Whitehead J and Bidarra R (2011) Procedural content generation in games. IEEE Transactions on Computational Intelligence and AI in Games 3(3):169-171, doi: 10.1109/TCIAIG.2011.2166554.

E. Propp, Morphology of the Folktale: Second Edition, Revised and Edited with Preface by Louis A. Wagner, Introduction by Alan Dundes, 1968, original version in Russian, 1928.

F. Peinado, P. Gervás, and B. Díaz-Agudo. A description logic ontology for fairy tale generation. In Proceedings of the 4th International Conference on Language Resources and Evaluation: Workshop on Language Resources for Linguistic Creativity, pages 56–61, Lisbon, Portugal, May 2004.

Cattinelli I, Goldwurm M, Borghese NA, Interacting with an artificial partner: modeling the role of emotional aspects, Biol Cybern,99(6), 473-489, 2008.

Jordan MI, Bishop C, Introduction to graphical models, 2004.

Villacorta P, Quesada L and Pelta D. Automatic Design of Deterministic Sequences of Decisions for a Repeated Imitation Game with Action-State Dependency - Proc. CIG 2012.

Alamia M, Borghese NA, (2010) Creating long gait animation sequences through Reinforcement Learning Frontiers in Artificial Intelligence and Applications; Volume 226, 2011; Neural Nets WIRN10 – Proc.20th Italian Workshop on Neural Nets, pp. 144 – 151.

Riedl and Young, Narrative Planning: Balancing Plot and Character, Journal of Artificial Intelligence Research 39 (2010) 217-268.

T. W. Bickmore and R. W. Picard, B Establishing and maintaining long-term human-computer relationships[ ACM Trans. Comput.-Human Interaction, vol. 12, no. 2, pp. 293–327, Jun. 2005.

Belpaeme, T., Baxter, P., Read, R., Wood, R., Cuayáhuitl, H., Kiefer, B., Racioppa, S., Kruijff-Korbayová, I., Athanasopoulos, G., Enescu, V., Looije, R., Neerincx, M., Demiris, Y., Ros-Espinoza, R., Beck, A., Cañamero, L., Hiolle, A., Lewis, M., Baroni, I., Nalin, M., Cosi, P., Paci, G., Tesser, F., Sommavilla, G. & Humbert, R. (2012) Multimodal Child-Robot Interaction: Building Social Bonds. Journal of Human-Robot Interaction, 1(2), 33-53.

Takayama, L., Dooley, D. and Ju, W. (2011). Expressing thought: Improving robot readability with animation principles. Proceedings of the IEEE/ACM International Conference on Human-Robot Interaction.

T. Ducourant, S. Vieilledent, Y. Kerlirzin, and A. Berthoz, “Timing and distance characteristics of interpersonal coordination during locomotion,” Neuroscience Letters, vol. 389, no. 1, pp. 6–11, November 2005.

E. Sisbot, L. Marin-Urias, R. Alami, and T. Simeon, “A Human Aware Mobile Robot Motion Planner,” IEEE Transactions on Robotics, vol. 23, no. 5, pp. 874–883, Oct. 2007; D. J. Feil-Seifer and M. J. Matari´c, “People-Aware Navigation For Goal-Oriented Behavior Involving a Human Partner,” in Proceedings of the International Conference on Development and Learning, Frankfurt am Main, Germany, Aug. 2011.

De Cindio, F, Peraboni, C, Building digital participation hives: Toward a local public sphere. In M Foth, L Forlano, C Satchell & M Gibbs (Eds), From social butterfly to engaged citizen: Urban informatics, social media, ubiquitous computing, and mobile technology to support citizen engagement. MIT Press, 2011

Nonaka I., Takeuchi H., The Knowledge Creating Company, University Press, Oxford 1995.