Resources required

1. UMIL

- Staff on project: 2 Senior researchers for 27 MM total + 2 Post-docs for 30 MM each + 1 Manager of TTO for 2 MM

- Equipment: 1 robot Giraff: 9.7K

- Travel: 4.5K for project meetings, 4.5K for short visits and development / testing on partners site, 7K for scientific meetings in which to present Robohome2.0 results, 3K for visiting on site and coordination / management activities.

- Consumables: 3.8K

- Other costs: 3,5K for external auditing and 1,5K for PSC meeting organization.

- Subcontracting: None.

2. ORU

- Staff on project: 1 PI 11 MM + 1 PHD student 24MM + 1 Post-doc 18 MM for a total of 53 MM

- Equipment: 1 robot Giraff: 9.7K

- Travel as UMIL: 4.5K for project meetings, 3.0K for short visits and development / testing on partners site, 6K for scientific meetings in which to present Robohome2.0 results.

- Other costs: external auditing: 3.0K.

- Subcontracting: None.

3. Giraff Technologies AB

- Staff on project: 15,3MM Senior researchers.

- Equipment: 1 robot Giraff: 9.7K

- Travel: 4.5K for project meetings, 6.5K for short visits and development / testing on partners site.

- Consumables: 2K.

- Subcontracting: None.

4.University of Plymouth

- Staff on project: 1 PI for 5 MM, 1 Post-doc for 36MM.

- Equipment: 1 robot Giraff: 9.7K

- Travel: 4.5K for project meetings, 7K for Scientific meetings, 5.5K for short visits and development / testing on partners sites.

- Other costs: 5K for students projects and 3K for external auditing.

- Subcontracting: None

5. SXT Srl - Sistemi per Telemedicina

- Staff on project: 3 senior engineers for 45.5 MM.

- Equipment: 4.2K for specific SW licenses for the time dedicated to the project. 4.2K for SDK and licenses for new generation low-power CPUS and Bluetooth 4 Smart device SDK. 0.9K for 1 PC for development end test on field (three years and further demonstration). 3.5K for special plants and equipment for the production for the prototypes.

- Travel: 4.5K for project meetings, 6.5K for short visits and development/testing on partner sites

- Subcontracting: None.

6. Fondazione IRCCS Cà Granda Ospedale Maggiore Policlinico

- Staff on project: 1 PI for 1MM, 1 Senior researcher for 2MM, 1 senior psychologist for 2 MM; 1 sociologist for 1MM; 2 Post-doc for 22MM each

- Equipment: 3 robots Giraff: 29.1K

- Travel: 4.5K for project meetings, 6 K for Scientific meetings, 2.5K for short visits and development / testing on partners sites.

- Subcontracting: None.

7. Politecnico di Milano

- Staff on project: 2 Senior researchers for 23 MM total + 1 Post-docs for 24 MM + 1 assistant professor for 30 MM.

- Equipment: 12 full sets for clinically validated instrumentation for: blood pressure and heart rate physiological measurements (4800K), Equipment for multiparameters physiological measures (HR, BP Glucose, Oxygenation, 14400K), Glucometers (8400K). 2 laptop (2400K).

- Travel: 4.5K for project meetings, 4.5K for Scientific meetings, 2K for short visits and development / testing on partners sites.

- Other costs: 3,5K for external auditing

- Subcontracting: None.

8. Fundació Privada Barcelona Digital Centre Tecnològic

- Staff on project:  1 PI, 2 Senior researchers  + 1 Junior researcher at partial time for a total of 68 PM.

- Equipment/materials:  6K for a dedicated server + 6.5K for 11 sets of monitoring sensors for the installations at homes + 1K for 1 PC full dedicated (for Robohome 2.0 developments) + 1,5K for 2 Android and iOS-based smartphones full dedicated (for Robohome 2.0 developments)

- Travel: 4.5K for project meetings, 8.5K for short visits and development / testing on partners site

- Consumables: 3.5K

- Other direct costs: 3K for External auditing

- Subcontracting: None

9. Servicio Andaluz de Salud

- Staff on project:  1PI Medical Doctor (6PM)+ 2 nurses (19 PM) + 1 medical doctors + 1 psychologist +1 sociologist (20PM) + 1 European project manager (2PM) for a total of 47PM

- Equipment: 3 robots Giraff: 29.1K

- Travel:  14 K in total (7k for project meetings + 4k for WP training meetings+ 3k for dissemination events attendance)

- Consumables: 1.5 k (pilot material)

- Other direct costs: 3k (for auditing and meeting organization)

- Subcontracting: None.

10. Korian

- Staff on project: 1 PI for 10 MM, 1 Junior investigator for 7MM, 1 Junior geriatrist for 13 MM; 1 junior physiotherapist for 13 MM; 1 psychologist for 8 MM; 1 nurse for 3 MM.

- Equipment: None

- Travel: 4.5K for project meetings, 8.5K for short visits and testing on partners site.

- Subcontracting: None.

11. Signal GeneriX Ltd

- Staff on project: 20 MM for 2 senior engineers.

- Equipment: None.

- Consumables: DSP and FPGA development boards, hardware components, development software for 9K Euros.

- Travel: 5.5K for project meetings, 8.5K for short visits and testing on partners site.

- Subcontracting: None

12. University of Malaga

- Staff on project: 2 Senior researchers for 18 MM total + 1 Post-docs for 20 MM + 1 Senior Engineer/CS for 10 MM.

- Equipment: 1 robot Giraff: 9.7K

- Travel:  9 K for project meetings, 6 K for scientific events (conferences, workshops, etc.), 3 K for supporting the pilot test site and for short visit to partner sites.

- Consumables: 2K.

- Other costs: 1.5K for PSC meetings organization.

- Subcontracting: None .

13. OREBRO Municipality

- Staff on project: 1 senior clinician (PI) for 3,5 MM, 2 clinicians for 12MM +1 sociologist for 1 MM + 1 Psychologist for 2MM + 1 therapist for 6MM for a total of 24,5 MM

- Equipment: 1 robot Giraff for 9.7K

- Travel: 4.5 K for project meetings, 5,5 K for scientific events (conferences, workshops, etc.).

- Subcontracting: None.