Call: H2020-PHC-2014-single-stage

Objective: PHC-19-2014: Advancing active and healthy ageing with ICT: service robotics within assisted living environments

Type of action: Research and innovation actions

- ROBOHOME2.0

Service ROBOt to monitor, assist and evaluate the elder at HOME

- ABSTRACT

Robohome2.0 develops, integrates and field tests an innovative robot based system to assist and monitor the elder at home actively promoting healthy lifestyle. The system consists of three hierarchical levels: 1) Core of the system is an intelligent virtual caregiver embodied into a service robot that guides the elder in personalized activities to improve lifestyle through state-of-the art Artificial Intelligence. It also helps the elder in critical everyday tasks, such as finding the lost keys, and in therapy adherence. 2) The virtual caregiver collaborates with a service layer including a distributed pervasive monitoring system that is transparent to the elder that provides quantitative information on early physical / cognitive decline and social attitude. It is also interfaced with an activity center that select and adapt activities, tailored to the user’s idiosyncrasies and needs. These activities are mainly conveyed through an adaptive, challenging gamification platform to stimulate motivation and to sustain attention. 3) The highest level is constituted of a users’ virtual community that connects the elder with clinicians, caregivers and other pairs promoting socialization and increased knowledge.

The polestar is to assemble off-the-shelf components in a robust and reliable way to get a low-cost system that can be deployed massively at home. A fully modular approach will assure the system to be tailored on single user needs. The use of the most wide-spread software and hardware standards will maximize interoperability and make the system adaptable to the utmost novel sensors and components. Configurability, personalization and automatic adaptation to elder needs and behavior applies also to interfacing modalities, with the aim of maximizing elder compliance, even when computer illiterate. A pilot evaluates effectiveness and suitability of Robohome2.0 and studies the most appropriate model to seamlessly connect home assistance to supervision by the public health network system and an adequate business model.

- Keywords

Robotics, gerontology, gamification, autonomous navigation, smart objects, sensor network, human robot interfacing, frailty, ambient assisted living, healthy and active ageing, social inclusion, independent living, [add keywords

Call: H2020-PHC-2014-single-stage

Objective: PHC-19-2014: Advancing active and healthy ageing with ICT: service robotics within assisted living environments

Type of action: Research and innovation actions

- ROBOHOME2.0

Service ROBOt to monitor, assist and evaluate the elder at HOME

| Participant no. | Participant organization name | Short name | Country |
| --- | --- | --- | --- |
| 1 (coordinator) | Università degli Studi di Milano | UMIL | IT |
| 2 | Orebro University | ORU | SWE |
| 3 | Giraff Technologies AB | GIRAFF | SWE |
| 4 | University of Plymouth | UOP | UK |
| 5 | SXT Srl - Sistemi per Telemedicina | SXT srl | IT |
| 6 | Fondazione IRCCS Cà Granda Ospedale Maggiore Policlinico | Fondazione IRCCS Cà Granda Ospedale Maggiore Policlinico | IT |
| 7 | Politecnico di Milano | POLIMI | IT |
| 8 | Fundació Privada Barcelona Digital Centre Tecnològic | BDIGITAL | ES |
| 9 | Servicio Andaluz de Salud | SAS | ES |
| 10 | Korian | KORIAN | FR |
| 11 | Signal GeneriX Ltd | SG | Cyprus |
| 12 | Unviersity of Malaga | UMA | ES |
| 13 | OREBRO Municipality | OREBRO KOMMUN | SWE |

| Name of the coordinating person: | Nunzio Alberto Borghese |
| --- | --- |
| Tel: | +39.02-503.16373 |
| E-Mail: | alberto.borghese@unimi.it |

# Table of content

ROBOHOME2.0	1

ABSTRACT	1

Keywords	1

ROBOHOME2.0	2

Table of content	3

1. Excellence	4

1.1 Objectives	4

Robohome2.0 General Objective	4

Specific Objectives	5

1.2 Relation to the workprogramme	7

1.3 Concept and approach	10

1.3.1 Overall concept	10

1.3.2 TRL analysis	11

1.3.3 Relationship with National and International Research and Innovation activities	12

1.3.4 Overall approach and methodology	14

Clinical Evaluation	14

Monitoring	15

Clinical Evaluation	19

Assistance	19

Activity center	21

Service Robot and Virtual Caregiver	25

Community of users	28

Deployment modalities.	31

1.3.5 Sex and/or gender analysis	32

1.4 Ambition	32

1.4.1 Beyond the state of the art	32

Monitoring	32

Assistance	34

Activity center	34

Interfacing	36

Community of users	37

1.4.2 Innovation potential	37

Patent search	37

Annex G. Technology readiness levels (TRL)	39

# 1. Excellence

# 1.1 Robohome2.0 General Objective

In Europe, the share of people aged 65 years or over in the total population is projected to increase from 17.1% to 30.0%,  going   from 84.6 million in 2008 to 151.5 million in 2060. Similarly the number of people aged 80 years or over is expected to almost triple from 21.8 million in 2008 to 61.4 million in 2060 and the availability of nurses is already becoming an issue in the US.

Physical activity, cognitive stimulation, social inclusion, balanced diet, therapy adherence and regular clinical screening promote a lifestyle that slows down the decline, thus enabling the elder to live at his home healthier and for a longer time. This is becoming a priority in Europe as recognized by the EC community: managing frailty and functional decline through targeted interventions, enhancing participation and independence, and promoting systematic-routine screening for pre-frailty are among the specific objectives of the Action Plan on “Prevention and early diagnosis of frailty and functional decline, both physical and cognitive, in older people” of the European Innovation Partnership on Active and Healthy Ageing (Bruxelles, November 6, 2012). Several approaches have been proposed to address these aspects but a comprehensive solution is far to be provided. Moreover, a high emphasis is often put on wearable devices for monitoring that limit the compliance of the users, especially on the long run [PSYCHO ISSUE – PCL].

Robohome2.0 is an intelligent system, integrating an existing robotic platform with environmental sensors, and smart objects, advanced user interfaces, a virtual community and an activity center, to provide assistance, transparent monitoring and continuous clinical evaluation of the elder at home through a full-fledged, modular, personalized, compliant approach.

Indeed, ongoing robotics, smart objects and smart homes and Human Robotic Interfaces (HRI) research plays a key role in this panorama for matching increased life expectancy with the enhancement of the quality of life as people grow old. Robohome2.0 builds upon most recent results in these areas to realize a prototype, test it into real-life environment so to get the ambition to find its way to the market. To this aim

Robohome2.0 will assemble off-the-shelf components in a robust and reliable way to get a low-cost hierarchical system that can be deployed massively at elders’ home.

Such system will provide several key aspects of clinical monitoring: a) Early cognitive and physical decline will be monitored by the robot observing and analyzing common everyday tasks (e.g. combing hair, preparing coffee), in cooperation with adequate sensorized objects, thus making the elder not aware of being monitored (transparent monitoring). b) Profiling of phone conversation will be done to identify meaningful changes in the emotional content associated to some degenerative deseases. c) Physiological samples (e.g. glucose level, pressure, oxygen saturation) will be provided by an adequate sensors’ network. d) A smart drug dispenser will provide to the elder the right pills at the right time thus largely increasing therapy adherence. e) Activities of Daily life (ADL) will also be monitored (e.g. number of hours of sleep that are related to ipnotic medicaments; home temperature that is associated to quantity of liquids to be taken, and so forth).

The robot will be able also to assist the elder in a confident independent living in finding lost crucial objects (e.g. the mobile phone, the TV remote control, the keys, …)  inside the house and will give the elder feed-backs, recommendations and suggestion through a virtual caregiver avatar.

Robohome2.0 will support an active lifestyle recommending and guiding the elder through a personalized mix of physical, cognitive and social activities that are tailored to the adequate challenging level. We will fully explore gamification to maximize motivation, sustain attention, and train memory and we will explore automatic narration to provide long life engagement. These same concepts will be explored in educational games on the elder diseases and lifestyle.

Gamification will be explored also through the virtual community that will not only support competition / cooperation in physical and cognitive games but also provide support for social games like cards games such that the elder is incentivized to avoid isolation. The community will connect all people involved: caregivers, GPs, geriatrists and elders that will be able exchange information and increase knowledge.

Activities, assistance, recommendations, monitoring, tuning will be managed by the robot through an embodied virtual caregiver, context aware, that will use the huge amount of etherogenous data coming from sensors, community and activity center to refine its stimuli, to evaluate the elder’s status and the tune the profile.

To guarantee system use, maximum compliance with the elder is required. Particular care will be put in the design of interfacing modalities not only from the technological point of view, but also from the psychological one to foster the development of stable and positive bonds. A distributed voice command system will be explored to enable voice commands.

Giraff robot has been identified as the most suitable robot for Robohome2.0. Giraff is the result of progressive work in the domain of assisted living and its development was partly financed by the AAL “ExCITE” and FP7 “GiraffPlus” projects. It is basically a robotics base carrying a control PC and an adjustable touch-screen monitor, whose target price for massive production is below 1K Euros. Because of Giraff’s commercial potential it was awarded “Most Promising Innovation” of 2011 by the AAL organization. It has an open software architecture that allows to easily add functionalities as we will fully exploit in Robohome2.0.

## Specific Objectives

In particular, here are the specific Objectives of Robohome2.0:

      - To improve Giraff robot capabilities of interaction with the elder

- To design and implement interfacing modality that promote a good emotional relationship between the elder and Giraff robot.

- To monitor and prevent frailty, age-related cognitive and physical decline and social exclusion, a hands-off network of sensors to evaluate activities of daily living and behavior, transparent to the user.

- To design and develop a context-aware virtual caregiver able to profile the single elder’s interests and condition, suggesting motivated exercises and activities as well as providing formal and informal carevigers, relative and clinicians information specific to their role.

- To develop assistance in everyday task by the Giraff robot.

- To design and implement a personalized activity center system.

- To promote elders health education, self-empowerment, and increase their perceived usefulness in the society aiming at improving quality of life of the elders and of their formal and informal caregivers.

- To field test a complete ecosystem, involving all players, to gather evidence of Robohome2.0 benefits.

- To demonstrate the cost-effectiveness of technology and develop a proper business models for the technology transfer to massively deploy Robohome2.0 within a sustainable healthcare system.

To address these challenges Robohome2.0 will develop the following set of devoted technologies and methodologies aimed at creating an ecosystem to support prolonged life at home:

1. To improve Giraff robot capabilities of interaction with the elder. Giraff will be transformed from a teleoperated robotics platform into a robotic platform endowed with autonomy fully exploiting vision capabilities offered by adding a 3D camera, like Kinect. Such approach will make Giraff an active companion for the elder that can assist in finding objects, gives him/her advice, feed-backs and recommendations, monitors everyday tasks and carries around the activity center to allow the elder exercising in the best time and place (WP3).

2. To design and implement interfacing modality that promote a good emotional relationship between the elder and the Giraff robot. A good relationship between Giraff and the elder is a very powerful mean to guarantee motivation in the interaction, easiness and even pleasure and increase the compliance in the use of the system. This is based on a constellation of activities and functions that will be carefully evaluated from the psychological point of view. Gamification, interaction modalities, unified GUIs and assistance in everyday life tasks will be part of this. We will exploit also several social intricacies in the interface with Giraff, like empathy, humour, references to mutual knowledge, continuity behaviors, politeness and trust. The information gathered by the sensors’network along with the inputs provided by the caregivers will be used by the virtual caregiver to create meaningful suggestions to the elder (WP2, WP3).

Scenario: Mike is wandering around at home, while Giraff, comes to him and says: “Today is the birthday of Matthew, your nephew, why don’t you call him?” Mike illuminates, and with a smile, he looks for his mobile phone to call Matthew. Unfortunately, he could not remember where he put it. He calls again Giraff and asks “where is my phone?”. Giraff activates the automatic location system, and after a while it moves towards the kitchen and takes a picture with its Kinect camera to the phone, partially showing under a box. Giraff sends a voice message to Mike, who can get the phone and calls Matthew. Mike is so grateful that he wants to kiss Giraff for this help… and Mathew too.

3 Monitoring the elder. Monitoring will be carried out while the elder executes the actions of everyday living. Instead of instrumenting the elder, we will instrument some of everyday life objects, like a tea cup, a comb, a fridge handle or other everyday use instruments, depending on elder’s habits. Instrumentation will provide wireless, real-time synchronous data on motion and handling pressure. We will sensorize also objects like a walking stick or a trolley, that are used to deambulate also outdoor, to evaluate the activity level and parameters for the stability of gait. We will combine vision provided by Giraff with information provided by all the sensorized objects to derive a “signature” of the movement. From these data we will define and validate indexes that will be made available to clinicians for elder evaluation. Transparent tests of clinical assessment of cognitive decline will be administered as spot questions or spot activities intermingled in the everyday tasks and games. We will also explore pitch analysis of phone conversations to early detect on-set of cognitive neurodegenerative diseases. Environmental sensors, e.g. measuring temperature, gas lost, humidity along with the gaming scores, and lifestyle monitoring will drive the virtual caregiver intelligence (WP5 and WP6).

4. To design and develop a context-aware intelligent virtual caregiver which realizes a closed-loop assistance system that cooperates with caregivers and clinicians. The virtual caregiver will analyze the huge amount of heterogenous data provided by the pervasive monitoring systems and the activity center and a) suggests structured and unstructured physical, cognitive and social activities to the user, adapting the level of difficulty to the current elder’s status. b) tune the estimated state of the elder according to data from the monitoring systems and the activity center and update his/her profile. c) provide the caregivers and the GPs with the relevant information on the elder status (WP3).

5. To develop assistance in everyday task by the Giraff robot. A key element to promote a solid bond between the robot and the elder is trust. One element that can help creating this bond is solving problems, even small, in everyday life. Loosing objects like keys, reading glasses or mobile phone is common and enabling Giraff to locate them for the elder can promote trustiness in the relationship. A novel system based on distributed microphones pairs with DSP processing capabilities will allow the elder to call Giraff, also when in a different room, realizing a distributed command system. Giraff will  guide the elder in taking prescribed physiological measurements, like blood pressure or glucose, at the correct time intervals through video/animation instructions with voice explanation. A smart drug dispenser, built on miniaturized mechanics and electronics, will made available only right pills at the right time with alert signals remembering the therapy timing (WP3).

6 To design and implement a personalized activity center, based on the gamification paradigm and fully integrated with the robot and with the community of users. The service will provide cognitive and physical exer-games that can be played preferable with other peers through the virtual community. These games will be designed upon a set of exercises defined by the clinicians to specifically train declining functions. Social activities, like playing cards through the virtual community, will also be supported to promote socialization and avoid isolation that is often the first step towards depression [POLICLINICO quotation].

7. To promote elders education to a healthy lifestyle, self-empowerment, and increase their perceived usefulness in the society aiming at improving quality of life of the users and their formal and informal caregivers. The activity center will provide also exer-games to support elders education for  healthy lifestyle, promoting knowledge and self-empowerment. The approach will be based on ontology automatic narration to define mini-games that can be casted into episodes, matched to pieces of knowledge on the diseases or lifestyle. We will explore how combine this with stochastic models, like stochastic finite state machines to chain episodes into stories. Reinforcement learning will be explored to steer the story development towards themes tuned on the elder preferences. Popular containers like fairytales, for which a clear structure has been proposed already at the beginning of last century, or sports competitions will be used. We will also implement a repository of real life stories recorded to Giraff from the elders themselves on a particular theme provided at regular intervals by the community manager (WP4).

8. To field test a complete ecosystem, involving all players, to gather evidence of Robohome2.0 benefits. The satisfaction of the end users is the “north star” in guiding the development of Robohome2.0. An end user advisory board will be set early in the project to help keeping the project on track representing the different players: geriatrists, GPs, caregivers, elders, political stakeholders, and service providers. The components and the system will be deployed  in successive stages inside the living labs provided by ORU and SAS in order to testing them, early on,  in strict link with the developers (WP8).

9. To demonstrate the cost-effectiveness of the technology and develop a proper business models for the technology transfer to massively deploy Robohome2.0 within a sustainable healthcare system. We envisage a business model based on service providing by a service company, like KORIAN (P10). This will be supported by an ICT service provider that provides the cloud that hosts the community and the data. Such system will integrate the components developed by the three industrial partners GIRAFF, SG and by SXT into a flexible, scalable and modular system that can be offered to the elders at home. Such model will be tested through experimentation. In particular, we will evaluate the actual market and available services and test how the different actors involved: from public to commercial entities, non-profit, philanthropic and other forms of social organization, can be involved. Costs and benefits will be made explicit, analyzing also hidden costs in the actual model. This will regard the whole system as well as its constituents and will be carried out throughout the project development (WP9).

# 1.2 Relation to the workprogramme

| Robohome2.0 Contribution | Milestone | PHC19 target outocomes |
| --- | --- | --- |
| We address these three risks with a holistic approach that is based on three main pillars: monitoring, assistance and evaluation that are not carried out in isolation, but mix the three aspects at the point of need. Data are gathered mainly in a transparent why, while the elder carries out the activities of everyday life. | 5 | Specific challenge: Citizens in an ageing European population are at greater risk of cognitive impairment, frailty and social exclusion. |
| Cognitive impairment will be addressed in a pro-active way, by proposing activities and exer-games that are negotiated with him/her and are adapted to the actual elder competences, status and psycho-physical condition. Cognitive tests of clinical validity will be administered in a transparent way to the elder through the activity center. Early detection of cognitive degenerative diseases through audio analysis of phone conversation will be explored. | 3 | How Robohome2.0 will reduce the risk of cognitive impairment. |
| Robohome2.0 will stimulate the elder to an active lifestyle in which a personalized mix of cognitive, physical and social activities is suggested. Data from the activity center and the monitoring systems are used to evaluate the current psycho-physical status. This allows Robohome2.0 identifying possible physical and cognitive decline. Specific validation of these decline indexes will be included into the project activities; they will be functional to a) adapting the system and the activities mix to the changing conditions of the user; b) follow up the user status keeping the carers informed and eventually favoring appropriate and timely interventions. Robohome2.0 helps the elder in therapy adherence in several ways: it provides home measurement of physiological parameters, it increases elder’s awareness on lifestyle importance through game based education and it provides a smart drug dispenser. | 3 | How Robohome2.0 will reduce the risk of frailty. |
| Robohome2.0 will set-up a community of users that will self-organize to propose connection with elders with similar profiles. The community will support multiplayer gaming and activities to promote socialization. It will also be the place inside which to exchange experiences and knowledge. Robohome2.0 intelligence will make simple suggestions to the users including solicitation to stay in touch with relatives, friends, etc., following the specific setting of the single user. A profiling of social activity through log book and phone conversation analysis will be carried out. | 3 | How Robohome2.0 will reduce the risk of social exclusion. |
| Robohome2.0 will push the elder keeping active with an everyday cognitive and physical training, properly calibrated on the single user’s requirements, assuring rewarding experience and confidence of the subject in her/his capability. In addition, Robohome2.0 will help the elder in some simple but basic tasks related to independent living such as finding the keys, the glasses and the mobile phone, remembering the time for having meals, the drugs to assure prescription adherence and assists him/her with the diet. Specific supervision of physiological parameters (e.g. blood pressure, heart beat, glucose level, oxygen saturation) will be included into the Robohome2.0 system so to alert critical situations, thus allowing anticipated discharge from the hospital and limiting the risks of relapses. Robohome2.0 will communicate the alarm directly to the adequate type of caregiver. | 3 | with considerable negative consequences for their independence, |
| The carers will be helped in the care practice by day-by-day monitoring information. An increased participation of the life of the elder through the community that allows providing information, recommendation and audio-video connection will help in keeping a strong bond also when being physically present is not possible. | 4 | quality of life, that of those who care for them… |
| The progress of the physical decline of elderly people sometimes is abrupt, such as in case of dramatic events (stroke, falls, psychological traumas) but sometimes it is a slow progress which might be even neglected by the relatives. The lack of recognition of worsening could provoke delayed interventions which amplify the decline itself, inducing a negative loop which impact on the requests to the health and care system. Transparent monitoring inside Robohome2.0 allows to objectively assess cognitive and physical decline continuously over time. It will communicate a periodic reports to the GP, so to allow prompt and tuned intervention in case of worsening conditions, slowing down the progression. Robohome2.0 will allow private partners, like KORIAN, to provide an effective continuity of care and assistance with public bodies. A business plan will be elaborated on this substantiated by project results. | 4 | and for the sustainability of health and care systems. |
| Hereafter, an analysis of the crucial ingredients of the aim of the call with respect to the Robohome2.0 proposal is detailed. Service robotics: The Robohome2.0 project is based on a commercial off-the shelf service robot (Giraff), which will be enriched with adequate features. Transparent Monitoring system: we will monitor the elder through the usage of everyday objects without requiring that he/she wears any device or does any particular action. Activity center: it is based on gamification and it provides a customized mix of activities with the adequate level of challenge that involve the community of users. Assisted living environment: proper environmental sensors will be integrated into the Robohome2.0 to monitor the home and elder’s behavior. | 5 | The challenge is to develop new breakthroughs for active and assisted living based on advanced ICT solutions. |
| Core of the system is Giraff robot that embodies an intelligent virtual caregiver. It monitors him/her through a monitoring network embedded in the house and in cooperation with sensorized objects of everyday use, thus achieving a monitoring completely transparent to him/her. It advices him/her and suggests tailored activities and looks for lost objects. | 3 | Proposals should focus on service robotics in assisted living environments which can help an ageing population to remain active and independent for longer. |
| - behavioural disciplines: to develop emotional bonds with a new body in the house, like a service robot, is fundamental for acceptance and a good interaction. Therefore interfacing functionalities and interface design will be inspired by this. UOP and PCL have complementary expertise. UOP has a strong background on Human Robot Interaction and PCL has a strong background in elder psychology [Carlo Abbate should be added on staff]. They will contribute to functional design and testing of the components and the whole system to maximize user acceptance. - social disciplines: social scientists from MUN and PCL will assure both in the design of the virtual community and in the evaluation phases that the project has a positive impact both on the social inclusion of the user and on the caregivers (including the family, the carers, the family doctor, the clinicians involved in the care as well as the society, in more extended sense) [PCL, SAS review please]. - health disciplines: regular physiological sampling and clinical assessment and smart drug dispenser provide clinical monitoring and compliance. This will be complemented with providing structured knowledge and education through gamification. Two teams of clinicians (PCL and SAS) with complementary specializations (GP and geriatrist) and a group of bioengineers (POLIMI) will collaborate in the project to design, develop and validate tests, of clinical validity, based on the analysis of ordinary life actions to assess the physical and cognitive status of the elder. | 4 | The project should combine multi-disciplinary research involving behavioural, sociological, health and other relevant disciplines. [SAS, KORIAN, and POLICLINO] Specify here additional competences related to this. |
| Indeed, Robohome2.0 will be built with modularity and flexibility in mind both at the hardware and software level. Environment monitoring will be built upon scalable protocols, like z-wave, already diffused in the domotic field. Sensorized objects will be built integrating a transmission module based on most diffused wireless transmission protocols. The activity center will allow providing a mix of exer-games specifically tailored to the user and to adapt automatically the level of difficulty to the user present ability. The system will be managed by the virtual caregiver that will implement deductive reasoning on the data received from the monitoring systems, the activity center and the community and the inputs from the caregivers and the GPS all organized inside the frame of an ontology. The use of off-the-shelf components and standardization, and the integration of already developed sensors and physiological measuring devices, allows to realize a cost-effective system and meet the widest range of functional requirements. | 4 | Characteristics of the solutions developed should be their modularity, cost-effectiveness, reliability, flexibility in being able to meet a range of needs and societal expectations, |
| Robohome2.0 will be tested from early on in specific living labs identified in Sweden and Spain. This will be fundamental to develop a system that can be really acceptable and compliant with the end users and the elders in particular. The pilot test in WP8 allows evaluating the compliance and suitability of Robohome2.0 also in real apartments inside which elder lives, as well as the safety of the technology. An end users advisory board will be set in the first months of the project with the aim of having an external highly qualified feed-back on project development, from the representatives of all the types of Robohome2.0 users. | 4 | applicability to realistic settings, safety and acceptability to end-users. |
| The activities proposed will be designed having gender in mind, realizing games episodes inspired to at least two themes, one most suitable to female and one to male attitude. [PCL::ABBATE, You may want to rephrase this]. Similarly, the avatar of the virtual therapist and all the elements that are gender sensitive, will be designed such that a configuration in the male and female version would be possible. | 2 | Gender and ethical issues should be paid due attention. |

# 1.3 Concept and approach

## 1.3.1 Overall concept

Robohome2.0 is a hierarchical platform aimed at supporting the elder, for a prolonged time, at his home, monitoring him/her and guiding him/her to a healthy lifestyle. It consist of three hierarchical levels (Figure 1): 1) a Core layer constituted of an intelligent virtual caregiver that provides feed-back and recommendations to the elder suitable to his/her state and to the lifestyle negotiated with his/her caregivers, embodied into a service robot the provides assistance. 2) a service layer that includes a distributed pervasive monitoring system that is transparent to the elder that provides quantitative information on early physical/cognitive decline and social attitude, and an activity center that guides the elder in activities, tailored to elder idiosyncrasies and needs and implemented through gamification, to stimulate the maximum adherence and motivation. 3) a Community of users connecting elders and other actors, aimed at improving socialization and knowledge.

These components will not work as stand alone but they will cooperate, under the supervision of the Virtual Caregiver, to provide key functionalities: a) regular clinical monitoring to control physiological parameters critical for the elder’s disesases, b) cognitive and physical assessment to early detect decline, c) lifestyle and social behavior evaluation to early detect risk of exclusion, d) an activity center that suggests and guides the elder in personalized cognitive and physical games, e) actively promotion of social activities, f) increase of knowledge in the elder’s diseases to promote empowerment, g) assistance in everyday tasks, and h) meaningful interaction with Giraff and the other components.

These functionalities, are not isolated but they are tightly interconnected. For instance, regular physical exercise has been shown to be effective at maintaining and improving the overall health of elderly individuals,,.. Physical fitness is associated with higher functioning in the executive control processes, correlated with less atrophy of frontal cortex regions, and with improved reaction times compared with the sedentary. Social interaction, and specifically high perceived interpersonal social support, has also been shown to have a positive impact on general mental and physical wellbeing, in addition to reducing the likelihood of depression,,,. We will fully exploit the unique possibility of Robohome2.0 of addressing all these aspects to provide functionalities through the best component of mix of components and functionalities of each elder. Moreover, they will allow to implement a closed loop monitoring and assistance system that continuously updates the elder profile upon the data from the activity center and from the monitoring systems, recommends a mix of activities, personalized and with a challenge level suitable to the elder status and provide tailored monitoring systems to elder needs.

Figure 1 .- The hierarchical structure of Rohohome2.0. The core layer is constituted of the Virtual Caregiver embodied in the Giraff robot and it is displaced at the elders’ home with the service layer. The latter is a modular layer that provides monitoring data to the virtual cargiver and offers functionalities to the elder: activity center, knowledge and assistance. The elder, his/her caregivers and the clinicians are all part of a community of user that promotes socialization and knowledge.

Such approach does call for various competences that are well represented in the consortium composition: clincians (GPs, geriatrists, physiotherapists, neurologists) are represented by SAS, PCL and KOMMUN, sociologists by KOMMUN, bioengineers by POLIMI and ICT researchers by ORU, UMIL and UMA. This will allow developing an inter-displinary research approach, promoting a strong bidirectional translation research approach, facilitating the communication between the non-technical and technical teams to come up with a shared view on how the Robohome2.0 platform should be (WP1, WP2). Plenary meetings at the different partners sites in the first stage of the project, will allow to better elucidate problems and current solutions on one side and on the other side make clear the current technological offer.

## 1.3.2 TRL analysis

The project is positioned in different Technology Readiness Levels (TRL) considering the various functionalities to which it is aimed and the whole platform.

Regular clinical monitoring of physiological parameters will be accomplished integrating off-the-shelf components that will have already been validated are therefore already products on the market. These components will be possibly integrated with the virtual caregiver that will provide instructions in audio-visual form. Data will be transmitted to the virtual caregiver and from it to the community. This activity is expected to be at TRL7 at the end of the project.

Cognitive and physical assessment. A very innovative approach will be followed here. Sensorized everyday objects (TRL3) will be combined with motion acquisition through Giraff robot to provide synchronous motion and pressure data. Motion acquisition requires Giraff robot to approach the elder and orient the camera adequately with respect to the elder (TRL2). The fused data will be used to segment movement into components (TRL4) and derive a degradation index of clinical validity (TRL1). The high effort in this work in Task5.1 and 5.2 will provide a TRL6 technology at the end of the project. Voice pitch analysis explored for early detection of onset of cognitive degenerative diseases it at TRL1 presently. We expect to obtain a technology at TRL4 by the end of the project. We will also explore cognitive and physical exer-games provided by the activity center from which specific assessment parameters can be evaluated. The starting point is TRL1 and we expect to have the parameters validated by the end of the project (TRL7).

Lifestyle and social behavior evaluation. We will use standard components like z-wave, that will be assembled into a modular and flexible network (TRL8/TRL9) and integrate it with the robot. Its information will be integrated with data from monitoring and from the activity center to update the elder profile and tune the recommendations and monitoring (TRL4). We expect to provide a technology close to TRL8.

Activity center. The activity center will be largely based on the IGER game engine is being currently validated on the field within the REWIRE project (TRL5). We will extend it to support mix of exer-games that involve also cognitive exercising and support for multiple output devices. We will build a new layer to address knowledge acquisition and long term motivation through gamification. Both these extensions will be starting from TRL2. We expect to arrive at TRL7 with the pilot.

Promotion of social activity. This will be supported by a virtual community of users that will be built starting from BDIGITAL experience inside the projects REWIRE, BACKHOME and SAAPHO, in which it has coordinated the work related to the implementation of the community services and environment monitoring (TRL5). The community features will be tailored to requirements of Robohome2.0 and further developed. It is expected to arrive at TRL7. The community will also support multi-player games, typical card games. Multi-player view will be integrated through multiple video streaming through for instance WebRTC technology (TRL8). Multiple videos will be combined with a dynamical graphical scene showing score, cards and other relevant information (TRL2). We expect the component to be at TRL7 at the project end.

Increase of knowledge. This will be mediated by the community of users (TRL5) and by continuous education through gaming created through automatic narration (TRL3). We expect to arrive a TRL6 by the end of the project.

Assistance in everyday tasks. Proposed systems on the market for locating objects have limitations in range and power consumption. The technology is presently at TRL3 but it is likely to increase its level at the time the project will start. We will explore this technology in combination with robots navigation. We expect to bring this methodology at TRL5 Cooperative drug dispenser will be built upon micro-architectures already explored by SXT (TRL5) integrated with micro electro-mechanical devices. We expect to bring this component at TRL8 by the end.

Meaningful interaction with Giraff and the other components. Tight collaboration between psychologists, HRI experts and ICT researchers will allow building meaningful and attractive interfacing modalities and interfacing. We will start from UOP and PCL competences (WP4) and shape Robohome2.0 throughout the development to promote compliance with the elder and provide HRI and GUIs at TRL7. In particular, we will explore an ecological approach for both the autonomous navigation of the Giraff and its approach to the elder, starting from the work of UMA (TRL4). We expect to arrive at TRL7 at the end. Lastly, an innovative distribute voice command system will be realized to provide a natural interface between the elder and the robot, starting from the experience of SG in signal processing (TRL4). We expect to arrive at TRL7 at the end.

## 1.3.3 Relationship with National and International Research and Innovation activities

The theme of elder assistance and aging well has been addressed by several research projects both under FP7 and AAL frameworks aimed at improving the quality of life of elder people, some targeting also disabled people.

The idea of having a robot that interact with an assistive environment has been explored in the Companionable project (http://www.companionable.net), where a mobile robotic companion interacts with a smart home sensorized environment with the aim of monitoring the elder against cognitive decline and stimulating cognitively him. Moreover, it can detect adverse events like falls. The Robo M.D. project (http://www.innovation4welfare.eu/307/subprojects/robo-m-d.html) was aimed specifically to detect critical situations like falling and launch an alarm. These concepts have been further developed in the Excite (http://www.aal-europe.eu/projects/excite/) and Giraff plus projects (http://www.giraffplus.eu/), coordinated by ORU. In Giraff plus a wide range of environment and activities signals are used to monitor the elder and to provides a pictorial representation of his/her activities that can be used to assess her/his lifestyle. Monitoring is complemented with a robot that provides video-communication with his caregivers. The Robot Era project (http:// www.robot-era.eu/robotera/), provides a complementary view providing a set of robots that assist the elder in specific functionalities of every day life like moving objects [UOP and ORU may comment on this]. On the other end, a few projects have explored the use of low-cost technology for support elder at home. The project Mobiserv (http://www.mobiserv.info/results/) will deliver a robotic prototype of an open standard-based personal platform capable of sensing the user’s personal environment and adapting to the user’s patterns of behaviour.The Oldes project (http://www.oldes.eu/home.html) is aimed to offer stimulation and remote overview to improve the quality of life of elder people, through a care platform designed to ease their life in their homes. More recently the Wecare AAL project (http://www.wecare-project.eu/) explores the social aspects in building a community to support the elders to live alone.

Several projects have been based on developing wearable devices to monitor elders at home. The Rosetta project (http://www.aal-europe.eu/projects/rosetta/) was aimed to monitor activities of elderly persons with sensors to generate alarm when unexpected activity, like a fall, is detected and support the elderly in carrying out daily and recreational activities. Monitoring of Parkinson people is carried out similarly in the Cupid project (http://www.cupid-project.eu/) that completes monitoring with specific rehabilitation exercises. Happy Aging (http://www.aal-europe.eu/projects/happy-ageing/) is a system for lifestyle monitoring, for issuing reminders and detection lack of activity or unusual behaviors. Hope (http://www.hope-project.eu) is targeted to Alzheimer patients and can provide alarms and communication with health professionals. It connects several house sensors and gives reminders and warnings via voice. eCaalyx (http//www.ecaalyx.org) integrates physiological sensors to monitor the elder at home that are worn and whose controlled is housed in a pocket of a t-shirt. The aim of the Interaction project (http://cms.interaction4stroke.eu/drupal/) is to develop a system based on e-textile and sensors to monitor motion and force exchange between a subject and the environment and to profile his activity. Using a similar approach, the Psyche project (http://www.psyche-project.org/) has developed a monitoring system based on e-textile and portable sensing devices for the long and short term acquisition of data from screened, patients, typically affected by mood disorders to manage psychiatric illnesses. However, the need to wear sensors limits strongly the usability of these systems that are still bounded mainly inside the research domain [PCL comment on this]. All these projects improve the elder life in some of its aspects; however they come short in providing a complete support to the elder in terms of monitoring and assistance, as well as providing connection with his/her caregivers.

A different approach was followed in the Fitrehab (http://www.innovation4welfare.eu/287/fitrehab.html) and Rewire projects (http://www.rewire-project.eu), coordinated by UMIL, in which a hierarchical architecture has been developed to support rehabilitation at home. Rewire, in particular, has shown that assembling off-the-self components, patients discharged by the hospital, are enabled to continue exercising intensively at home, still under supervision by the clinicians. Monitoring the performance, adapting the exer-games at point of needs and motivational feed-back to the user and informative feed-back to his/her supervisors are deems to be a winning strategy. Robohome2.0 builds on this concept and extends it to support the elder at home.

Besides research projects, a few companies have approached assisted living market through robotics. Kompai, developed by Robosoft (http://www.robosoft.com/robotic-solutions/healthcare/kompai/index.html ) inside the Domeo project (http://www.aal-domeo.eu/) is a companion robot, meant as an open robotics architecture with, presently, limited capabilities. Giraff robot, developed over the years by GIRAFF (P3) (http://www.giraff.org/) is a robotics platform aimed at containing the costs on one side, and on the other side it has been developed with particular attention to a good interfacing with the elder and it has been selected as the most suitable service robot for Robohome2.0.

The other pillar of Robohome2.0 is the introduction of gamification. Games, or better exer-games that mix exercising and gaming, have been widely explored in EU projects mainly targeted to rehabilitation as a good way to stimulate, motivate and guide patients through exercises. In the Script project (http://www.scriptproject.eu/), games are combined with small robots and are aimed at guiding patients in the rehabilitation of wrist and hand functions. Also should be mentioned the project H_Cad, which was aimed to rehabilitate cognitive dysfunctions was carried out through tasks used in occupational therapy inside a controlled environment. In the EU project Backhome, how to provide cognitive rehabilitation tasks to people with severe disabilities is investigated. Currently, three categories of cognitive games have been taken into account: perception; attention and concentration; and memory. It is beyond the scope of BackHome to develop, validate, and illustrate clinical outcomes, however the intention is to validate the efficacy and stability of the proposed solution within a future evaluation. Cupid is aimed to Parkinson patients and specific exer-games have been developed which provide audio, visual and tactile feedback. The RGS system is aimed at upper arm and develops a game aimed at guiding the arm in 3D space. However, few of these projects go beyond basic graphics and gameplay resulting into exer-games of little attraction as they lack addressing good game design guidelines. Moreover, they have limited configuration capability and adaptation as well as monitoring is not provided. Moreover, the repetitive nature of their game mechanics make them not fit for prolonged exercising. The IGER (Intelligent Game Engine for Rehabilitation) game engine, developed inside the Rewire project (htttp://www.rewire-project.eu), is an exception. This is a game engine: a set of tools that are aimed, on one side at making the games run on the machine they are designed for, on the other end, help the developer in creating games that share the same features. Therefore, IGER has allowed a fast prototyping of new games, reusing the gaming functionalities that been developed for previous games. In particular, it contains the functionalities required to configure and adapt the exer-games to the user and to supervise him while exercising at home, to make exercising at home feasible and robust, on one end and, IGER offers therefore a good starting point to Robohome.

## 1.3.4 Overall approach and methodology

TO BE CONTINUED FROM HERE

The areas of research required to develop Robohome2.0 can be grouped into four main areas: monitoring subsystems, clinical evaluation, activity promotion, assistance robotics and virtual communities. We will here analyze the research and development required inside each area.

### Clinical Evaluation

Clinical monitoring is fundamental to trust the elder to stay home for a prolonged period of time also when facing with objective frailty. To this aim Robohome2.0 will carefully address monitoring specifications and come up with a set of defined functions that will address frailty and critical elements for most elders.

Clinical monitoring of physical and cognitive frailties will be performed with two main modalities. In the first modality, identified common assessment test will be carried out at-home with the help of Robohome2.0 platform. Smart Giraff navigation system allows to carry out the tests in the most comfortable situation of the elder. In the second modality, these tests will be carried out transparently from the data collected by the activity center and the monitoring systems in a transparent way.

Interactive version of these already validated tests will be designed and administered. Giraff will remind the user not only when he/she has to perform a test but it will also guide him/her step by step during test execution through explicative video animations and providing also the ICT support to complete them. The Virtual Caregiver will compare the assessment result with the initial value and provide a time course picture of assessment. To this aim, congruent evaluation scales have to be developed and validated. When score drops below a given threshold an alarm will be sent to the reference GP and to the caregivers. Alternatively, taking advantage of video-communication support provided by Giraff the tests can be tele-monitored by the GP.

In the second modality, A novel approach to clinical monitoring will be to implemented through  pervasive clinical tests. The pervasive cognitive and physical tests will be scored daily and weekly and then after a proper data analysis it will be possible to extract important informations about the user condition and its changes over time, thus providing continuous clinical evaluation of the elder.

The most used cognitive and physical tests that can be easily performed by the elder himself/herself at home will be identified

Giannakouris k., Aging characterizes the demographic perspective in the European Societies, Eurostat, Statistics in focus, 2008, 72. http://eppeurostat.ec.europa.eu

P. Buerhaus, BCurrent and future state of the US nursing workforce, J. Amer. Med. Assoc., vol. 300, no. 20, pp. 2422–2424, 2008. Nursing Shortage Fact Sheet, American Association of Colleges of Nursing, 2010. Online at http://www.aacn.nche.edu/media/FactSheets/NursingShortage.htm...

http://www.giraff.org/

T.Bickmore, R.Picard, Establishing and maintaining long-term human-computer relationships, ACM Trans. CHI, Volume 12:2, 2005, pp 293 – 327.

Fayzullin et al., 2007

Cattinelli et al.

V. Propp, Morphology of the Folktale: Revised and Edited with Preface by L.A. Wagner, Introduction by A. Dundes (Vol. 9), University of Texas Press, 2010.

E. Baum, D. Jarjoura, A. E. Polen, D. Faur, and G. Rutecki, BEffectiveness of a group exercise program in a long-term care facility: A randomized pilot trial. J. Amer. Med. Directors Assoc., vol. 4, pp. 74–80, 2003.

D. Dawe and R. Moore-Orr, BLow-intensity, range-of-motion exercise: Invaluable nursing care for elderly patients, J. Adv. Nursing, 21, pp. 675–681, 1995.

M. D. McMurdo and L. M. Rennie, BA controlled trial of exercise by residents of old people’s homes, Age and Ageing, vol. 22, pp. 11–15, 1993.

V. Thomas and P. Hageman, B Can neuromuscular strength and function in people with dementia be rehabilitated using resistance-exercise training? Results from a preliminary intervention study, J. Gerontol. A, Biol. Sci. Med. Sci., vol. 58, pp. M746–M751, 2003.

S. Colcombe and A. Kramer, BFitness effects on the cognitive function of older adults, Psychol. Sci., vol. 14, pp. 125–130, 2003.

S. J. Colcombe, A. F. Kramer, K. I. Erickson, P. Scalf, E. McAuley, N. J. Cohen, A. Webb, G. J. Jerome, D. X. Marquez, and S. Elavsky, BCardiovascular fitness, cortical plasticity,and aging,[ in Proc. Nat. Acad. Sci. USA, 2004, vol. 101, pp. 3316–3321.

W. Spirduso and P. Clifford, BReplicationof age and physical activity effects on reaction and movement tim time, J. Gerontol., vol. 33, pp. 26–30, 1978.

Z. B. Moak and A. Agrawal, BThe association between perceived interpersonal social support and physical and mental health: Results from the national epidemiological survey on alcohol and related conditions, J. Public Health, vol. 32, pp. 191–201, 2010.

L. K. George, D. G. Blazer, D. C. Hughes, and N. Fowler, BSocial support and the outcome of major depression,[ British J. Psychiatry, vol. 154:  478–485, 1989.

E. Paykel, BLife events, social support and depression,[ Acta Psychiatrica Scandinavica, vol. 89, pp. 50–58, 1994.

B. Prospective relations between social support and depression: Differential direction of effects for parent and peer support? J. Abnormal Psychol., vol. 113, pp. 155–159, 2004.

S. A. Stansfeld, G. S. Rael, J. Head,M. Shipley, and M. Marmot, B Social support and psychiatric sickness absence: A prospective study of British civil servants, Psychol. Med., vol. 27, pp. 35–48, 1997.

1.Nathan DG. Careers in translational clinical research - Historical perspectives, future challenges. JAMA 2002;287(18):2424-7.

http://www.signomotus.it/h_cad_site/h_cad_accessible/system_description.htm

http://www.backhome-fp7.eu/content/project

http://www.cupid-project.eu/

http://rgs-project.upf.edu

M. Pirovano, R. Mainetti, G. Baud-Bovy, P.L. Lanzi, N.A. Borghese, IGER – Intelligent Game Engine for Rehabilitation, IEEE Trans. CIAIG, submitted. Short version in Proc. CIG 2012.

.A. Borghese, P.L. Lanzi, R. Mainetti, M. Pirovano, Apparatus and method for rehabilitation employing a game engine,

US Application number: 13/911577, 6th June 2013