# 3. Implementation

# 3.1 Work plan — Work packages, deliverables and milestones

## 3.1.1 Overall strategy and general description

The Robohome2.0 project will build on 10 work packages. WP9 and WP10 will cover transverse activities, namely: Dissemination and Exploitation and Management activities, while the other work packages will be devoted to the design, the development, the integration and the evaluation of the complete Rohome2.0 System.

WP1, Functional Specifications: will be carried on the basis of the needs and requirements of end-users: clinicians (SAS, PCL), caregivers (represented by KORIAN and MUNICIP) and elders (represented by PCL, SAS and MUNICIP). The Roohome2.0 platform will be designed to support the elder at home and to allow the caregivers and clinicians a reliable supervision of the elder at home. To this aim, a clear picture of the functionalities required for monitoring (the elder lifestyle, his/her psycho-physical status and the environment), for assistance in every day life tasks, for activities and for evaluation will be drawn and documented in D1.3. Modality for functional evaluation through the pilot (WP8) will also be defined, with case use scenarios, taking into account the functionalities required (Task 1.6). Ethical submission documentation will also be prepared (Task 1.7).

WP2, Implementation requirements: will be carried out in pipeline with WP1 with the aim of defining the technical specifications of the system and of its components. The most suitable devices and components will be identified. Given the large number of components envisioned, particular attention is put on modularity and interoperability: diffused standards, both hardware and software, will be used. The modalities of evaluating the different components and the whole system will be set as well as the requirements in terms of availability, dependability, accuracy and latency (Task 2.6).

WP3, Virtual caregiver and service robot: will focus on the technology required to further develop Giraff to meet functional requirements set in WP1 and service specifications set in WP2. Particular attention will be made on energy optimization and autonomous ecological navigation. The virtual caregiver that controls the entire system and provide assistance and evaluation of to the elder status, through state-of-the art AI functionalities, will be also developed. Data from activity center and monitorings will be used to tune the robot behavior. Functionalities that assist the elder in everyday tasks will be also designed and implemented (Task 3.8, Task 3.9).

WP4, Activity center: The activity center will provide most activities under the form of adequate exer-games built inside the gamification framework. It will extend the capabilities of the IGER game engine developed by UMIL, that already provides full configuration, adaptation, monitoring and feed-back though avatar, to support multi-player exercising to promote socialization. Motivation will be designed and implemented as a gluing elements of all the mini exer-games developed and games themselved will be designed to maximize compliance of the elder (Task 4.3). Massive use of stochastic of assets will be used to promote games variability and increase motivation. The engine will also be extended to produce educational exer-games that can be adapted to specific elder’s needs and idiosyncrasies combined stochastic elements, like stochastic finite state machines and controlled randomization, and ontology based automatic narration (Task 4.4). Gaming results will be made available to the community to increase socialization (Task 6.3) and interaction data will be made available to the Virtual Caregiver for evaluation, assessment and tuning (Task 3.3, Task 3.6).

WP5, Monitoring systems: it will design and implement the networks that monitor the environment data and collect physiological measurements. It will also design, realize and implement the transparent physical monitoring system. The aim is to get all the information on the patient’s physiological vital signs, the psycho-physical status, the environment data and meaningful information related to lifestyle that are required to identify the clinical, psycho-physiological status and habitudes of the elder along with the data provided by WP4.

WP6, Community of users: it will cope with the design and realization of a dynamic community in which the elders can find a suitable group of pairs with whom to interact. The motivation and adherence issues related to usage of community by elders will be addressed during its design. The community will also allow the GP to view the physiological data and trend and to the caregivers have a summary of the lifestyle of the elder. This may become a new channel of communication between elders and their caregivers. It will also feed the virtual caregiver with data required to initialize and tune monitoring and activities as well as to tune the robot behavior. Lastly it will work as a portal of knowledge for the supported elders.

WP7, System integration: it will take care of the final integration of all the components identified above. To achieve most effective integration early testing of the components will be carried out from the technical and functional point of view. UMIL will set-up progressively a Robohome2.0, integrating and testing the components developed in increasing stages in WP3,WP4, WP5, WP6, under the guidance of GIRAFF. An early development of components developed in WP3, WP4 and WP5 in living labs in ORU and SAS will allow derive feed-back and suggestions to improve them. This will allow testing the system in real conditions and to tune its tuning the different components according to the feedback collected from patients, family members, physicians and elders themselves. Early testing will start at M13 and D7.1, refined functional and technical specifications, due at M24, will provide the final view of the specifications of Robohome2.0. This task will end with D7.2 – Report on technical and functional tests of the Robohom2.0 system.

WP8, Robohome2.0 pilot: It will allow the testing of the system in real conditions and tuning it according to the feedback collected from elders, caregivers, family members, physicians and therapists. This WP will allows us to come with quantitative comprehensive evaluation of Robohome2.0 and the new modality of assistance offered by it. Functional and behavioral analysis will be a fundamental part of this evaluation.

WP9, Dissemination and exploitation: Conventional channels, like exhibitions, meeting, as well as non-conventional ones, like LinkedIn, YouTube, Facebook, will be exploited to diffuse the project results. Most effort will go towards private and public structures that offer support to elders.

WP10, Management: will provide all the support to the project, through a structure that will promote a shared view of the project and minimize risks. A strong emphasis will be devoted to ethical issues, through a dedicated ethical review board and to IPR management through a direct involvement of UMIL technology transfer office in the evaluation of project’s results.

## Timing of work packages and their components (GANNT Chart)

## Detailed work description

#### WP1 – Functional specifications

| Work package number | 1 |  |  |  | Start date or starting event: |  |  |  |  |  |  | M1 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Work package title | Functional Specifications |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Participant number | 1 | 2 | 3 | 4 |  | 5 | 6 | 7 | 8 | 9 | 10 |  | 11 | 12 | 13 |
| Participant short name | UMIL | ORU | GIRAFF | UOP |  | SXT | PCL | POLIMI | BDIGITAL | SAS | KORIAN |  | SG | UMA | MUNIC |
| Person-months per Participant | 2 | 2 | 1 | 3 |  | 0 | 9 | 5 | 1 | 9 | 9 |  | 1 | 2 | 3 |

Objectives: - To identify users and use cases of the Robohome2.0 system. - To define all the functionalities required to Robohome2.0 and define user-case scenarios. - Prepare the ethical submission document.

Partners role: PCL leads this WP. It has a very large clinical experience with the elderly and has strong tights with social services. It is a multi-disciplinary geriatric team with also psychological and physiotherapeutic competences. Other main actors in this WP will be SAS and MUNICIP. KORIAN will provide the view of a service provider that has a clear idea on the functionalities required to support elder at home reliably. UMIL will bring the feedback matured in designing virtual games for rehabilitation and in particular related to Duckneglect and IGER and will foster interfacing between clinical and technological teams. In BDIGITAL will be heavily involved in setting up the functional specifications of the community of users and the interfaces towards the clinicians and the elders maximizing its usability with the help of UOP. POLIMI will provide the technological background to help define the monitoring functionalities. UMA and OREBRO will provide the framework inside which Giraff functionalities can be extended. Description of work. The major effort of Robohome2.0 in the first few months will be to clarify the scope and implications of the project to drive the development in the most effective direction. A bi-directional translational research approach will be pursued, facilitating the communication between the teams, which carry the instances of the users, and the technical teams, which portray the possibilities offered by technology. Final aim is to come up with a shared view on Robohome2.0 platform.To this aim we will start from the elder’s and other Robohome2.0 users’ needs to move towards functional specifications to implementation specifications addressed by WP2 and then to implementation carried out in WP3, WP4, WP5, WP6, integration in WP7 and testing in WP8. Implementation specifications may eventually lead to adjustment of functional specifications (PERT diagram). These methodologies will lead to the definition of the user requirements, and of the design of the metrics to evaluate the user experience and acceptance of the robot. User specifications and functional requirements will be written in a comprehensive technical report (D1.1), publicly available, that lays the ground for the future development of the Robohome2.0 system modules. To achieve effectively WP2 goals, three approaches will be followed. The first approach is bottom-up and it is based on soliciting the end users expectations by means of a continuous feedback through questionnaires, interviews and focus groups according to the different needs and organization in the different pilot sites. This approach will be implemented looking directly at the users expectations through questionairs, created specifically for each group of users, starting from the functionalities identified in the DoW, trying to collect different views of the same functionality to come up with a complete description. The second approach is top-down, and it is based on identifying functionalities and their operation modality through UML language or conceptual maps. The resulting schemes will be used to elicit further feed-back from the end-users. The data gathered from these two approaches will be integrated into a coherent and complete set of functions. In parallel, several meeting will be organized to promote bidirectional research in the first months of the project. During these meetings, the technology on which the project is based will be shown live and discussed along with videos and mock-ups of the components of Robohome2.0. Caregivers, on their site, will illustrate some of the features and possibilities currently offered by the social services to support elders at home in the different countries, stressing the weaknesses and strengths of the current system. A set of multiple applicability scenarios, spanning from the old independent adult to the chronic disabled person living at home will be defined. A cohort of 20 end-users, care-givers and physicians, will be involved both in the definition of the requirements of the system and in testing the system. An extended evaluation will be set for each scenario within a within a living lab made available by MUNICIP; the evaluation will include the acceptability by the users and their caregivers and, when applicable, also the evaluation by other actors, such as the family doctor, the physiotherapist, etc. Refinement of the functional specifications is obtained from the definition of the implementation requirement and from the early stages of the development of the components. Task 1.1(M1-M4) Identification and characterization of Robohome2.0 users (PCL, KORIA, SAS, MUNICIP, UMIL) Possible Robohome2.0 group of users will be identified. These are 1) the elderly, 2) people with a technological role like managing the community and providing SW/HW support 3) people with a functional role: clinicians, care-givers, relatives and so forth. For each of these categories a clear role for Robohome2.0 will be identified and their possible functions identified. Accordingly the relationship between them is outlined. Unified Modeling Language (UML) and conceptual maps can be used for instance to clarify such processes and roles. Robohome2.0 target are elderly subjects who are at risk of frailty, cognitive impairment, dependence and social exclusion. Frailty syndrome is defined as a state of excessive vulnerability to environmental factors accompanied by a progressive decrease in the functionality of many organs and body systems. Beyond this classical phenotype definition, the term frailty is operatively used in geriatric medicine to identify older adults who are at increased risk for future poor clinical outcomes, such as development of disability, dementia, falls, hospitalisation, institutionalisation or increased mortality. According to the Cardiovascular Health Study (CHS) index definition, an individual is classified as frail if he/she meets three or more of the following five criteria: • Weight loss (>5% in last year) • Exhaustion • Weakness (decreased grip strength) • Slow walking speed (>6 to 7 seconds for 15 feet) • Decreased physical activity (males <383 kilocalories); females <270 kilocalories) When one or two of these characteristics are met a condition of pre-frailty exists. Otherwise, the person is classified as robust. According to this, possible eligibility criteria for the ROBOHOME2.0 project can be: - pre-frail subjects - with more than 65 years - without a cognitive impairment at baseline (Mini Mental State Examination score ≥ 24) - living at home. Possible case scenarios are: - subject meeting the eligible criteria living at home with a non-married son who works for 8 hours a day - subject meeting the eligible criteria, still mostly autonomous, living alone (no close relatives), affected by multiple morbidities, at high cardiovascular risk (e.g. diabetes mellitus, hypertension, hypercholesterolemia, atrial fibrillation) but without a previous major event - subject meeting the eligible criteria, living at home with a sitter, with relatives living in a different house in the same city, with a previous stroke with mild residuals (mild strength reduction of left limbs, walking with a cane walking stick to feel safer) Inclusion and exclusion criteria will be clearly defined for the pilot (WP8) on the basis of physical and mental conditions, their availability and willingness to be involved and, finally, of their living environment. In particular, compliance with technology has to be appreciated. Particular issues to be assessed are: lower limbs motor function ability, upper limbs motor function ability, mental function capabilities, willingness and availability to use the system, availability of caregivers and families. The selection of the end users will be based on the same procedures already experimented in Giraff+ and Rewire projects. Elders will be chosen tentatively according to the following steps: 1. Pre-selection of users and first contacts with elder associations and GPs. 2. Identification of 20-30 potential end users of Robohome2.0 at home 3. First personal interviews in order to establish their availability and willingness to participate in the project. A plan (including insurance cover) for emergency situations that might occur during the pilot study will be designed. This last effort will be carried out in collaboration with the Ethical Review Board of the project. Assessment measures will be identified. Assessment will be carried out before and after Robohome2.0 period of use. Primary outcome is the evaluation of the fraility condition. According to the principles of a Comprehensive Geriatric Assessment, the following specific outcomes will be measured at baseline and at the end of the pilot study: Measures of physical performance that can be Tinetti scale, Short Physical Performance Battery (SPPB), 4-m walking speed, balance and chair-stand tests; muscle strength (hand-grip strength); functional (ADL and IADL); cognitive status (MMSE); mood (Geriatric Depression Scale); nutritional status; quality of life ; satisfaction; frequency of access to Emergency Department/hospitalization/institutionalization; adherence to therapy; quality of life and satisfaction of the caregiver. Additional specific outcomes might be added according to the phenotype of the elder, the specific tasks required by the elder to the Robohome2.0 (for example, HbA1c for a diabetic elder; number of daily naps and so forth). Measures of physical performance that can be Tinetti scale, Short Physical Performance Battery (SPPB), 4-m walking speed, balance and chair-stand tests; muscle strength (hand-grip strength); functional (ADL and IADL); cognitive status (MMSE); mood (Geriatric Depression Scale); nutritional status; quality of life ; satisfaction; frequency of access to Emergency Department/hospitalization/institutionalization; adherence to therapy; quality of life and satisfaction of the caregiver. Additional specific outcomes might be added according to the phenotype of the elder, the specific tasks required by the elder to the Robohome2.0 (for example, HbA1c for a diabetic elder; number of daily naps and so forth). Task 1.2(M1-M12) Identification of the Robohome2.0 activities and assistance functions (SAS, KORIAN, PCL, MUNICIP, UMIL, POLIMI) A proper set of activities that counteract social, physical and social decline will be defined, at least four activities for each domain. Some activities will be based on facilitating the interactions with other elders, like playing cards or doing exercising watching the self mirrored inside the Giraff or TV monitor. Other activities will be implemented through exer-games. The latter will be designed to maximize compliance with the goal set. Functionalities required will be defined with particular attention to compliance: scenarios, interaction modalities, feedback provided during gaming will be identified to facilitate a relationship between the elder and Giraff and make gaming most effective. Particular care will be made in defining the most effective functionalities for supervision. As far as physical activity is concerned, a wide range of exercises can be proposed to improve selectively control, coordination or strength. Exercises that are most important to keep a healthy lifestyle will be selected according to current geriatric practice. A similar approach will be followed for the cognitive training, for which the most suitable activities will be selected. Depending of the type, each physical and cognitive activity scenario should include information among the following: • A set of possible virtual environment that can be suitable for the largest elder population to contain all the exer-games developed for exercising and tutoring. • A set of possible exercises required. • The parameters that determine their difficulty and some possible adaptation mechanisms inside the exercises (e.g. amplitude, accuracy or speed of the movement). • The parameters to monitor and evaluate the elder’s performance quality in terms of intensity, time and of correctness • The modality of the activity: personal or within a group. • The possible constraints on the design associated to elder characteristics, for instance elements size and contrast; avatar anthropometic measurements. Particular care will be put in the definition of a proper cognitive load of the exer-games scenario and the gameplay, associated to the different groups of elders identified such that each exer-game will automatically adapt to the actual user. • Explicit definition of all the elements that can concur to motivation. An effective and balanced reward system will be defined as well as several possible ways of defining levels of difficulty of the exercises in front of the elder residual capabilities. • Exercises that can be carried out through the everyday activities will also be identified and monitoring of these activities will be implemented in WP5 to derive a feed-back on their quality and intensity. • The need of additional feed-backs, besides the visual one, will be investigated and possiblye additional components required to implement additional cues and reward mechanisms (e.g. loud speakers) will be defined. Assistance functions will also be identified and a set of key objects that Giraff has to locate automatically will be identified. Real-case senarios will be designed that have to be solved in Task 3.8. An important feature of the Robohome2.0 system will be also the integration of some services to facilitate and promote independent living. Some examples are: an intelligent and novel system to manage the location of specific objects in the house; a novel cooperative system based on a smart drawer to assure the prescription adherence of the user. Groups of possible diets will be also identified in this task. Functional specifications of these services will be identified along with real case scenarios that will be used for testing. Task 1.3(M1-M12) Identification of clinical monitoring, transparent monitoring and environment monitoring functionalities (PCL, SAS, KORIAN, MUNICIP, BDIGITAL, POLIMI, UNIMI) Aims of clinical monitoring will be clearly identified and use case defined and reported in D1.3. Possible implementation modalities will also be described having in mind the whole spectrum of aspects to be monitored: A. Monitoring Cognitive and physical performance through exer-gaming provided by the activity center. The activities offered by Robohome2.0 and defined in Task 1.2 allow to collect data that are useful for monitoring the elder. These can be for instance the time required to complete a “memory” game or a puzzle or a physical exer-game, the score, the average number of points lost in card games, and so forth. B. Monitoring physical activities by means of instrumented objects. Movement stability will be monitored by means of sensors mounted inside objects typically used by the elder so that the monitoring will be transparent to him. A few objects that can be of use for a wide variety of elder population will be defined in this task. These objects will be used both during the physical exercises performed by the user within the activity game center (WP4) and during specific clinical tests (WP3). They will also be used during everyday life, like for instance the supporting walking stick, thus garthering information both indoor and outdoor. C. Monitoring the elder lifestyle through environment sensors- The Robohome2.0 system will monitor and store data about the main activities carried out by the user during the day such us the number of hours of sleep, regularity of meals and drinks, number of times the user goes to the toilet. All these data will be helpful to monitor the user habits and behaviors and to understand how and how much his/her condition is changing over time. D. Monitoring social interaction. Monitoring functions of social aspects will also been defined with the idea to come with a rough picture of the elder isolation that can be linked to depression or disorders mood. Such picture will be made at the beginning, with the help of interviews with relatives and caregivers and deviation from the usual social profile will be monitored. The social monitoring will be carried out mainly through a simple week dairy that the caregiver can compile on-line on the portal of the community of Robohome2.0 (Task 1.4). Additional simple information can be derived from profiling the telephone calls and the analysis of the pitch, volume and speed of the calls. Finally, the monitoring of the multi-player activities and games can enrich the social monitoring (see WP2 and WP4). E. Monitoring Health Conditions. Another important user requirements will be to monitor specific parameters to assess the health condition such as blood pressure, heart rate or, in case of patients with diabetes mellitus or pre-diabetes conditions, the glucose concentration. Conditions that have to trigger an alert to the elder GP will be defined, on the basis of the parameters measured and the elder clinical profile (Task 1.6). Task 1.4(M1-M12) Identification of the community of users functions (KORIAN, SAS, PCL, MUNICIP, BDIGITAL, UMIL) Within this task the functions to be supplied by the Robohome2.0 Virtual Community will be identified. Taking into account the possible actors who will be participating in the usage of the Robohome2.0 platform, the user requirements will be defined. A role will be defined for each type of user and each role will have its own assigned permissions and specific functions. In particular, the relationship between the caregivers, the clinicians, the elders and the other possible users of ROBOHOME2.0 platform will be identified. Functions required to provide virtual interaction between community members, as also to run and review personalized activities adapted to the elder status will be identified with a tight cooperation between technological and clinical partners. Task 1.5(M1-M12) Identification of the functions of the virtual caregiver and of the service robot (PCL, KORIAN, SAS, MUNICIP, POLIMI, OUR, GIRAFF, UMA, UOP) The caregiver will supervise and monitor the elder lifestyle and advise her/him. Therefore, the following functionalities have to be defined: • Modality of prescription of the activities. The involvement of all Robohom2.0 users, including the elder, in the definition of lifestyle goals, the definition of a-priori information on elder idiosyncrasies, and an effective feed-back to the elder to increase her/his intrinsic motivation are already a routine in nursing homes where elders can be recovered. One of the goals of Robohome2.0 is to move this holistic integral approach to the elder living at home, for which the continuous presence of specialized operators that enforce the program cannot be guaranteed. Such role can be partially taken up by the community of users but a clear definition of functionalities is required. - Association of the mix of activities to the elder profiling carried out in Task 1.1. - Functionalities required by the clinical tests defined in Task 1.4 (e.g. approaching of Giraff to the elder). - Alarm for health conditions and major hazard detected by transparent monitors (e.g. large problems with memory or hazard in equilibrium) or through physiological samples (e.g. physiological parameters increased (or decreased) significantly over (under) the reference value), combined with the elder profile, will active a warning system to the GP and to the elder’s caregiver. - Robot capabilities required. - Interaction of the robot with the elder: modality of approach, voice feed-back, interaction modalities. Task 1.6(M7-M12) System functional evaluation (PCL, KORIAN, SAS, PCL, MUNICIP, UNIMI, UOP) Given the expected interplay between the elder and the robot, and given that the type of assistance provided is multi-dimensional, the evaluation task will be complex and based on a series of indexes. Overall, the system activity will be evaluated using measures for three comprehensive aspects: 1) measures for elder’s compliance with the intervention; 2) measures for elder’s satisfaction with the intervention; 3) customized measures for the achievement of the cognitive, physical, social and clinical objectives set at the beginning of the intervention. Measures for elder’s compliance with the system will be the frequency of use of the system and the rate of completion of the activities proposed. The elder’s satisfaction will be evaluated using TAM questionnaires developed in the last years aimed to assess the impact of the technology, . TAM builds the prediction of individual adoption and use of a technology on two main beliefs that affect the behavioral intention of the individuals: (i) the perceived usefulness, defined as “the extent to which a person believes that using a technology will enhance his or her job performance”; and (ii) the perceived ease of use, defined as “the degree to which a person believes that using a technology will be free of effort”. The questionnaire will be administered before the beginning of the intervention to all actors, including family/non-family caregivers involved in the intervention. Then the perceived usefulness and ease of use will be evaluated again at the end of the planned period of usage. Finally, since the typologies of intervention, among the range of potential activities that Robohome2.0 can perform, will be customized according to the characteristics and the needs of each elder, users will be asked to define their own metrics and modalities to evaluate the overall effectiveness of the intervention, which might involve the cognitive, physical, social and clinical sphere. For clinical assessment we will use well established clinical measures and the clinical measures defined for transparent monitoring in Task 1.3. Use of the Barthel index and modified Rankin scale will be also considered as well as the Functional Independent Measure (FIM) index. Assessments will be collected before and after Robohome2.0 usage and will be useable for designing a later randomized controlled trial that will compare Robohome2.0 technology with standard assistance provided by socio-health services. Such indexes will be used in Task 8.4 for assessment. Task 1.7(M7-M12) Ethical submission (PCL, KORIAN, SAS, MUNICIP, All partners) Being volunteers and patients involved in the intervention, the proposal will be submitted for approval to the competent Ethics Review Board. Together with the Ethics Review Board a consent form for participants will be elaborated. It will have at least the following fundamental components: it will be describe all the information concerning the characteristics of the intervention, including the possible expected risks; it will protect data confidentiality; it will guarantee subject’s freedom to refuse to participate to or to withdraw from the study at any time without affecting the preceding management plan. The consent to participate will be sought from the elder, but also from other possible users involved in the intervention (e.g. family/non-family caregivers). Task 1.8(M13-M18) Refinement of functional specifications (UMIL, PCL, SAS, MUNICIP, POLIMI, ORU, UOP, BDIGITAL) The specifications set in D1.1 will be reanalysed taking into account the constraints posed by technical offer and early implementation. The solution has still to match the users requirement although it might be implemented differently with respect to what envisaged in D1.1. For instance, a given physiological measurements turns out not to be reliable with available technology and the presence of a nurse or of a caregiver is required. The final specifications will be collected inside a public deliverable that pretends to offer the state of the art in assisted robots in smar environments.

Deliverables: D1.1 [R, CO] Preliminary functional specifications (PCL, M12). Elders inclusion / exclusion criteria will be defined. Required functionalities for monitorings: environment, psyho-physical, social and lifestyle, assistance both in everyday tasks and in therapy adherence, activity center and evaluation will be defined. Specifications of clinical tests will also be provided. All specifications will be supported by use-case scenario design. D1.2 [R, CO] Documentation for ethical commission submission (PCL, M12) D1.3 [R, PU] Final functional specifications. The functional specifications in D1.1 will be refined according to the definition of the implementation requirements in WP2 and to early testing in WP8. The final functional specifications represent therefore a complete document of the functionalities of a service robotic platform that can support the elder at home and will be fully exploited in WP9, as a scientific publication and as a publication targeted to policy makers (UMIL, M18).

#### WP2 – Implementation requirements

| Work package number | 1 |  |  |  | Start date or starting event: |  |  |  |  |  |  | M2 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Work package title | Implementation requirements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Participant number | 1 | 2 | 3 | 4 |  | 5 | 6 | 7 | 8 | 9 | 10 |  | 11 | 12 | 13 |
| Participant short name | UMIL | ORU | GIRAFF | UOP |  | SXT | PCL | POLIMI | BDIGITAL | SAS | KORIAN |  | SG | UMA | MUNIC |
| Person-months per Participant |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Objectives - Define the technical specifications of the Robohome2.0 platform and identify the most suitable components in terms of reliability, costs, availability. - To identify and design the main HRI interfacing modalities to maximize compliance and effectiveness. - To identify and design the main GUIs that will be displayed on the different displays used (Giraff monitor, TV monitor, smart phone of PC). - To design technical evaluation tests of the system components and of the whole platform.

Partners role: The implementation requirements are aimed at finding the best technology and implementation that matches the requirements in WP1. UOP for its experience in working with robots and users is the ideal candidate to lead this work. BDIGITAL will mainly contribute in defining the implementation specifications of the virtual community and of environment monitors, POLIMI for designing the assistance system, POLIMI with SXT and POLIMI in designing the psycho-physical transparent monitoring and the game center and UMA and GIRAFF on enhanced Giraff. Clinical partners, PCL, SAS, and KORIAN will provide the user point of view of the users. Description of work WP2 has the role of defining the technical specifications of the Robohome2.0 platform and of its components to comply with the functional specifications set in WP1. A strict coordination with activities in WP1 is needed and will be guaranteed by the PC. Analysis of technical specifications may start a further refinement of the functional specifications to obtain a system that matches the goals set: low-cost, reliability, dependability, usability will all be considered. The technical specifications of all the components will be identified: robot, activity center, assistance, community and the different monitoring systems (environment, physiological parameters and lifestyle), so that the functions identified in WP1 are made available. From the technological point of view, the development of an effective monitoring system relies on a good integration of available devices and applications with specifically developed ones. Thus, the available off-the-shelf devices and the best components that have to be assembled to produce reliable and accurate customized sensors will be selected. The modality of use and recharge of the customized sensors will all be considered in this task. The identified sensors should obey to one of the Robohome2.0 principles, namely they have not to be attached to the elder. We will identify a modular architecture suitable to be expanded already during the project. Given the fast pace of development of new sensors and physiological devices, Robohome2.0 will reserve the opportunity to integrate novel sensors that are made available in due course. Task 2.1(M2-M9) Identification of the technical functions for transparent cognitive-physical monitoring and assistance (SXT, POLIMI, UMIL, GIRAFF, ORU, UMA) The specification and identification of the components of the micro-architecture that will constitute the sensing module that provides pressure and motion of objects of everyday life will be identified to match specifications set in WP1. Recharging modalities and data transmission will also be specified. These data will be: pressure range and accuracy, acceleration range and accuracy, drift, non-linearity, and all the data that are required to characterize the obtained measurements. The specifications of the motion data that will be acquired syncrounously by Giraff through its 3D camera will also be defined in terms of number of joints, accuracy and sampling frequency and motion amplitude. Data storage dimension and bandwidth and delay in the transmission will also be identified. Similarly, the specification of the micro-architecture used to locate lost objects will be identified. Power required to obtain a reliable localization signal will be identified and a proper miniaturized design will be produced. A smart chest of drawers will be designed with the adequate number of drawers and adequate dimension. The control circuits will also be designed in this task. Task 2.2(M2-M9) Identification of the technical specifications of the environment and lifestyle monitoring (BDIGITAL, POLIMI, UMIL, GIRAFF, ORU) The specification and identification of the off-the-shelf components that have to be assembled to produce a reliable and accurate sensing embedded inside the environment, according to specifications set in WP1, will be carried out. Temperature, gas alerts, opening entrance door will be among the monitors of choice. Sofa and bed pressure mattress as well as mattress humidity are among the possible measurements taken on lifestyle. For each of these measurements range, frequency, accuracy will be defined. The most diffused networking systems, like z-wave, will be analyzed and reported in D2.1. Task 2.3(M2-M12) Identification of the technical specifications of enhanced Giraff and activity center (UMIL, ORU, GIRAFF, POLIMI, UOP, SG, UMA) The factors upon which the approaching path of Giraff can be defined are identified by UMA in collaboration with PCL and SAS, and a suitable parametric model whose shape is controlled by these parameters will be identified by SAS in collaboration with UMIL. The most suitable framework to implement the reasoning engine inside Giraff will be identified, taking into account its speed and scalability. The conditions required by the distributed voice control system will be defined in terms of microphones aperture, signal to noise ration and number of words that can be distinsuished. Languages differences will also be addressed. The solution based on local DSP processing, envisaged in Robohome2.0, will be compared with a centralized solution based on Microsoft APIs for voice recognition, made available since Windows 7 Operating System. As far the activity center is concerned, we will first defined the most suitable software platform, compatible with Windows OS mounted on Giraff. IGER system seems the most suitable as it provides a middleware suitable to use many different devices, the possibility create new exer-games and to extend easily the functionalities through Python script language to implement the motivational layers. Task 2.4(M2-M9) Identification of the technical specifications of the virtual community (BDIGITAL, POLIMI, UMIL, GIRAFF, ORU) The characteristics of the software and hardware elements that will constitute the Virtual Community will be defined in terms of workload, data storage and responsiveness. A high level architecture based on open source standards and accessible technologies will be designed. As the base of entire community technical structure it will be used the Integrated Continuous Care telemedicine platform (ICCPlatform) provided by BDIGITAL. A set of interconnection interfaces between different Virtual Community components will be defined. All technical requirements captured in this task will be used as input for the WP6 during the Virtual Community components development, deployment, testing and production tasks. Task 2.5(M3-M24) Design of the hierarchy of interfaces with Giraff, the activity center and the community (UOP, BDIGITAL, SAS, PCL, KORIAN, MUNIC, UMIL) A flexible graphic user interface (GUI) will be designed to allow the different type of users to interact effectively with Ronohome2.0. To achieve this, adaptive and configurable GUIs will be designed according to classical design rules set by Constantine and co-workers: 1. The structure principle. Your design should organize the user interface purposefully, in meaningful and useful ways based on clear, consistent models that are apparent and recognizable to users, putting related things together and separating unrelated things, differentiating dissimilar things and making similar things resemble one another. The structure principle is concerned with your overall user interface architecture. 2. The simplicity principle. Your design should make simple, common tasks simple to do, communicating clearly and simply in the user’s own language, and providing good shortcuts that are meaningfully related to longer procedures. 3. The visibility principle. Your design should keep all needed options and materials for a given task visible without distracting the user with extraneous or redundant information. Good designs do not overwhelm users with too many alternatives or confuse them with unneeded information. 4. The feedback principle. Your design should keep users informed of actions or interpretations, changes of state or condition, and errors or exceptions that are relevant and of interest to the user through clear, concise, and unambiguous language familiar to users. 5. The tolerance principle. Your design should be flexible and tolerant, reducing the cost of mistakes and misuse by allowing undoing and redoing, while also preventing errors wherever possible by tolerating varied inputs and sequences and by interpreting all reasonable actions reasonable. 6. The reuse principle. Your design should reuse internal and external components and behaviors, maintaining consistency with purpose rather than merely arbitrary consistency, thus reducing the need for users to rethink and remember. Particular care will be put in modularization and parameterization. We will keep particular attention to interface elements, like text font size and colour, sprites dimension and scene apparent size: they will be made adjustable to the elder residual sight so that no effort is required for interacting through the chosen display. Figure 1 - Two possible Virtual Caregivers from the IGER system: a) a humanoid avatar, Hannah, b) a mascot, Piggy: some users preferred a puppet, that stresses the game nature of the interaction, while others felt more reassured seeing on the screen an avatar resembling a doctor. All interfaces will be designed incrementally. A first mockup with identified functionalities will be provided at M6 and refined afterwards with the feedback of all the formal caregivers mediated by SAS, PCL, MUNICIP and KORIAN. A new interface constituted of mockup and real functionalities will be delivered every three month and questionnaires will be possibly updated. The GUI will be designed and adapted for web browser, smartphone applications, TV monitor and Giraff robot screen. Particular care will be put in the design of the virtual caregiver avatar, such that it does not fall in the so called “uncanny valley”. Its aspect will be stilyzed so as the subject clearly understands that the avatar is a humanoid being, but does not really pretend to be a human being (cf. Error: Reference source not found). We will design and provide several avatars so that the elder will be able to choose the preferred one according to his taste. Such avatar will be endowed with a repertoire of movements and simple facial animation with approximated lip synch among which the most suitable animation congruent with voice feed-back will be produced,. Task 2.6(M2-M12) HRI and user requirement s analysis (UOP, PCL, SAS, MUNICIP, KORIAN) This task will provide the user requirements for the Robohome2.0 system to facilitate natural interaction between the robot and the users. This task will concern the design of the multimodal HRI interface to allow the user to integrate the facility of the Giraff robot and the integrated smart environment systems and the virtual caregiver module. The interface will combine various interaction modalities as speech, touch screen, movement. Focus will be placed on interface facilities to manage the user’s explicit and implicit feedback, as we have previously shown, user feedback is critical to task performance in any assistive, cooperative, or interaction-based robot systems. Such interface will also be able to track the user’s gestures when this is in front of Giraff and it will be used in combination with a speech dialog system to facilitate interaction. On the other hand, the interface will provide speech-based feedback to ask questions, to solve pragmatic ambiguities, to motivate and encourage the elder or simply to establish emotional bonds. Scenario: Giraff approaches Ann this morning and says to her: “Come on Ann, today is a beautiful and sunny day, why don’t you call your nephew Jane to bring her to the park?”. Ann, was a bit said; she finds this a beautiful idea, called Jane and spent a wonderful morning. She was really greatful to Giraff. This will inform the design of the interaction features, the HRI multimodal interface, and the design and analyses of the experimental sessions. The task will combine the use of questionnaires to reach a larger group of potential users in the different countries of the ROBOHOME2.0 partners’ sites. In addition, individual interviews and focus-group sessions will be conducted to investigate specific design interaction issues in more depth. These methodologies will lead to the definition of the user requirements, the design of the metrics to evaluate the user experience, acceptance of the robot, and also the carers’ feedback that will be evaluated in Task 8.1. Task 2.7(M9-M12) Testing will proceed in two directions: technical testing and functional testing (UMIL, POLIMI, SXT, SG, BDIGITAL, UMA). A set of tests and experiments will be designed for testing the functionality and of each component and define their specifications. Tests and experiments to verify the proper communication between the components and between the different stations will also be developed. Software will be developed in a high modular fashion, therefore unit testing methodology will be preferentially be used. This will allow the possibility to adapt easily the tests to specific sections of software that change throughout the development.

Deliverables: D3.1 (R, CO) Technical specifications of the platform and its components (POLIMI, M12) D3.2 (R, CO) HRI analysis and definition of robot-users interfacing modalities (UOP, M12) D3.3 (R/OTHER, CO) GUI design. Design of the major GUI of Robohome2.0 inspired to modularity and adaptation (UMIL, 24). D3.4 (R, CO) Design of testing the system and its components. A set of tests each of the components will be defined. Data associated to these tests will be reported at the end of the development of the components: WP3, WP4, WP5 and WP6 (POLIMI, M12).

#### WP3 – Virtual Caregiver and service robot

| Work package number | 3 |  |  |  | Start date or starting event: |  |  |  |  |  |  | M3 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Work package title | Virtual Caregiver and service robot |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Participant number | 1 | 2 | 3 | 4 |  | 5 | 6 | 7 | 8 | 9 | 10 |  | 11 | 12 | 13 |
| Participant short name | UMIL | ORU | GIRAFF | UOP |  | SXT | PCL | POLIMI | BDIGITAL | SAS | KORIAN |  | SG | UMA | MUNIC |
| Person-months per Participant |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Objectives: - To provide Giraff with autonomous navigation compliance with the elder. - To enable Giraff to provide transparent cognitive and physical transparent clinical tests with sensorized objects. - To develop tele-monitored clinical tests to be performed by the user at home by using Robohome2.0 components. - To profile the user and update his/her profile according to data provided by the activity center, the environment and lifestyle monitoring and the psycho-physical monitoring and from inputs from the community of users. - To infer changes in the user condition from the whole information gathered by the sensorized home and the activity center. - To design and realize a smart drug dispenser.

Role of the partners: ORU will lead this WP for its competences in AI that allow developing the real-time reasoning layer. UMA will coordinate all the developments related to navigation. UMIL will provide expertise in using Kinect mainly for exer-gaming and POLIMI for modeling human motion. SXT will lead the work on building assisting devices. BDIGITAL will bring its expertise in designing and processing environmental data and GIRAFF the knowledge on robot infrastructure. PCL, SAS and KORIAN will bring their view of users on robot and virtual careviver. Description of work Aim of this WP is to transform Giraff from a teleoperated platform into an autonomous service robot that can provide assistance, advice and monitoring of the elder upon the work on a virtual therapist embedded in Giraff. Task 3.1(M7-M18) Infrastracture technical specifications (ORU, GIRAFF, SXT, BDIGITAL, UMIL, POLIMI) To effectively develop the system, it is made clear that all components have to be developed such they can be easily and effectively integrated. It was important that the different parts of the system were communicating from start and therefore the definition of a proper software architecture is required. A middleware in Giraff that can support and communicate the different Robohome2.0 components will be defined. We are aiming to resort to OSGi architecture that is widely diffused for AAL applications and it allows to integrate heterogeneous devices and scale with new devices/services at need. This task defines also the software services that the infrastructure should support. The middlware should be able to support both the acquisition of sensors data periodically, and the immediate acquisition of some sensitive data like gas alarms or voice commands that needs to be processed immediately by the virtual caregivers. Z-wave communication seems to offer the best match for environment sensors acquisition, but other standards that would become available at project starts will be evaluated as well. Similarly, Bluetooth connection seems the most effective transmission modality for data transmission because of its tread-off between power and latency. Indeed Bluetooth connection has already been implemented in devices for clinical use, like the Tymo balance board. We will implement a service to identify the most suitable device for a particular output. For instance, at due time, Robohome2.0 will inform the elder through the virtual caregiver that she has to take a given pill and that the corresponding drawer has been unlocked. The virtual caregiver will transmit this information to the patient with the best channel available, taking into account the elder preferences and the status of the devices (e.g. it can be through an SMS or video message on cell phone, through Giraff monitor or through TVscreen). Task 3.2(M3-M24) Enhanced navigation (UMA, UMIL, GIRAFF, ORU) This task capitalizes on the experience on navigation and SLAM of UMA, . We will develop an ecological approach for both the autonomous navigation of the Giraff and its approach to the elder by identifying the path and velocity profile that are most suitable. For the autonomous navigation, we will provide the robot the capacity to move from one place of the house to another, selecting the best route (global navigation) and avoiding any obstacle encountered along its way (local navigation). As for the global navigation, houses present a highly structured topology, typically a corridor connecting rooms. Our proposal for global navigation between two locations of a house (in general, from two different rooms) is as follows: first, planning a sequence of intermediate places (from the topological map) from the start to the destination, and then to concatenate a series of reactive navigations between them. Two are the major challenges for the reactive navigation: 1) to manoeuvre in tight spaces, without being trapped in local minima, and to deal with 3D-shaped objects. It’s important to notice that, for the Giraff robot, the common assumption of worst-case, constant shape along its height is quite unreal, and prevents finding possible free space to traverse through. We propose to work towards a solution that accounts for these features by extending to 3D the previous work of the UMA group on 2D reactive navigator, which models the robot shape as a polygon and embeds its kinematic constraints into different motion models through the so-called Parameter-Space Transformations. Apart from the geometrical and kinematics robot constraints, we will explore here how introduce additional proxemic ones that take into account the idiosyncrasies of the elder. For instance, she/he may not like that Giraff approach him frontally, or to stand too close. Task 3.3(M3-M18) Motion tracking for transparent monitoring (UMA, UMIL, POLIMI) In this task a function that automatically determines the optimal location and orientation of Giraff for transparent monitoring will be designed and implemented. Motion will be captured as a moving skeleton that is automatically fit to a moving human by Kinect SDK. To obtain this, a clear view of the motion should be provided to Giraff’s Kinect camera. The function will take into account the type of movement , its amplitude and position in space as well as the constraints provided by the room inside which the activity takes place. The solution will be the result of the optimization of a cost function that takes into consideration all these aspects. Task 3.4(M3-M12) Modeling the users and the functionalities of Robohome2.0 (ORU, UMIL, UMA, SAS, PCL) This task is concerned with creating semantic models (ontologies) that depict information about the end users, domain, activities, functionalities of objects etc. The goal will be to align the various high level models in order to link them for eventual reasoning on the data provided by monitoring and activities. This information will be used to tune the activities inside the activity center; this task will be developed in tight connection with UMIL. The actual elder profile will be initialized according to information gathered from clincians and caregivers, and it will be updated according to informations gathered by monitoring and activity. Elder’s idiosyncrasies will be also considered. Task 3.5(M3-M27) Reasoning and Recommendation Layer (ORU, UMA, UMIL, POLIMI) Based on the models in Task 3.4, eventual rules will be constructed that will link the models with the data from the sensors, the community and the activity center. Such rules will be then be used for providing recommendations. A deductive reasoner will be used [ORU, may you add reference / or description. Do you use any particular commercial reasoning Software?] that will take into account also the past history of recommendations. Recommendations may be triggered by the reasoning layer but may also be provided by the caregivers; they are constructed from atomic actions using the actual semantic model of particular user. Recommendations are presented via the caregiver avatar which passes the actual utterances with recommendations to the elder. Recommendation is tuned by the caregiver itself according to the evaluation of the elder and of the caregivers, as well as possible deteriorations of psycho-physical conditions. SCENARIO: Anna is calling her friend less often in the last week. Giraff (ROBOHOME) identifies that Anna has to be suggested more social activities and suggests her more social activities, suggesting playing cards, give calls to Michela or Mary, who has not heard about since a long time, or to go with her friend to the violin concert of her nephew to which she was invited. Task 3.6(M2-M24) Teleoperated clinical evaluation (POLIMI, KORIAN, PCL, SAS, BDIGITAL, GIRAFF) These tests are complementary to the transparent tests developed in WP5 and they have both the aim of a clinical validation of the cognitive and physical status of the elder. The most suitable cognitive and physical test to be telemonitored will be identified, for instance [TO BE COMPLETED by UMIL]. A procedure to compute the evaluation will be designed and implemented. For cognitive tests can be the collection of the answers provided pressing a given virtual button on the screen. For physical tests, tracking with Giraff camera can provide the data required. Task 3.7(M7-M24) Development of a cooperative smart drug dispenser (SXT, POLIMI, BDIGITAL, UMIL) This is aimed to improve therapy compliance. It will be constituted of a chest of drawers, each with an electro-magnetic lock, a led, and a micro-controller wireless connected to Robohome2.0 virtual caregiver. Upon command, the chest drawer will un-lock only the right drawer from which the right pill will be taken, and will switch on its associated led. At the same time, the virtual caregiver warns the elder through all the devices available, Giraff, mobile phone, TV and so forth and it renew the memo every given period, until the drawer is not opened and pills are extracted. Adequate modular remaining software will be developed. Task 3.8(M7-M24) Development of an assistance system based on instrumented objects of everyday life (SXT, POLIMI, BDIGITAL, UMIL) In this task an assistance system able to locate of everyday objects (eyeglasses, keys, mobile phone, and walking stick) will be developed. Scenario. Jessica does not find her keys, call Giraffs and asks for the keys. Giraff activates and ask to the virtual caregiver help. This logs the actual power of the signal from the keys and guides Giraff towards an increase of the signal. Giraff starts moving to the right towards the sitting room, that is prioritized in the list of the rooms in the house. It then moves towards the dining room and registers and increase in the signal and moves in that room until it gets close to a drawer on the top of which are the keys. Giraff calls then the elder to get the keys. To this aim different already existent sensors to assist tracking of everyday objects will be investigated. There are new emerging solutions based on sticks or key rings to be used with specific Apps, but elderly people would have still to find by themselves the objects and, moreover, the mobile phone has not to be lost. The Phone can be located through GPS signal, but usually GPS signal cannot be received at home. Also RFID technologies already are used for tagging objects. However, RFID tags devices require a reader to be placed inside all the rooms, with a high impact on the house. At present At present, the most interesting approach seems the one based on Bluetooth technologies (v 4.0) that will allow to extend the range of detection, even with reduced power consumption. An adequate receiver software/hardware module will be realized that can be integrated inside Giraff. API will be provided such that the device can be controlled by apps developed for smart phone or by the Giraff caregiver.

Deliverables (brief description and month of delivery) D3.1 [R, PU] Methodology for profiling the elders and the functionalities and some real case scenarios (ORU, M12) D3.2 [R/OTHER, CO] Improved navigation functionalities (UMA, M24) D3.3 [R, PU] The reasoning and recommendation system (ORU, M24) D3.4 [R/OTHER, CO] Tested prototype of everyday life assistance and therapy compliance (SXT, M24)

#### WP4 – Activity Center

| Work package number | 4 |  |  |  | Start date or starting event: |  |  |  |  |  |  | M3 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Work package title | Activity Center |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Participant number | 1 | 2 | 3 | 4 |  | 5 | 6 | 7 | 8 | 9 | 10 |  | 11 | 12 | 13 |
| Participant short name | UMIL | ORU | GIRAFF | UOP |  | SXT | PCL | POLIMI | BDIGITAL | SAS | KORIAN |  | SG | UMA | MUNIC |
| Person-months per Participant |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Objectives: • Realize the Smart activity Center with full functionalities and the communication infrastructure with the virtual caregiver; • Design, implement exer-games that can be adapted to the physical and cognitive status of the elder; • Design and develop automatic narration for long lasting games; • Explore the use of generic everyday physical objects as trackers; - Provide support to social activities and to card games in particular.

Role of partners: UMIL will lead this WP for its specific experience on gamification developed in FITREHAB and REWIRE project. POLIMI will also participate supporting mainly multi-player gaming. UOP, SAS, PCL and KORIAN will help finding the most suitable game design and gameplay. UMA will contribute in the camera processing data and GIRAFF in the architectural support. Description of work: The activity center will be built around the gamification concept and therefore all its functionalities will be implemented with entertainment in mind. Task 4.1(M3-M27) Design and implementation of the activity center (UMIL, GIRAFF, PCL, SAS, KORIAN, UOP) The most suitable software architecture will be designed to support a large range of cognitive and physical exer-games, according to specifications set in WP1 and WP2, that can guide the elders through social cognitive and physical activities. Basic functionalities will comprehend loading scenes and avatars, collision detection, rendering, and animation capabilities. Most accepted standards for data storage and transmission will be used (e.g. XML for definition of activities and configuration, quaternions for motion representation). The center will be based on the IGER game engine and it will be realized in subsequent steps, incorporating via via new features. IGER already integrates methods of computational intelligence for users’ monitoring: user’s movements are continuously monitored using a fuzzy system (leveraging for instance the therapists’ knowledge) to avoid wrong postures or wrong movements, which would make exercising more harmful than useful. A novel color coding feed-back is used to inform the user in real-time on wrong movements. IGER also integrates a personalized avatar that guides the elders providing advice and fed-back to them (Task 2.5). Given that much care should be put in making these exercises at the proper level of difficulties and games attractive in order to achieve a strong treatment adherence, IGER games are fully configurable so that they can be tailored by the clinicians to the users needs and exercising goals, and they are continuously adapted in real-time to the user’s performance through a Bayesian framework that updates game parameters to provide an adequate difficulty level while keeping the elders within the therapeutic constraints specified by the virtual caregiver. All these features will be fully exploited in Robohome2.0. IGER will be extended in several directions. We will explore the different visualization possibilities offered by modern ICT technology. We aim, in particular, at introducing the concept of device equivalence. This is a concept well known in the technology domain,, and it will be fully exploited here to allow the elder to interact with Giraff and with the activity center through different displays. These can be: Giraff display, computers, laptops, tablets, digital frames, mobile phones and in particular, TV screens. The middleware will be extended to provide this support, formatting the output to the current display chosen by the Virtual Caregiver as most suitable for a particular activity / message. To this aim we will explore a wireless connection between the game center and the TV, using for instance miracast solution. This solution will be exploited also to provide news, advice and recommendations to the elder through the TV display, by means of the Virtual Avatar. Interfacing based on Natural User Interface (NUI), defined in WP2, will be developed, such that activities will be played in the most natural way, without needing to hold or wear additional devices. In particular, voice and gesture interfacing will be developed for gaming with the TV (with Giraff on the side) or with Giraff itself or which touch and voice control modality when smart phones are used. An extrinsic motivation framework, common to all activities, based on balanced reward, game design of adequate cognitive complexity and gameplay at the proper level of challenge will be developed. Controlled randomization of assets, targets, voice feed-back avatar choice, and facial animation are all aimed to increase compliance with the therapy, . Automatic mesh simplification algorithms, working on both geometry and viual appearance, will be adopted to create a sets of game assets of different LOD; alternatively more simple heuristics based on objects count and on their dimensions will be used. LODs model will allow loading the game scenes with the most adequate cognitive load will be selected. An adequate measure of cognitive load, that takes into account both 3D geometry and texture, will be defined to match the profiling of the patient. Task 4.2(M7-M12) Silhouette extraction for improved immersion (UMA, UMIL) In this task we aim to segment the body of the elder in front of Giraff 3D camera from the background, and to use this for visualizing the elder inside a virtual environment through alfa channel blending. To achieve this task robustly, we will start from segmentation obtained using only the depth data. Although this produces a robust identification of the user, the borders of the silhouette are jerky and not allow a clean view of the self inside the virtual environment. Although several attempts to smooth the boder have been proposed, an effective solution is still not available. We will combine in this Task, the rande and RGB image provided by the Kinect camera to achieve a better segmentation. In particular, RGB image will be used to refine the border of the silhouette locally, through a local regularization approach that allows identifying the most clear borders in RGB images. Task 4.3(M7-M21) Mini-games content generation (UMIL, SAS, PCL, MUNICIP, POLIMI, UOP) We will begin from two starting points: the identified profiles of the elders and the associated mix of activities (WP1) and the identification of suitable theme, among those made available for the project identified taking into account gender preferences. The latter can be familiar for the elder, like for instance a classical environment of a fairy tale or a virtual Olympic competition or a travel around the world. Such personalized environments will constitute the containers inside which the activities will be accommodated. We will then design mini-games, inside the theme chosen, that match the functional requirements. These can be for instance solving a puzzle, playing a memory game, specific physical exercises. For instance a balance exercise that requires raising alternatively one leg can be guided by a mini-game that asks the elder to raise the leg to step from one stone to the next one to cross the river and therefore continues hunting the monster that terrifies the town. A meaningful gameplay will be designed and implemented to guide the elders through the desired exercises; in particular, clear interaction and feed-back with reasonable lasting effects, enjoyable environment, music, sound, rich graphics will be adopted according to the rules of good game design. We will design physical exer-games such that the elder can exercise alone or with her/his caregivers and friends either remotely or inside the house. The first option will be supported by the infrastructure developed in Task 4.5 and 6.1) that support multiplayer games. We will also enable the elder to play in from of the TV. In this case Giraff Giraff will accommodate besides the TV using its Kinect to survey elder motion in front of the TV. The elder will see on the monitor the virtual caregiver introducing the exer-games and starts exercising following the gameplay. To avoid perspective distortion, correction for viewing angle of Giraff. SCENARIO: Robert gait is becoming slower and less stable. Giraff identifies that Robert needs to move more and identifies exercises for balance and posture as the best remedy. It proposes to him a set of exer-games to be played for a quarter of an hour for at least two weeks. It also shows to Robert the picture of all the other elders inside the Robohome2.0 community that has entered in the same program. The idea of a group of new people with whom Robert can compare turned out really motivating for him who start exercising regularly without missing a day. His caregiver and GP were extremely happy of this as they believe this would keep him far from needing a wheel-chair for longer time. Cognitive activities will be based mainly on touch screen interaction. A set of suitable exer-games, identified in WP2 and WP3 will be designed and implemented. Some of them could be puzzle, Simon game or other memory games. Content will be generated automatically according to the elder idiosynchrasis. For instance, puzzle games can be based on pictures uploaded by the elders, possibly regarding happy times with children and nephews. Memory tests may be related to diet, and sequence of instructions of a given recipie of the preferred cake of the elder’s housband has to be guessed, and so forth. Some games already diffused like ruzzle can be incorporated inside training, promoting the use of games already distributed by the open source community. Similarly to physical games, cognitive games can be played with caregivers and/or friends inside the house of remotely through the community. Besides exer-gaming, the activity center will also provide simple questions for assessing purpose. For instance, when switching on the TV the virtual caregiver may ask a question from a cognitive test, picked up randomly, asking for instance the current day, season, month, the name of daughter or son and so forth. Social activities. Card games are most popular among the eldest. They combine three important aspects: cognitive stimulation (memory, strategy), social interaction and competition with pairs. It is not always possible for the elders to get together in a physical place to play, and Robohome2.0 can help the elder in this activity providing a virtual environment to play together. Robohome2.0 will take advantage of multi-player support and video interaction to provide a real-time video-stream of all the elders playing together inside the same display window, so that each elder sees the other as he was present in the room. A virtual table will be represented with the cards played, the cards on the table, the card virtual deck and the cards in the hand of each elder. SCENARIO: Anna is listless today. She is invited by the smart caregiver to contact her friends for a card game. Anna starts playing with Emma, Michela and Lina but Emma realizes that Anna is slower than usual to play her card and she is not at her best level. Emma herself leaves a message to her virtual caregiver that transmits the gentle message to Anna’s relatives. SCENARIO. Maria has started to use a walking stick, with whom she feels more comfortable. However she is still stable enough and the caregiver identifies postural exer-games useful to maintain a good postural control for prolonged time. It suggests to Maria to play games like the arcade game: “Whac-A-Mole” in which she has to smash a virtual mole coming out the virtual floor displayed in front of her. Indeed such exer-games was fun but allows also Mary improve in managing her walking stick. Task 4.4(M7-M30) Automatic narration (UMIL, POLIMI, UOP, ORU) To provide long last activities, variety may not be sufficient on the long run and their integration inside a narration will be explored inside this task to provide long-term motivation, with novel approaches. We will design several mini-episodes on the themes identified in Task 4.1 and describe them using ontology based methods to derive a meaningful initial and final state for the episode and a structured content. Stochastic finite state machines will be used to chain each next episode, by defining a transition probability that reflects the degree of compatibility of one episodes with respect to the next based on their ontologies and by the capability of that episode to support the activity prescribed (e.g. crossing a river can be implemented also through a puzzle game of through a memory game that assigns a reward that allows to accomplish the task). This method will provide the elder with an unpredictable sequence of episodes, thus creating a surprise element that is a fundamental ingredient for motivation. We will explore also reinforcement learning to make the activity center learn which can be the best next episode, for the elder, given his/her idiosyncrasies, by collecting her/his qualitative feedback at the end of each episode. Games will be heavily embedded into a social dimension through an on-line community that will enable patient empowerment strategies such as negotiation of the goals of care and communicating with other patients. These services will allow clinicians to get feedback on patient treatment perception, symptoms and the execution of exercises and increase patients motivation and compliance. Trust and reputation mechanisms will be implemented to encourage patients in exercising and increasing their compliance with the therapy. Task 4.5(M18-M36) Personalized educational games (UMIL, PCL, SAS, BDIGITAL, POLIMI) The same features developed for exercising will be used to build educational games that will be used by the elders and their caregivers to learn on their diseases and therapy and on their lifestyle. The elders, gaming, can for instance learn the interaction between the drugs he takes and the avoidance of the decline associated with aging. To realize an effective educational game engine, all the functions and elements on which to build education: therapy, comorbidity, desease description and lifestyle have to be identified with clinicians. Possible critical elements will be defined as well as consequences associated. Throughout the game, the patient will be guided to increase his knowledge about his conditions, with the aim of increasing his self-management skills and information about the medications related with the disease and the possible collateral and interaction effects. In addition, serious games will try to produce lifestyle changes in patient promoting healthy and active lifestyles, fostering patient treatment adherence. Task 4.6(M3-M24) Social activities through multiplayer games (POLIMI, UMIL, BDIGITAL, UOP) This is a mainly technological task aimed in maximizing the sense of presence when more elder people are doing activity together. To this aim it will be provided two different settings. The first setting will be based on multi-video streaming, in which the video captured in multiple sites is shown in the same display window. Such setting can be used to support social activities. For instance these video can, for instance, capture a group of elder that are playing the same card game, each in his own house. All the elders will see themselves and the other pairs in different windows on the screen. Card played will be shown in the middle of the screen mixing virtual elements with multiple videos. It will analyzed the most suitable technology to realize this. On the one side SkypeVideo APIs seem particularly suitable for this as they allow point to point video streaming, that can be manageable for a few elders playing together. On another side WebRTC technology provides more secure video streaming because it offers a direct peer-to-peer streaming without having any other intermediary server. Moreover it is an open standard based on web technologies. BDIGITAL CAN PUT HERE ITS VIEW. Merging video streams with virtual scene will take place at visualization time, resorting to alpha shading as shown in the Duckneglect system: a silhouette with the virtual scene, a card virtual carpet in this case, is created and this is used as a binary transparency mask, substituting to the current content of the viewport outside the silhouette area with the videos. Similarly the same platform will be used to do physical exercises in a group, while still being each elder at his own home. In this case, a virtual trainer will lead the exercises showing what to do in the center of the screen, and the different elders will see all the other pairs doing the exercises. Such setting will promote also discussion and speech between the elders themselves and will promote socialization. SCENARIO Michela leaves in Milano. She is feeling lazy and a bit less social in the last days and is moving less time as shown by more time spent on the sofa, watching TV and the average decrease of telephone conversations. The virtual caregiver approaches her and, with nice voice, remembers that she was a dancer when she was young and that some exercise would indeed helpful to her. The Virtual Caregiver suggests also her that at 3pm in the afternoon there is a live virtual session of dancing for a group of people of her capability. Lucille is sceptic, but when the Virtual Care Giver remember her this appointment just after lunch, she decides to try. With her surprise, she sees in the group a old co-dancer of her, Lenita, living now in ORU. They are happy to make dance movements together and, at the end, they could restore the old friendhship. Since then they started meeting not only for the exercises, but also through video communication through Robohome2.0 platform. Eventually their nephews met each other and could meet one year in Italy and one in Sweden in summertime, enlarging the social dimension of their whole family. Michela and Lenita were very happy of this. In the second form, the multi-player platform will support some collaborative work. We will explore for instance this through puzzle games that can be made cooperatively. In this case, in addition to see on the screen the virtual table with some of the puzzle tiles in place and the video of the other pairs playing Robohome2.0 will also track elder gestures to select virtual pieces not yet positioned, rotate and put them in place. This will be exploit gesture recognition developed in Task 4.1. With this set-up , we aim to realizing a collaborative, goal oriented activity that can have a cognitive and social value. Most of the work will be completed in the first year of the project (D4.1). We leave open the possibility of few refinements that could be implemented in the second year of the project, according to the technology offer that will be made available (D4.3). Task 4.7(M3-M18) Definition of calibration games for video and/or inertial systems (UMIL, SXT, POLIMI, UMA) This task is aimed to developing all the methods that allow fusing tracking data obtained from different sources. These methods will be based on games and therefore we will explore games also for calibration the platform. A high accuracy calibration will be carried out by the service provider before delivering the system, but fine tuning of the calibration is required on the field and should be as simple as possible to cope with limited abilities of the elder and his caregivers and work in a general environment. This is required for instance to register the motion data acquired from the instrumented objects with the graphics or with the video data. Ad hoc calibration objects that can be integrated in the room furniture will be studied. Automatic spatial registration of the tracker with the graphical engine will be carried out. [COMPARE TO WP5] Task4.8(M7-M27) Functional and usability tests (PCL, UMIL, POLIMI, SXT, BDIGITAL, UMA, SAS, MUNICIP, KORIAN) The activity center and its exer-games will be tested starting early in the project, when simple features and infrastructure will be built up to the end of development. Such tests will be organized for groups of users who will evaluate the usability and effectiveness of the functionalities from the early prototypes to the final system to verify that they match users expectations and needs. Task4.9(M13-M36) Smart gaming with instrumented objects (UMIL, POLIMI, UMA, UOP). We will explore the use of instrumented objects as trackers. We can envisage the elder trying to comb a virtual doll with a real comb or drinking virtual coffee from a real cup. We can envisage also transforming these objects into virtual ones, the cup becoming a “magic potion” and the comb a “magic sword”. We will also explore pressure sensing to realize magic effects like making objects disappearing. Using these objects with games endowed of the adequate gameplay, these objects would allow to acquire specific motion and pressure patterns that are required by clinicians. It will also be interesting for gamification and for new paradigms for gaming. To achieve this the calibration between the sensorized objects and the graphics carried out in Task 5.x wil be continuously updated to improve the accuracy and compensate possible drifts of sensor parameters. IGER middleware will allow to easily integrate the motion and pressure data coming from the sensorized objects.

Deliverables: D4.1 (R/OTHER, CO) A first nucleus of physical and cognitive games + silhouette tracking. A first user manual will be provided (UMIL, M12). D4.2 (R/OTHER, CO) The full system for education (POLIMI, M18). D4.3 (R/OTHER, CO) The full smart activity center with the final reference manual, user manual and installation manual (UMIL, 27).

#### WP5 – Monitoring Systems

| Work package number | 4 |  |  |  | Start date or starting event: |  |  |  |  |  |  | M3 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Work package title | Activity Center |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Participant number | 1 | 2 | 3 | 4 |  | 5 | 6 | 7 | 8 | 9 | 10 |  | 11 | 12 | 13 |
| Participant short name | UMIL | ORU | GIRAFF | UOP |  | SXT | PCL | POLIMI | BDIGITAL | SAS | KORIAN |  | SG | UMA | MUNIC |
| Person-months per Participant |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Objectives: - To design and implement the sensorized objects and the communication infrastructure with the virtual caregiver and the service robot; - To design and implement environment, lifestyle and social monitoring; - To design a physiological monitoring sub-network; - To design and implement a distributed voice control system; - To realize the sensorized home monitoring system; - To design and validate cognitive and physical transparent clinical tests.

Role of partners: POLIMI will lead this WP for its specific experience in multimodal monitoring and assessment of the user condition. POLIMI will implement the physiological measurements sub-network with the support of KORIAN, PCL, SAS, and MUNICIP and will collaborate with PCL in the validation of the novel transparent clinical tests. SXT will develop of the sensorized objects for physical and cognitive monitoring and the micro-architecture that allows the integration of the monitoring systems within Giraff (WP3). GIRAFF will collaborated with SXT in the design of the architecture to integrate the sensorized objects with the service robot motion tracking feature. BDIGITAL will work on the environmental and social monitoring and SG on the implementation of distributed voice command system. UMIL will design and implement the interfaces that are required by the different tasks, having in mind usability and ease of use Description of work: The aim of this WP is to provide a set of customized and off-the-shelf very low cost devices and tools to monitor the elder behavior at home and his physical and cognitive condition. All of the sensors will be designed and selected following the user and functional monitoring requirements (Task 1.3) and the technical specifications identified in Task 2.2. For each of the sensors different technological solutions will be studied. The developed sensors and sensorized devices will be also used to develop an innovative transparent monitoring modality to be executed at home, novel cognitive and physical transparent clinical tests as defined in Task 2.1. This cognitive and physical transparent monitoring will be embedded in the usual user lifestyle such that the elder does not perceive monitoring as an activity disjointed from his/her ordinary life. All the sensors will be integrated in the sensorized home (full monitoring system) and a comprehensive middleware will be implemented allowing the communication between the monitoring system and the virtual caregiver. The definition of user scenarios (WP1) will be necessary to identify the set of sensors to be selected by each user profile. The modularity approach of the monitoring system will assure the flexibility and adaptability to different users and scenario. The implemented middleware will provide to the virtual caregiver (WP3) the updated information about the parameters required to monitor the single user so to allow the personalization of the user profile according to the actual user condition. Task 5.1 (M3-M24) Design of the micro-architecture for transparent monitoring and implementation inside objects (SXT, POLIMI, UMIL, BDIGITAL, GIRAFF) Both to monitor the physical performance during the exer-games proposed by the Robohome2.0 Activity center (WP4) and during the transparent clinical tests, different objects of daily life will be instrumented to monitor the user interaction with them. The objects to be instrumented will be defined in Task 1.3. To this aim, micro-architectures will be realized that can be adapted to different objects. Such micro-architecture is based on micro-sensors of pressure and acceleration [e.g. Digitacts sensors by PPS (left figure), or Flexiforce sensors by Tekscan (right figure) for pressure/force and LIS331 by STM for acceleration. Pressure sensors can be directly integrated on the surfaces of objects, while the electronic circuits can be introduced in specific lodge, like for instance inside the handle of a walking stick. Inertial sensors can be integrated with the electronic circuits inside the body of the object. The personalization of the lodge containing the sensors will be carried out using 3D printing technology to achieve maximum physical and psychological compliance with the elder. Psychological issues in accepting these high technology devices will be properly dealt with PCL and ORU. The micro-architecture will be switched on from the virtual caregiver and controlled remotely through Bluetooth 4.0 connection (enabling “smart-device” technology). In the past SXT developed inertial, wearable systems to analyze human movement at work, during sport activities or rehabilitation, like Protheo (a compact device to measure Heart rate and movement in daily-life activities) Nowadays such technology can be reduced in size and transferred to objects, using the Bluetooth module to directly control sensors and measure analog signals, requiring only the preconditioning circuitry in case of pressure/force sensors. UI (if needed) UTENTE BT MEMS CONDITIONINGZIONE UISIZIONE POWER TRASMISSIONE SENSORS After integration, inertial sensors can be easily calibrated to remove offsets due to their orientations, while pressure and force sensors can be easily calibrated before their integration on the object. Refinement of calibration can be implemented in case of need through the auto-calibration techcniques developed by UMIL that are transparent to the user. By means of inertial sensors integrated in the handle of walking stick for instance, it could be possible to analyze changes in movements, or specific behavior and or pattern modifications (peak of acceleration, speed of objects and their orientation when used are parameters that can be used to infer indication about users’ performances and behavior). MEMS technologies are now a stable and cost effective solutions: 3D, smart accelerometer and gyroscopes are wide diffused in game consoles and automotive systems. Many different models are available. The really compact design of such transducers (as low as 2x2x1 mm3) that allow to perform different kind of measures at really low power consumption (LIS331 and a modern Cortex™ CPU can require few µA, thanks to the different operating modes that can be implemented). With the aid of modern tactile sensing technology, it will be possible to measure the pressure or the force applied to different kind of handles, in order to infer data related to the clamping force and direction. Both inertial and tactile sensors can be connected or embedded with wireless modules, such as low power Bluetooth® modules (e.g. class 4.0) in order to create really low power, compact and flexible systems. During the rest condition, through wireless charge or standard charge technologies it will be possible to recharge the systems. The source of power can be introduced in specific places where instrumented objects will be put during rest condition. The new Bluetooth® Smart Technologies [http://www.bluetooth.com/Pages/Bluetooth-Smart.aspx] will be able to create extremely low power, standard transmission. Such wireless solutions are already compatible with emerging wireless charge technologies that can make really easy and safe the usage from elderly people. These microarchitectures will be realized with two modalities: - The first modality will be a real-time transmission of the data in which the micro-controller will read the data from the sensor, process them and output in real-time the value through blue-tooth connection. It will be used for the activities integrated in the exer-games (WP4) or for designing the transparent clinical tests in combination with Giraff motion tracking developed in Task 3.3. - The second modality will allow the on-board storing of the data related to an entire day. This modality will be used to gather information on the physical behavior of the elder during the day. The data will be downloaded automatically when the walking stick is put on rest using an approach similar to that of Giraff and of Sony AIBOs [ ]. Task 5.2 (M7-M27) Design and clinical evaluation of transparent monitoring (POLIMI, PCL, SXT) In this task psycho- physical monitoring of elder status will be performed by a novel approach that combines a robot to measure the elder movement by means of motion tracking (Task 3.3) in combination with a set of sensorized common use objects to measure objects interaction in gestures of typical everyday activities (Task 5.1). This monitoring will be called transparent monitoring because it will allow to acquire the elder natural behavior throughout his usual daily activities such that the elder does not perceive monitoring as an activity disjointed from his/her ordinary life. The transparent monitoring is based on the principle that gestures are the expression of the motor and cognitive ability of the patient. Efficient gesture segmentation algorithms based on kinematics or pressure time courses will be implemented. This will provide candidate points for start and end of a single gesture that will prompt a search for a motion pattern that will be identified through clustering and time warping. Regarding physical transparent monitoring, we will define a Gesture Degradation Indexes that analyzes the variability of the relevant motion and force parameters during daily activities to infer motor decline. Regarding cognitive transparent monitoring, we will evaluate the proper concatenation of the different actions that constitute everyday activities The transparent tests will be validated against gold standard clinical tests in collaboration with PCL. [TO BE REFINED and COMPLETED by POLIMI] Task 5.3 (M7-M24) Design and implementation of environment and lifestyle monitoring (BDIGITAL, POLIMI, SXT, UMIL) This sub-network will chain several sensors that are associated to the home. The final list will be defined in Task 1.3, but a preliminary list can be: - Presence sensors to check the level of mobility of the user in the day - Cushion pressure sensor to understand how long the elder is sitting. - TV power consumption monitoring (how much is on and the elder is sitting in front of it). - Gas alarms - Temperature and humidity sensor We can use, for instance, z-wave sensors to control the presence of the elder in the room and this will be used to evaluate if this is a normal or anomalous behavior. For instance the presence in different rooms at night is a sign of insomnia, or the prolonged period in the bathroom with respect to normal time will be an anomalous behavior that can be detected by the virtual therapist with this information. Temperature, humidity, cushion pressure are all information that can be used to tune the intensity of the activity and have an unbiased reading of the current lifestyle activity. he same sub-network will check for gas and smoke alarms to the virtual caregiver that will immediately raise an alarm and warn the caregivers through the network and through phone. We envisage an architecture based on a Rasperry micro-server that transmits the data to the virtual caregiver embodied in the Giraff robot, that combines environment monitors with monitors from other devices to adapt activity and possibly raise alarms. Different priority in the acquired information will be casted: gas alarms will raise a high level alarm with no delay while temperature and humidity may be acquired and processed with delay. Task 5.4 (M7-M24) Design and implementation of social behavior monitoring (BDIGITAL, POLIMI, SXT, UMIL) Social behavior will be tracked through heterogoenous information. First source information will be made available through a log book of activities compiled by the elder caregiver, for instance on a weekly basis. Such documentation will be formatted according to the ontology defined in Task3.1 and provided to Giraff through a smart phone app or directly to Giraff from a control panel. Additional information will be provided by the analysis of the activities. Lastly, a profiling of the phone conversation of the elder will be carried out in terms of duration and called numbers. We will also carry out a pitch analysis with the aim of identifying possible consistent changes of emotional status that can be carried out, for instance, through time window Fourier analysis or cepstrum analysis of audio signal. Such information might be an early warning of emotional and cognitive changes that are indeed associated with some degenerative cognitive illnesses. The task will end with a technical and functional testing. Task 5.5 (M7-M24) Design and implementation of distributed voice command system (SG, BDIGITAL, UMIL) A low-level speech processing software library will be developed so as to enable basic behavioural characteristic detection but also enable specific voice command execution . The software library will be design in such a way so as to execute on the robot embedded hardware. Various speech analysis and recognition approaches based mainly on the cestrum coefficients and HMM models will be examined. Task 5.6 (M7-M24) Design and implementation of physiological measurements sub-network (POLIMI, KORIAN, SXT, BDIGITAL, PCL, SAS, MUNICIP, UMIL) To monitor the health condition by means of the typical parameters identified in Task 1.3 (e.g.,blood pressure, heart rate and glucose concentration, oxygen saturation ...) low cost devices already available in the market that complies with all the medical equipment safety and quality standards are required (EN 1060-1, EN 1060-3, EN 1060-4 and ISO 8106). An initial detailed analysis of the state of the art and of the devices already available in the market at project start will be carried out as this is a field evolving at an extremely fast pace. A possibility would be to select off-the-shelf OEM modules (e.g. http://www.medlab.eu/english/modules/, http://www.casmed.com/files/documents/OEM_SellRev00.pdf). These cost-optimized and miniaturized modules can offer accurate measures meeting all of the medical equipment safety and quality standards and can be simply integrated in the final Robohome2.0 platform. The modules will be specifically selected according to the scenarios and user clinical needs. These modules can be directly mounted on Robohome2.0 without using any wearable solution and would allow the elder to take required samples with the assistance and instructions of the virtual caregiver. Alternatives that can be explored are those associated with smart phones, like the heart rate sensor integrated in the new Samsung-5 smart phone. In this case an app to communicate wireless from the Smart phone with Giraff will be implemented. To provide a non-invasive measure of blood components the possibility to use retinal imaging (http://www.google.com/patents/US6477394) will be also investigated and an off-the-shelf product being a trade-off among low cost, usability and reliability will be selected. Task 5.7 (M19-M27) Functional and usability tests of the sensorized home (POLIMI, SXT, BDIGITAL, UMIL, PCL, SAS, MUNICIP, KORIAN) After the design and optimization of all the sub-networks of the monitoring system, the integration phase is very delicate and critical. The system integration represents the connection between technology and medical application. The assembly of every biomedical instrumentation requires not only the specific technical knowledge but also the knowledge of ergonomy and usability aspects especially when the device as to be deployed at home to a non-expert user. The development of preliminary prototypes will help to define the sensor-network integration process step by step. Indeed, the extensive set of bench testing performed with each submodule developed in Tasks 5.1-5.4 and the results of these tests will be used as reference for the bench testing after the integration of the sensor network. The network of sensors will be a modular sensorized home that allows its personalization with respect to the user scenario. The network of sensors will be integrated in a middleware that will provide to the intelligence the updated information on the required parameters. The most suitable standards will be identified and used to facilitate interoperability. All of the selected and developed devices will have most different transmission capabilities and cabling the entire house cannot be feasible. A structure based on WiFi transmission will be the most reasonable. It could be based on a Hub or concentrator that integrates for instance a Raspberry card with a set of USB ports and a WiFi transmitted to the Intelligence. Technical and functional testing of the sensorized home will be performed and particular attention will be devoted to the characterization of the performance of the integrated system in terms of robustness, usability, and dependability.

Deliverables: D5.1 [R, CO] Design and development of the monitoring sub-networks; a first report will be provided (BDIGITAL M12) D5.2 [R, CO] The full monitoring systems ready for usability testing (POLIMI, M18) D5.3 [R, PU] Validation of the clinical transparent clinical tests (POLIMI, M27) D5.4 [R, PU] Report on the functional and usability tests of the monitoring systems (POLIMI, M27)

#### WP6 – Virtual Community

| Work package number | 6 |  |  |  | Start date or starting event: |  |  |  |  |  |  | M3 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Work package title | Virtual Community |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Participant number | 1 | 2 | 3 | 4 |  | 5 | 6 | 7 | 8 | 9 | 10 |  | 11 | 12 | 13 |
| Participant short name | UMIL | ORU | GIRAFF | UOP |  | SXT | PCL | POLIMI | BDIGITAL | SAS | KORIAN |  | SG | UMA | MUNIC |
| Person-months per Participant | 11 | 1 | 1 | 1 |  | 0 | 6 | 7 | 30 | 5 | 2 |  | 4 | 0 | 4 |

Objectives: - Implement and integrate social platform called Virtual Community based on web technologies which will provide services to unify all actors involved within ROBOHOME2.0 system; - To provide a set of specific services oriented to elderly people and formal/informal caregivers to promote socialization and communication between them; - To offer a social and healthcare support to the elders; - To interconnect a different type of devices used within ROBOHOME2.0 such as smartphones and Giraff robot through Virtual Community; - To provide an interaction point for Virtual Community users; - To create an environment to increase elderly motivation, adherence, cognitive and physical stimulation.

Partners role: BDIGITAL will lead this WP for its wide experience in designing web-based communities inside the projects, Rewiere, Backhome and Saapho and will design and implement the infrastructure. UOP will provide the support to integrate the interfaces developed in Task 2.5 and POLIMI will provide the support for data recording. SG will develop the voice processing system in Task 6.6. UMIL will bring in its competences in structuring social communities and in developing clients for the communities. PSC, SAS and MUNICIP will bring in the psychological, sociological and psychological view to obtain the most compliant implementation. ORU will bring in its expertise in designing functionalities mediated by Giraff robot. Description of work: The community is aimed at improving motivation and increase compliance of the elders. It will provide structured knowledge, offer a virtual space to meet, cooperate and compete with other patients. The community will also deliver to the elders additional information that can promote a healthy lifestyle like, for instance, controlled kitchen recipes associated to therapy support or diets. To make it a lively place, structured content will be inserted in the first year of project, and will be continuously updated throughout the life of the project. The community will be made available also to other people, outside the Ronohome2.0 elder enrolled inside the project. The community supports also the interaction with caregivers and with clinicians in particular, to which the physiological measurements, monitoring results will be delivered with possible warnings. The community will be hosted in the cloud of a service provider and it is conceived as a cloud service that provides the community functionalities and storage for the data. We will explore in this WP the use of voice analysis for early detection of FTD. The members of the virtual community around each elder will be established at the beginning of the experience to be engaged in the deliverable socio-sanitary actions. Further members can be added throughout the Robohome2.0 life. Task 6.1(M3-M18) Structuring the Virtual Community and management (BDIGITAL, UMIL, PCL, SAS, MUNICIP, KORIAN, ORU, UOP) Goal of this task is to provide a low level architecture of Virtual Community platform taking into account both functional and technical specifications identified previously in WP1 and WP2. An adequate client and server architecture will be designed using web services technology that will communicate through the ROBOHOME2.0 infrastructure. The interfaces defined in WP2 will be incorporated. It will be explored the possibility to use the open source software and technologies during the future implementation of such architecture within WP6. It could be one already used by BDIGITAL inside the FITREHAB and REWIRE projects: Apache Tomcat, Java programming language, Spring framework, jQuery, Apache Tiles among others. The architecture will be able also to support multi-playing. The output provided by this task will be used in subsequent development tasks of this WP and in WP4. Data bases on new generation, like MongoDB, Cassandra or Neo4j will be considered for storing data as they have recently emerged as particularly suitable for the efficient analysis of big data. Task 6.2(M7-M24) Data repository design and implementation (POLIMI, UMIL, BDIGITAL, KORIAN) The data collected by Robohome2.0, provided by transparent monitorings and activities will be stored inside the database designed in Task 6.1. The data will be transferred from the Giraff memory on a regular basis. This task will also design and build a repository of stories that can be narrated by the elders, related to a particular period of their life. This can be part of the memory activities but it has the very important impact on the elders that they can still feel important in the society [MORE COMMENTS FROM PCL]. On the other side, this can generate collective knowledge of close past of the elderly that would get otherwise lost. To this aim, an adequate infrastructure based on automatic voice recording and reply will be set-up. This way, a collective knowledge of our close past can be collected, that otherwise would go lost. Task 6.3(M6-M18) Services design and implementation (BDIGITAL, UMIL, GIRAFF, SAS, PCL, KORIAN, MUNIC) According to the community structure defined in Task 6.1, a set of services will be provided to be integrated within each component used by each different kind of user. Three community components will be developed in Robohome2.0: web application, smartphone application and Giraff-based application. Each component will provide its own list of services. Moreover, depending on the type of user, the services available in each component may also vary. Through these services the users involved within the community will be helped to stay in touch between them at all times, display the status of the sensors and send notifications. The portfolio of specific services provided by the Virtual Community will be defined in collaboration with clinical, psychological and sociological project partners (SAS, PCL, KORIAN, MUNIC). The set of services which will be intended to integrate within the ROBOHOME2.0 Virtual Community platform could include alerts sending, news diffusion, forum, videoconferencing, achievements and score, reputation, calendar, medical reminders, social information reminders, notifications, VoIP calls, recommendations, monitoring results, diet among others. The implementation of these types of services will be at the discretion of technical feasibility analyzed in WP2. The output of this task will be integrated Virtual Community components developed in Tasks 6.5 and 6.6. Task 6.4(M12-M24) SOA layer and Communications (BDIGITAL, UMIL, GIRAFF) The different Virtual Community devices such as Giraff robots, smartphones and personal computers will be connected through a Care Station. This station will be developed as a web application installed on a dedicated server, which will have access to the internet in order to accept, validate and send communication requests between Virtual Community components. The components involved within the Virtual Community will include the Care Station web application, smartphone applications and Giraff robot applications. Communications among them will be implemented using a service oriented architecture (SOA) developed with Open Software components. The issue of confidentiality will be analyzed to be guaranteed in all communications. The output of this task formed by communication layer design and implementation will be integrated in developments carried out in Tasks 6.5 and 6.6. Task 6.5(M12-M27) Applications for virtual community management and activities personalization (BDIGITAL, GIRAFF, POLIMI, UMIL, PSC, ORU, UOP) The Care Station claims to be the base station installed on a dedicated server as a web application. All the community services and communication layer will be based on a centralized web platform. Other components will interact with this station through communication layer defined in Task 6.4. Robohome2.0 community will resort to two devices more that will communicate with the Care Station providing the overall set of community services: - Smartphone – will be used by Informal Caregivers to be in touch with the people they care for and which have the ROBOHOME2.0 installed in their home. - Giraff robot – will be used by Elderly to be in touch with their Formal/Informal Caregivers and also with other elderly who are users of ROBOHOME. This station will provide different features depending on the user’s role that uses it. There will be three types of user roles defined within this application: - Formal caregivers – a specific GUI will be provided for this user role, a set of specific services will be provided for users who have this role. - Informal caregivers – a specific GUI will be provided for this user role; furthermore a specific smartphone application will be provided (see Task 6.6 which will be connected with Care Station. - Elders – for this type of users a different GUI will be provided (see Task 2.5) The GUI design provided in Task 2.5 will be used in this task. Full support to deliver graphical/video content of virtual community to Giraff monitor or through Giraff to the home TV (cf. Task 4.1) will be provided. Giraff APIs and plug-in support options will be explored. Task 6.6(M12-M27) Smartphone application (BDIGITAL, UMIL, SG, PCL, SAS) To provide better community accessibility and usability for informal caregivers a smartphone application will be developed within this task. In this way informal caregivers will have two alternatives to use the community, through the web application or through a smartphone application. In this way the mobility benefit of this device will be used, which will offer a better use of services such as “Contact-me button” or “Shopping list” or “Look for my glasses at home”. The smartphone application will integrate some of the services provided by the Care Station and moreover will offer other complementary services that are specific only to this application. Within the Task 6.5 the set of communications will be defined between Care Station and smartphone application. The smart phone will be used also transparent to the elder to profile his/her emotional state. The software library designed in Task 5.3 will be further developed so as to provide a powerful speech analysis app running on I-phone and android platforms. The time course of the pitch of the conversation will be carried out separately for each number called to avoid emotional bias and on aggregated data. To this aim, we will screen elders, who have developed FTD and who have some audio registrations that were collected before the illness started. Finally an application to call Giraff or its services (e.g. “Help”, “Search keys” or “Search glasses”) will be developed. Task 6.7(M13-M24) Self-organization of the community (UMIL, BDIGITAL, KORIAN, PCL, SAS) The community will allow also self-organize a network of social ties among users, defined by symmetric or asymmetric relationships and will allow deriving self-organized clusters. Such clusters will be characterized by activities and by other parameters that can be derived from the profile like interests, age, familiar status and so forth. These clusters will be used to refine patients social profile, to support social activities and to target knowledge delivery. Task 6.8(M13-M27) Functional and usability tests (BIDIGTAL, SAS, KORIAN, MUNICIP) The community and its components will be tested starting early in the project, when simple features and infrastructure will be built up to the end of development. Such tests will be organized for groups of users who will evaluate the usability and effectiveness of the functionalities from the early prototypes to the final system to verify that they match users expectations and needs.

Deliverables (brief description and month of delivery) D6.1 [R/OTHER, CO] Virtual Community design. Report on the initial virtual community design and implementation of the basic features. Description of the structure of services planned to be included in the final version of the platform Robohome2.0 will be described. Questionnaires to evaluate the design of community at the functional and usability level will be defined (M15, BDIGITAL) D6.2 [R, CO] Virtual community final design and implementation. The complete final design and architecture of the community will be presented as well as the full list of services along with their description and user manual. The implementation process as well as the technical specifications of the platform on which virtual community is based will be described (M24, BDIGITAL) D6.3 [OTHER, CO] Virtual community software package. The associated software of the virtual community will be packaged in this deliverable. The installation manual will be presented along with the code. (M24, BDIGITAL)

#### WP7 – Integration

| Work package number | 7 |  |  |  | Start date or starting event: |  |  |  |  |  |  | M13 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Work package title | Integration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Participant number | 1 | 2 | 3 | 4 |  | 5 | 6 | 7 | 8 | 9 | 10 |  | 11 | 12 | 13 |
| Participant short name | UMIL | ORU | GIRAFF | UOP |  | SXT | PCL | POLIMI | BDIGITAL | SAS | KORIAN |  | SG | UMA | MUNIC |
| Person-months per Participant | 8 | 1 | 8 | 1 |  | 7 | 0 | 4 | 8 | 0 | 1 |  | 0 | 6 | 0 |

Objectives: • To coordinate the integration of the modules developed in WP4, WP5, WP6 and WP7 into a complete first prototype of Robohome2.0 system; • To validate the functioning of the prototype.

Role of the partners: Integration will be carried out by partners who have developed the components under the lead of UMIL. BDIGITAL will supervise the integration of the community, POLIMI of the monitoring systems and assistance functionalities and UMIL of the activity center. GIRAFF will carry out extensive testing for validation. KORIAN will participate to the integration of the community to provide its view of final service provider and possible channel of commercialization of Robohome2.0. Description of work: After the design and optimization of all components of the system, the integration phase is very delicate and critical. The system integration represents the connection between technology and medical application. The assembly of every instrumentation requires not only the specific technical knowledge but also the knowledge of ergonomy and usability aspects especially when the device as to be deployed at home to a non-expert user. The development of preliminary prototypes will help to define the integration process step by step. Indeed, the extensive set of benchmark tests performed on each component and the results of these tests will be used as reference for the benchmark tests carried out during integration. Task 7.1(M7-M24) Communication development and testing (BDIGITAL, UMIL, GIRAFF, POLIMI, SXT, SG) This is a critical task for integration. In this task the communication between all Robohome2.0 components such as the game center, Giraff, the virtual community and the monitoring system will be developed and tested. This task will start early so as to shape the development of each Robohome2.0 component that deals with communication, maintaining a shared view of the system. The type of data, the possible links, the technological requirements (bandwidth, protocol, and transmission media) as well as the functional requirement (data anonimization, organization) will be taken into account. In particular, data confidentiality and safety will be a main concern in the design phase and will be properly addressed using OASIS web service security specifications (WS-Security protocol). Connection with specific community of interests or specific sites (e.g. ruzzle game site) will be provided. Task 7.2 (M18-M27) Integration and testing of the community services (BDIGITAL, UMIL, GIRAFF, KORIAN) All the services developed in the WP6 will be integrated in the whole Robohome2.0 platform. Suitable tests will be performed to evaluate the provided functionalities according to the user and technical specifications defined in the WP1 and WP2. Several communication tests will be performed with the purpose of ensuring the full integration of all components that are part of the community. Task 7.3 (M6-M27) Integration of monitoring newtworks and activity center (POLIMI, SG, SXT, GIRAFF, BDIGITAL, ORU, UMA) The third layer of Robohome2.0 will be integrated with Giraff platform in this Task. This comprehends networks for environment monitoring and physiological parameter sampling; activity center, transparent psycho-physical monitoring and activity center. The networks will be integrated in a middleware that will provide to the virtual caregiver the updated information on the required parameters. The most suitable standards will be identified and used to facilitate interoperability. All of the selected and developed devices will have most different transmission capabilities and cabling the entire house cannot be feasible. A structure based on WiFi transmission will be the most reasonable. A Hub, for instance based on a Raspberry microprocessor, that integrates all the sensors, manages them and communicate with the virtual caregiver, will be explored. We will proceed one component at a time proceeding in subsequent steps, from early prototypes to the full developed components. This is fundamental to early detect possible conflicts and software / hardware incompatibilities. Task 7.4 (M21-M27) System testing and validation (GIRAFF, BDIGITAL, UMIL, SG, SXT, KORIAN, UOP) Quantitative experiments and tests will be carried out according to the functional specifications set in WP1 and to the technical specifications set in WP2 over the whole platform. Within WP3, WP4, WP5 and WP6, a variety of particular technologies will be developed and adapted according to the requirements and the interfaces designed in WP2. In Task 7.4, all these elements are integrated into a working system. The whole Robohome2.0 system will be widely tested in a protected environments, represented by the living labs of ORU and SAS, to identify any bugs and/or functional limitations. An exhaustive testing at technical level will be performed before delivering the Robohome2.0 system for use and evaluation. Particular attention will be devoted to the characterization of the performance of the integrated system in terms of robustness, reliability, usability, and dependability. A specific focus will be paid to user safety. Furthermore, during integration of the Robohome2.0 system, consistency with international medical regulations and communication standards will be pursued by the Ethical Advisory Board.

Deliverables (brief description and month of delivery) D7.1 [R, PU] Description of the hardware and software infrastructure of Robohome2.0. Interfacing specifications and SW and HW specifications of the components and of the whole system will be reported in a comprehensive way (BDIGITAL, M24). D7.2 [R, PU] Report on functional tests on the final integrated platform (UMIL, M27) Results on functional tests developed in collaboration with the different groups of users will be extensively reported. D7.3 [OTHER, CO] Integrated SW / HW prototype to be used for the pilot (UMIL, M27).

#### WP8 – Robohome2.0 pilot

| Work package number | 8 |  |  |  | Start date or starting event: |  |  |  |  |  |  | M13 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Work package title | Robohome2.0 pilot |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Participant number | 1 | 2 | 3 | 4 |  | 5 | 6 | 7 | 8 | 9 | 10 |  | 11 | 12 | 13 |
| Participant short name | UMIL | ORU | GIRAFF | UOP |  | SXT | PCL | POLIMI | BDIGITAL | SAS | KORIAN |  | SG | UMA | MUNIC |
| Person-months per Participant |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Objectives To evaluate the Robohome2.0 technology in a real home setting, for the following aspects: • technical and implementation feasibility; • usability by the elder, the caregivers and the physicians; • efficacy in assisting the elder in everyday living, therapy compliance and stimulation;

Partners role: SAS will be the leader of pilot testing, WP8, for its extensive expertise in this field. SAS will collaborate intensively with PCL and MUNICIP in all the aspects of pilot testing. KORIAN and GIRAFF will be also be involved in those aspects more related to industrial exploitation like system usability and therapy compliance. The improvement in patient to doctor communication will be analyzed also with BDIGITAL that has accumulated expertise in this field working with applications devoted to real patients or through patients and elder communities. UMIL, POLIMI, BDIGITAL, UMA and ORU will contribute on information gathering on the use of the components and of the whole platform and they will tightly collaborate with the clinical partners, PCL, SAS, MUNICIP and KORIAN, with a “bi-directional translational research approach” to define objective evaluations outcomes on elder multi-dimensional status: psyho-physical, clinical and social profile and its evolution during the use of Robohome2.0. SAS and MUNICIP will start early testing the components in their living labs to provide early on-the-field back on usability and compliance of the device developed (Task 8.2). Description of work: Robohome2.0 will be used with at least 21 elders, selected by SAS, PCL and MUNICIP among the elders who meet inclusion criteria set in WP1. These will be interviewed for their possible enrollment. During the interview they will be asked to test the platform and to verify their interest and commitment to use it, and to start defining the specific needs (and relative objectives) of each elder. The patient is enrolled in the study following the rules of the reference hospital, upon receiving the ethical approval (Task 1.7). If the elder consents to participate, a Robohome2.0 system to his needs and lifestyle aims will be tailored with the help of GIRAFF, BDIGITAL, UMIL, POLIMI and SXT. After a few days he will be able to be briefly trained for a period that can be estimated from 1 to 3 days at home according to his deficits and needs. The system will be then installed at elder’s home by UMA for Spain, by GIRAFF for MUNICIP and by UMIL for PCL. In this pilot study not only the elder will be involved but also a network of social and health care providers, represented by relatives and/or non-family home caregivers, friends, GPs, geriatrists that will be connected through the virtual community of Robohome2.0 upon their consent. The clinical partners will be collect all the events associated to the pilot, like hazards, criticality, observations, suggestions that will be compiled into a comprehensive report. Elders will use Robohome2.0 for at least 3 months depending on the requirements defined in WP1. Instructions for use will be given to the elder and his caregivers at the time of set-up according to the modalities specified in WP1. The sample size of 21 elders is the number that can realistically be treated for the 9 months training period that can be allocated for the trials. Keeping in mind that our primary aim is to assess the technical feasibility and usability, we cannot provide a power-based sample size estimation. Nevertheless, 21 subjects with different pre-frailty characteristics will allow us to obtain a generalizable evaluation of feasibility. We will also focus on the safety of the technology, on the elder’s compliance and satisfaction with the technology, and on the customized objectives as defined in Task 1.6. In particular, we will have enough man months (21*3 = 63) to register adverse events if there are any caused by Robohome2.0 training, and to acquire a large set of feed-back on compliance, usability, effectiveness and flexibility of the system and of its components. Task 8.1(M13-M36) Behavioral analysis (UOP, SAS, PCL, MUNICIP, KORIAN, UMIL) In this task we will design experiments to evaluate interaction modalities with Giraff and its functionalities with a long run perspective. Long-term interaction and acceptance, matching perceived and actual ability, readability and responsiveness are among the factor that make the interaction with a robot successful. None of the above mentioned qualities can be considered in isolation: long-term interaction and acceptance, readability, responsiveness and matching of perceived and actual ability all impact on each other. As such it is impossible to develop one quality while neglecting the others. Our research and development on the HRI aspects will focus on incrementally improving these HRI qualities through implementing the latest insights in the field of HRI and field testing with naive users (Task 8.1). In particular, the choice of the open experimental scenarios and of controlled interaction experiments will consider (i) the quality and effectiveness of long-term interaction and acceptance of the robot, (ii) Matching of perceived and actual ability; (iii) feedback and readability of the interaction partners; (iv) responsiveness of the robot. For the qualitative and quantitative HRI behavioural analyses, in addition to video analyses of the human-robot interaction strategies, dialog transcripts and non-verbal behavior (gestures, gaze), questionnaire-based measurements will be collected after the experiment. This will be based on the scales on Trust, Likability and Source Credibility used by Rau et al. (2009) and the Bartneck et al. (2009) questionnaire to measure a range of HRI factors (Anthropomorphism, Animacy, Likeability, Perceived Intelligence, and Perceived Safety). The experimental interaction tasks will be based on the key scenarios identified in Section 1.3. Results will be used to refine the specifications, the components and the interfaces to maximize robot compliance with the elder. Main way of communication of the virtual caregiver will be through speech combined with simplified animation. Desired features can be the clarity of language exposure and pitch / characteristic of the voice reproduced by the virtual caregiver some variability and even surprise elements in the feed-back. We will also aim to provide to the elder some possibilities of personalization. Task 8.2(M13-M27) Early testing (ORU, MUNICIP, PCL, KORIAN, UMIL, SAS, UMA, POLIMI) ORU will set up the Robohome2.0 components at different stages of completeness produced in WP3, WP4, WP5 and WP6, in its living lab made available in Orebro and in the living lab made available by SAS, updating the components with major updates provided by the leaders of those WPs. This pre-prototype platform will be tested with different types of end users: therapists, clinicians, caregivers and elders themselves in collaboration with SAS, MUNICIP and PCL. This would allow to early identify criticalities in the interaction, compliance and usability and provide refinement of the specifications and of the final implementation. Task 8.3(M27-M36) Usability evaluation (SAS, PCL, MUNICIP, KORIAN, GIRAFF, UMIL, UOP, ORU) During and after the pilot trial all involved physicians, caregivers and other users will answer a standardized questionnaire on system usability. This will be possibly based on TAM approach and will look on several aspects: easiness of use, compliance, pleasantness, perceived usefulness, looking at the point of view of the different users. Particular care will be put on the adaptation mechanism and the evaluation of their suitability from the motivational and effectiveness point of view, as evaluated by the different users. PCL: to be reviewed according to WP1 Task 8.4(M25-M36) Quantitative evaluation (SAS, PCL, MUNICIP, UMIL, ORU, POLIMI, KORIAN) Given the number of elders studied and the time horizon of the project, the assessment of efficacy will remain preliminary. But, these preliminary data are necessary to design a future randomised controlled trials that will yield a valid assessment of efficacy. Efficacy here will be assessed with proper tests according to the specific main assistance goals with measures taken before and after entering the pilot. We will collect data on daily usage of monitoring, activity center, assistance and community by the elders and the other users. Usage will be regressed on several parameters related to elders like: clinical status, age and gender, physical and cognitive deficits, to gather preliminary knowledge on whether certain subgroups of elders can accept the system better than others. Information on technical failures, operation errors, system abuse and hours spent with implementation and instructions will be recorded. These data will be reported to and discussed with the other partners to further improve and refine the Robohome2.0 components. The data will also be used to derive a preliminary estimation of the cost of implementation. Task 8.5 (M13 - M36) Analysis and assessment on the improvement in therapy adherence and elder-doctor communication (PCL, SAS, BDIGITAL, MUNICIP, UOP) Health is a critical aspect limiting prolonged staying at home. Usual patient-doctor relationship mainly in Italy, Sweden and Spain takes place through ambulatory or hospital visits. This work will be based also on the outcome of WP1 on functional specifications and will elaborate and estimate possible models and methods to take full advantage of Robohome2.0 characteristics on: monitoring (pervasive psycho-physical monitoring and physiological monitoring as well and validated clinical tests), assistance (video-communication, assistance in therapy adherence, knowledge distribution through the community and education). The summary of this work will be contained in D8.3, that will contain also possible scenarios and metrics to evaluate mainly the increase in therapy compliance and patient doctor relationship. The evaluation would take into account the elder’s involvement his own lifestyle program, knowledge and management of deseases as well as the satisfaction of all Robohome2.0 users. This will be done through the use of specific questionnaires that will consider all the possible interactions between elder and clinicians, either directly through video-communication, or mediated by Robohome2.0 collected data (monitoring or activity results, physiological data trends and so forth). These questionnaires will be customized for each kind of actor, so that the relevant aspects of the communication process can be evaluated. In order to analyze the relation clinician-patient, a questionnaire that covers the main dimensions of such relation will be developed. These dimensions could include accessibility. acceptability level of elders and clinicians, elder adherence to the lifestyle program and to the therapy and usability level of the system. Other elements worthwhile to be considered will possibly emerge during the project and, in particular, from the early trials carried out in the living labs of SAS and MUNICIP. Further information on this issue will be obtained by means of the analysis of the usage data and patterns gathered from the information systems that make the platform up. Overall an improvement of at least 10% in the satisfaction of patient-doctor communication is expected, and we expect also to alleviate the feeling of patients and families to be left alone with their difficulties. Task 8.6 (M13-M36) Platform deployment modalities (PCL, SAS, MUNICIP, UMIL, POLIMI, KORIAN) A survey on the platform for remote elder assistance in Sweden, Spain and Italy will be carried out at project start with the aim of identifying critical points and actual practices. We will elaborate on this to provide possibly deployment schemes and critical issues that are expected. Deliverable D8.1 will serve as the basis for definining Robohome2.0 platform deployment modalities. Knowledge and expertise acquired through the project execution will be carefully analyzed in order to identify and describe the keys for success and failure of such a platform and methodology to overcome all the barriers. Form these data, the most appropriate model to seamlessly connect at home assistance to hospitals, GP and elder service providers networks, appropriate service settings needed to guarantee a realistic implementation, adjusted to the needs of the elders and the reality and possibilities of service providers, will be studied and a business plan defined on these data in Task 9.5. Feedbacks obtained from the pilot test study outcome will be used to creation of best practices, guidelines and policy recommendations for the successful deployment of such platforms within the national health systems of the EU zone. Our reasonable goal would be to prolong the period in which elders can stay safely at home, still monitored and supervised in a way that is transparent to them. Besides increasing their quality life, we expect to reduce the cost of the National Health Service of at least 10% in primary and secondary recoveries and clinical visits.

Deliverables (brief description and month of delivery) D8.2 [PU, R] Analysis of assistance platform available on the market and their deployment modalities (KORIAN, M24) D8.2 [CO, R] Refinement of functional and technical specifications (UMIL, M24) D8.3 [PU, R] Report on deployment modalities and patient-doctor communication improvement and therapy compliance with Robohome2.0 (PCL, M36) D8.4 [PU, R] Assessment of Robohome2.0 effectiveness, compliance, usability and reliability in assisting the elders at home (SAS, 36)

#### WP9 – Dissemination and exploitation

| Work package number | 9 |  |  |  | Start date or starting event: |  |  |  |  |  |  | M1 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Work package title | Dissemination and exploitation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Participant number | 1 | 2 | 3 | 4 |  | 5 | 6 | 7 | 8 | 9 | 10 |  | 11 | 12 | 13 |
| Participant short name | UMIL | ORU | GIRAFF | UOP |  | SXT | PCL | POLIMI | BDIGITAL | SAS | KORIAN |  | SG | UMA | MUNIC |
| Person-months per Participant |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Objectives - to disseminate project results to the relevant target groups; - to promote best practice and/or further exploitation; - to facilitate the up-take of ideas and results by the market; - to assess sustainability and harmonise links of Robohome2.0 with related European and international initiatives.

Partners role: UMIL, leader of this WP, will work in strict collaboration with POLIMI, head of the technical committee and PCL, head of the functional committee to identify best solutions and to promote dissemination among the clinical providers (hospitals, regional and national service providers, private service providers). All the other partners will contribute with suggestions and material for the different domains and to the different diffusion actions according to their specific expertise. UMIL will take care of the Web-site that will be set-up at start and will grow towards the whole project. Description of work: Main goal of this task is to ensure effective and wide spread diffusion of project results, channeling the diffusion of the different results to the proper audience to raise globally the perception of the new possibilities offered to the elder for assisted living through grounded results. The unique mix of the consortium, made of information technology experts, clinicians, caregivers, policy makers and companies allows the discussion and the presentation of the results in very different domains. Conventional channels like exhibitions, meetings, as well as non-conventional ones like LinkedIn, YouTube, Facebook, will be exploited to diffuse the project results. The communication Officer will be kept informed in due time of any diffusion activity.Main focus of the project is to improve elder care and the dissemination effort will be directed mainly in this direction. Health and Social service providers at different levels, private and public, will be contacted throughout the project to demonstrate the project results and receive a valuable feed-back. However the project is expected to have a strong outcome also in the ICT domain. The possible industrial exploitation modalities for the whole project results and for the single components will be monitored and discussed throughout the project. A right of first refusal will be granted to industrial partners of the consortium that will be privileged in taking advantage of the technology developed. To take into account all the possibility a use and dissemination plan will be prepared in the first year of the project (D9.1) and continuously updated until the end of the project (D9.2). Particular care will be put on active evaluation of the results. Indeed effective assistance at home raises a lot of hopes on elders and their caregivers and the consortium feels very much the responsibility of correctly managing these expectations. Although plenty data to support possible exploitation of such platform will be gathered, the project itself considers a small pilot study. Robohome2.0 will not rise frustrating hopes. The technology developed, the experimentation results and real possibilities will be honestly discussed with the different stakeholders, without any hype, but with a realistic shared evaluation. One modality is through a continous active evaluation of the pilot results. Fundamental for project exploitation will be the feed-back from the users that will come early to refine the functional and technical specifications and will fundamental to make a thorough assessment of the system. In this process, stakeholders, policy makers as well as patients associations and end-users advisory board will be heavily involved. To achieve this, workshops, smaller meetings and exchange visits will be organized. Robohome2.0 members and invited experts and stakeholder will come together to discuss how the developed system should be assessed and against what criteria increase in the duration and quality of life at home should be evaluated. The outcomes of the systematic review, of the workshops and of the results from WP9 will be used to produce recommendations, protocols and deployment modalities as well as of different scenarios in the assistance living context to which the system is most suitable. Task 9.1(M1-M36): Definition of a dissemination plan (UMIL, All partners) A dissemination plan will be designed by UMIL together with all partners during the first 6 months of the project, identifying the communication objectives, activities and tools for dissemination and distributing the work among project partners. It will be discussed during the Kick-off meeting. Updates of the dissemination plan will be provided at months 12, 24 and 36. Task 9.2(M1-M36): Creation and maintenance of the project website (UMIL) UMIL will take care of designing, populating, and publishing the project website within the first 3 months, aiming to outline the project aims, share technical information among partners, make the project deliverables and results available online, and activate a discussion forum for the scientific community interested in Robohome2.0. A restricted access section will give partners the opportunity to access drafts of documents and to provide input to the development process. This area will provide an interactive working space for partners will be implemented by means of co-operative working tools. Task 9.3: (M1-M35) Organization of a Workshop and of Presentations/Seminars (UMIL, All partners) Dissemination activities will be carried out by all partners throughout the whole project duration and include: a) information about the project and its aims to stakeholders; b) presentation of interim results and of the final ones in national and international specialized publication organs and peer-reviewed journals in the relevant areas; c) presentations of interim and final results at national and international conferences in the area, in the form of papers/posters; d) organisation of workshops, presentations and seminars to sustain awareness about the project and its results; e) a Final Workshop will take place at the end of the project (Month 36). Task 9.4(M1-M36): Participation in Trade Fairs and Exhibitions (UMIL, SXT, SG, KORIAN, GIRAFF, All partners) Robohome2.0 industrial partners will participate in relevant European and International Trade Fairs and Exhibitions held inside and outside Europe by hiring stands at which hands-on technology demonstrations will be held. An example and the relative number of potential events could be: - Ambient Assisted Living Forum (AAL) - International Conference Neurorehabilitation (ICNR) - IEEE RAS/EMBS Conference on Biomedical Robotics and Biomechatronics (BIOROB) - Association for the Advancement of Assistive Technology in Europe (AAATE) - International Conference on the Recent advances in Assistive Technology and Engineering (RAaTE) - International Medical Fair (MEDICA) - International Conference on Intelligent Robots and Systems (IROS) - International trade fair for those with special needs and those requiring care (REHACARE) - International Conference on Computers Helping People with Special Needs (ICCHP) - International Conference on Rehabilitation Engineering and Assistive Technology Society (RESNA) - International Conference on Technology and Persons with Disabilities (CSUN) - Japanese Conference on the Advancement of Assistive and Rehabilitation Technology (JCAART) - International Conference on e-Health Networking, Applications and Services (Healthcom) - International Conference on Pervasive Computing Technologies for Healthcare (PervasiveHealth) - International Symposium on Robot and Human Interactive Communication (RO-MAN) Moreover, all participants will attend European and International conferences and/or workshops to which Robohome2.0 achievements will be disseminated, such as AAL Forum, 2014, Bucharest, 9-12 September 2014. Task 9.5(M1-M36): Industrial exploitation of results (KORIAN, POLIMI, All partners) – months 1-36 An Exploitation plan is prepared during the project period and finalized at the end of the project. The plan will present how the partners involved in Robohoe2.0 intend to exploit the results of the research and development activities. The plan will take into account the different regions/countries and their specific features and priorities identifying actual and potential industrial and sales partners. Possible risks and hurdles which need to be tackled before starting the exploitation of project results will be identified and measured in order to minimise their impact and corrective actions will be recommended. Appropriate alliances for the deployment of project results will be investigated. Negotiations and contracting with potential industrial and commercial partners will be started as soon as possible. 9.6(M18-M36) Business plan (KORIAN, SXT, SG, GIRAFF, All partners) A business plan will be prepared for the end of the project substantiated with the data gathered during the pilot. We will summarize inside a business plan a set of possible business goals, the reasons they are believed attainable with the development of Robohome2.0, and the plan for reaching those goals. Financial and technological content will be highlighted as well as competitive advantage with respect to similar systems will be highlighted. Task 9.7(M1-M36): Management of collaboration with external organizations (UMIL, PCL, SAS, All partners) Robohome2.0 aims at a tight collaboration with external end-users. The objective of this task is to manage the collaboration with external organisations. PCL, a National center for Geriatry and SAS, the reference node for Socio-Health public services in Andalusia have developed a long term follow up and a continuous elder care assistance with screening of fraility [PCL and SAS may comment on this]. Due to this, they have the possibility to follow the elders in different stages of pre-fraility functional development and they will be able to maintain a strong connection with elders groups through GPs on the territory. Task 9.8(M1-M36): Cluster activities, development of strategic vision and synergies with other EC projects (UMIL, All partners) During the lifetime of the project, contributions to technical roadmaps and standardisation of modular, multi-modal pro-active assisted living will be analyzed and examined. It is foreseen to participate to Continua Health Alliance (CHA) and Assisted Ambient Living joint program (AAL). The first initiative is aimed at technology, linking consumers with interoperable, personalized health solutions that meet their lifestyle needs, the second initiative. The second initiative is aimed at function, and it networks business users and research around the theme of assisted living, providing also funding. Synergies with other projects of Horizon2020 will be explored, in order to make provisions to complement or adopt existing standard interfaces and network protocols, and components to favor interoperability and scalability. The goal would be to pursue the idea of Robohome2.0 experimental testing platform as a living lab in which novel components, especially targeted to environment monitoring and to taking physiological samples can be tested and integrated. Task 9.9(M2-M36): Scientific dissemination. (UMIL, SAS, PCL, ORU, UOP, POLIMI, UMA) Potential conferences relevant to the project content will be continually updated on the web-site and a web-based conference calendar to alert the relevant project partners to deadlines for submissions of papers and conference registrations. A minimum of 5 peer-reviewed journal articles and 8 publications on major conferences are expected. The results shown may increase the interest of the different research communities involved to invest into improving elder assistance levels. Coordination of the scientific dissemination will be carried out by UMIL. PCL will play the role of shaping the information related to the project for the National Health Providers and of producing the material adequate to diffuse, and sensibilize the Health Provider of the EC countries.

Deliverables (brief description and month of delivery) D9.1 [PU, DEC] Project Website (UMIL, M3) D9.2 [PU, DEC] Project leaflet, poster (UMIL, M6) D9.3 [CO, R] Preliminary exploitation and dissemination plan (UMIL, M12) D9.4 [CO, R] Refined exploitation and dissemination plan, with refined poster (UMIL, M24) D9.5 [CO, R] Final exploitation and dissemination plan, with final leaflet and poster (UMIL, M36)

#### WP10 – Management

| Work package number | 10 |  |  |  | Start date or starting event: |  |  |  |  |  |  | M1 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Work package title | Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Participant number | 1 | 2 | 3 | 4 |  | 5 | 6 | 7 | 8 | 9 | 10 |  | 11 | 12 | 13 |
| Participant short name | UMIL | ORU | GIRAFF | UOP |  | SXT | PCL | POLIMI | BDIGITAL | SAS | KORIAN |  | SG | UMA | MUNIC |
| Person-months per Participant | 11 | 1 | 1 | 1 |  | 1 | 1 | 2 | 1 | 1 | 1 |  | 0,5 | 1 | 1 |

Objectives: The WP aims to ensure that the project remains on track and to ensure a successful completion of the Robohome2.0 project providing administrative and scientific co-ordination This includes the following detailed objectives: Objectives of the scientific coordination are: - to manage the overall scientific and ethical activities of the project according to approved plans; - to monitor, track and control deviations due to progress, costs, financial and scheduling changes; - to ensure that the required reporting is prepared and delivered in a timely manner; - to implement an administration and communication infrastructure to establish a basis for efficient and easy communication within the project. Also to ensure that external communication (project website, dissemination and exploitation) is undertaken and controlled by the project management, to raise the proper level of expectation; without any hype, but with a realistic shared evaluation. - to perform a procedure for updating and revising the plans due to changes and new knowledge. - to communicate with the Commission, with the Consortium and with other project bodies; - overseeing science & society issues, related to research conducted within the project; - Promotion of gender equality in the project; - Risk Management Plan implementation; - Managing IPR issue. Objectives of the administrative-financial management are: - Overall financial, administrative and contractual management of the consortium, ensuring continuous and timely communication; - Obtaining financial statements of partners; - Managing the Consortium Agreement among the partners; - Organisational and logistic support for training activities, conferences, workshops and meetings.

Partners role: All partners are involved in this WP since each organisation has to provide the mandatory financial and administrative documents requested by the EC. UMIL will act as coordinator. All other partners will nominate a member in the PSC and will participate in steering the progress of work. Management will take advantage of a reserved area set-up in the Web-site installed and developed in WP9. UMIL will be in charge of IPR management. Description of work: The main objective of the project management work package is to ensure a successful completion of the Robohome2.0 project providing administrative and scientific co-ordination. This work package is aimed at scientific and strategic project management including project meetings, project internal reviews, strategic discussions and the technical coordination among partners. The basic aim of this WP is to keep the project correct dynamics by setting the appropriate mechanisms to achieve the objectives. It will work to ensure the successful completion of the project by interacting with all the other WPs, not only in terms of tasks and deadlines fulfillment but also in terms of quality of the results. Particular attention will be paid to the management of risks and issues and to their early detection with a pro-active attitude in solving them, already experimented in coordinating the projects FITREHAB and REWIRE. ## Task 10.1(M1-M36): Planning and scheduling. (UMIL, All partners) This task will provide accurate planning of different actions during the project’s lifetime. Activities that have to be performed in this task are: - form the PSC and the technical and functional committees. Install the internal EAB (UMIL, All partners). - providing inputs and needs for changes (All partners); - defining and checking consequences according to budget, scheduling and objectives UMIL); - communicating and arranging meetings (UMIL); - defining management meetings Agenda (All partners based on UMIL proposal); - collecting partners inputs on meeting Agenda (UMIL); - circulating meeting agenda and logistic information. Preparing minutes of each meeting (UMIL). - preparing updated plans for final approval in the Project Steering Committeee (PSC) (UMIL). This might include the request of amendments to the European Commission; in this case the involvement of the partners is distributed as follows: a) amendment requested for technical issues (UMIL and all partners); b) amendment requested for entrance or withdrawal of beneficiaries (UMIL and all partners); - communicating updated plans with the consortium members. Large use of IT-based communication platforms, like Skype, will be used to cut the costs and increase the responsiveness (UMIL). ## Task 10.2(M1-M36): Progress and costs reporting. (UMIL, All partners) Robohome2.0 brings together researchers from different institutes and different countries. In order to establish common operational procedures and taking into account the enlarged Robohome2.0 partnership, UMIL prepares written guidelines and operational instructions to be followed by the partners for carrying out their research activities, that have to be approved by the PSC. This task focuses on project’s reporting starting from the individual reports provided by the partners. Periodic reports for the EC are issued every 12 months and at project completion. The reports contain an overview of the activities undertaken during the period, a summary of the S&T results, a list of the deliverables published and of the milestones reached during the period, a description of the monitoring actions (measurement / evaluation / corrective actions) undertaken to assure adherence to the project workplan, the financial statements by each participant and their summary. Activities that have to be performed in this task are: - providing administrative/financial data and relative explanations requested for each reporting period: table including detailed explanation of the use of the resources for each partner, Form C and if applicable Certificate on Financial Statement. The procedure includes the preparation of draft documents and then once the EC approves the costs, signature of the Form C. (All partners) - providing customised templates for reporting to all concerned participants (cf. Task 1.1, UMIL); - assistance on the use of the on-line tools for the completion of the financial reporting, and on how to complete the templates and revision of their first draft documents (UMIL); - first control on the administrative/financial documents provided by partners (UMIL and All partners). Once the PC approves the financial report of each partner the latter can proceed with the final draft to be up-loaded in the on-line system (All partners); - maintaining a document repository for reporting (UMIL); - submitting on time reports deliverable, milestone reports and cost claims of the required quality (UMIL); - creating periodic reports (UMIL). The periodic report for each period, will regroup in one single report both the technical report and financial reporting. The latter will include also the Financial Statements and the Certificates. The final report will comprise a final publishable summary report, the plan for use and dissemination of foreground and a report covering the wider societal implications of the project, in the form of a questionnaire. UMIL as Coordinator is in charge and responsible to create the final version of reports. Task 10.3(M1-M36): Monitoring, control and quality management. Risk Management (UMIL, All partners) This task will ensure that approved plans are monitored and controlled. Progress control will be done at WP level by measuring resources and costs. Activities to be performed include: - research and development progress control (UMIL); - cost control (UMIL, All partners). In this context each partner prepares periodical estimates on expenditure from which UMIL will produce a lumped estimate. These figures will be discussed within PSC to evaluate possible deviations and correction actions. - checking schedules, deliverables and milestones (UMIL). - risk analysis (UMIL, All partners). Risk management is fundamental to keep the project on track and to tackle early any hazard in which the project might incur. Risk management addresses the monitoring of scientific/technical results, their dissemination/ exploitation and of the overall project coordination. It comprises the supervision of the project management performance and its assessment, change of procedures, if necessary, and monitoring of the impact of such changes on the overall project progress. Task 10.4(M1-M4): Set-up of the end-users advisory board and of the project committees (UMIL, All partners) Robohome2.0 consortium believes that a continuous, effective and reliable feed-back of users is fundamental for the project success. Beside the functional committee that will bring the end-users point of view, we aim also to have an external independent advice. To this aim, in the first stage of the project key figures for each type of end-users will be identified: informal caregivers: relatives, elders, formal care-givers: nurses, physiotherapists, Psychologists and clinicians, and ICT personnel. They will be invited to be part of an end-users advisory board. This will meet at M6 of the project with the PSC and, afterwards, at M12 M24 and M36. Their role will be a pro-active evaluation of the project and suggestions of improvements that will fully discussed with the PSC of Robohome2.0. Task 10.5(M1-M36) IPR management (UMIL, All partners) Knowledge developed in Robohome2.0 will be secured as early as possible by the consortium as a whole and each partner individually. PSC and single partners will evaluate which results are suitable to be patented and identify the best options to protect SW and HW aspects of the results; patenting will be the method of choice in most cases. A continuous patent survey throughout the project will ensure the priority to the IPR. UMIL will lead this task, with the contribution of the director of its TTO, with the role of scouting the solutions developed and secure the results as early as possible to avoid that early disclosure would make patenting not possible. A report will summarize the IPR activities and achieved patents at the end of the project (M36).

Deliverables (brief description and month of delivery) D10.1 [OTHER, PU] Set-up of the end-users advisory board (UMIL, M4) D10.2 [R, CO] Project management and quality plan. Report on ethical guidelines and regulations (UMIL, M6) D10.3 [R, CO] Periodic Report I (UMIL, M12) D10.4 [R, CO] Periodic Report II (UMIL, M24) D10.5 [R, CO] Periodic Report III (UMIL, M36) D10.6 [R, CO] Final Report (a public section is provided) (UMIL, M36).

### List of Workpackages

| Work package No | Work Package Title | Lead Participant No | Lead Participant Short Name | Person-Months | Start Month | End month |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Functional Specifications | 6 | PCL | 47 | 1 | 18 |
| 2 | Implementation requirements | 4 | UOP |  | 2 | 24 |
| 3 | Virtual caregiver and Service robot | 2 | ORU |  | 3 | 27 |
| 4 | Activity center | 1 | UMIL |  | 3 | 36 |
| 5 | Monitoring Systems | 7 | POLIMI |  | 3 | 27 |
| 6 | Virtual Community | 8 | BDIGITAL |  | 3 | 27 |
| 7 | Integration | 3 | GIRAFF |  | 10 | 27 |
| 8 | Robohome2.0 pilot | 9 | SAS |  | 13 | 36 |
| 9 | Dissemination and Exploitation | 1 | UMIL | 34,50 | 1 | 36 |
| 10 | Management | 1 | UMIL | 24,5 | 1 | 36 |
|  |  |  |  | Total months |  |  |

### List of major deliverables

| Deliverable (number) | Deliverable name | Work package number | Short name of lead participant | Type | Dissemination level | Delivery date |
| --- | --- | --- | --- | --- | --- | --- |
| 9.1 | Project Website | 9 | UMIL | DEC | PU | M3 |
| 10.1 | Set-up of the end-users advisory board | 10 | UMIL | OTHER | PU | M4 |
| 9.2 | Project leaflet, poster | 9 | UMIL | DEC | PU | M6 |
| 10.2 | Project management and quality plan. Report on ethical guidelines and regulations | 10 | UMIL | R | CO | M6 |
| 1.1 | Functional specifications | 1 | PCL | R | PU | M12 |
| 1.2 | Ethical submission | 1 | PCL | R | CO | M12 |
| 2.1 | Technical specifications | 2 | POLIMI | R | CO | M12 |
| 2.2 | HRI analysis and definition of robot-users interfacing modalities | 2 | UOP | R | CO | M12 |
| 2.4 | Design of testing the system and its components | 2 | POLIMI | R | CO | M12 |
| 3.1 | Methodology for profiling the elders and the functionalities and some real case scenarios | 3 | ORU | R | PU | M12 |
| 4.1 | A first nucleus of physical and cognitive games + silhouette tracking | 4 | UMIL | R/OTHER | CO | M12 |
| 5.1 | Design and development of the monitoring sub-networks; a first report will be provided | 5 | BDIGITAL | R | CO | M12 |
| 9.3 | Preliminary exploitation and dissemination plan | 9 | UMIL | R | CO | M12 |
| 10.3 | Periodic Report I | 10 | UMIL | R | CO | M12 |
| 6.1 | Virtual Community design and structure | 6 | BDIGITAL | R | CO | M15 |
| 1.3 | Final functional specifications | 1 | UMIL | R | PU | M18 |
| 4.2 | The full system for education | 4 | POLIMI | R/OTHER | CO | M18 |
| 5.2 | The full monitoring systems ready for usability testing | 5 | POLIMi | R | CO | M18 |
| 2.3 | GUI Design | 2 | UMIL | R/OTHER | CO | M24 |
| 3.2 | Improved navigation functionalities | 3 | UMA | R/OTHER | CO | M24 |
| 3.3 | The reasoning and recommendation system | 3 | ORU | R | PU | M24 |
| 3.4 | Tested prototype of everyday life assistance and therapy compliance | 3 | SXT | R/OTHER | CO | M24 |
| 6.2 | Virtual community final design and implementation | 6 | BDIGITAL | R | CO | M24 |
| 6.3 | Virtual community software package | 6 | BDIGITAL | OTHER | CO | M24 |
| 7.1 | Description of the hardware and software infrastructure of Robohome2.0. | 7 | BDIGITAL | R | PU | M24 |
| 8.1 | Analysis of assistance platform available on the market and their deployment modalities | 8 | KORIAN | R | PU | M24 |
| 8.2 | Refinement of functional and technical specifications | 8 | UMIL | R | CO | M24 |
| 9.4 | Refined exploitation and dissemination plan, with refined poster | 9 | UMIL | R | CO | M24 |
| 10.4 | Periodic Report II | 10 | UMIL | R | CO | M24 |
| 4.3 | The full smart activity center with the final reference manual, user manual and installation manual | 4 | UMIL | R/OTHER | CO | M27 |
| 5.3 | Validation of the clinical transparent clinical tests | 5 | POLIMI | R | PU | M27 |
| 5.4 | Report on the functional and usability tests of the monitoring systems | 5 | POLIMI | R | PU | M27 |
| 7.2 | Report on functional tests on the final integrated platform | 7 | UMIL | R | PU | M27 |
| 7.3 | Integrated SW / HW prototype to be used for the pilot | 7 | UMIL | OTHER | CO | M27 |
| 8.3 | Report on deployment modalities and patient-doctor communication improvement and therapy compliance with Robohome2.0 | 8 | PCL | R | PU | M36 |
| 8.4 | Assessment of Robohome2.0 effectiveness, compliance, usability and reliability in assisting the elders at home | 8 | SAS | R | PU | M36 |
| 9.5 | Final exploitation and dissemination plan, with final leaflet and poster | 9 | UMIL | R | CO | M36 |
| 10.5 | Periodic Report III | 10 | UMIL | R | CO | M36 |
| 10.6 | Final Report (a public section is provided) | 10 | UMIL | R | CO | M36 |

#### Effort per Task per partner

## Graphical presentation of the components and how they inter-relate (Pert chart)

Description.

Tight collaboration between WP3, WP4, WP5, WP6 will be guaranteed by PC that will keep track of the development in the different WPs through summaru of advancement in each WP. Feed-back from development will allow refining further Functional and technical specifications up to M18.

# 3.2 Management Structure and procedures

## 3.2.1 Organizational structure and the decision-making

When establishing the consortium, great attention was placed to fully cover the different aspects involved in Robohome2.0, by choosing partners capable of dealing as effectively as possible with their tasks. We found an enthusiastic feedback to the participation both to the consortium and to the advisory board.

The Management structure consists of:

- the Project Co-ordinator (PC) Nunzio Alberto Borghese from UMIL;

- the Project Steering Committee (PSC), formed by all partners, being the Principal Investigators (PIs) of the 13 partners. Each member of the PSC is entitled to nominate a substitute to attend any meeting when a member is unable to attend. The PSC will be the organ of the consortium entitled to make decisions.

Given the size of the consortium and the type of project, two committees will be formed, with the aim of making internal discussion easier. The first committee, the functional committee lead by PCL, will supervise the functional aspects of Robohome2.0, and it is constituted of PCL, MUNICIP, SAS, KORIAN, UOP and UMIL. The committees will discuss specific issues related to functional aspects and their implementation, coordinates relevant information and feed-back to the PC. The second committee, the technical committee led by POLIMI, is devoted to discuss technical aspects and their implementation. It will comprehend POLIMI, UMIL, ORU, GIRAFF, UOP, SXT, BDIGITAL, SG and UMA. Other partners will possibly adhere to the committees or to their initiatives.

The two committees will discuss specific issues, possibly keeping trace of the discussion, and they will report the conclusion to the PC. The PC will forward relevant information to all partners and, in case decisions have to be made, it will request a PSC meeting for final decision.

A committee specifically devoted to manage the Ethical issues will be set-up, the Ethical Advisory Board of the project, led by PCL. It will comprehend: PCL, MUNICIP, SAS and UMIL. It has the responsibility for monitoring the conformity of the project to the ethical standards, analyzing all the ethical issues of the project like data protection, privacy, approval of the draft of the proposal to the ethical committee (cf. Task 1.7), gender issues, proper level of communication.

The WP leaders are responsible to assure the successful completion of their relevant workpackages.

At every level, decisions will be made by consensus whenever possible, to keep the maximum collaborative atmosphere inside the consortium. If a major dispute arises (for example between partners), it will be referred to the PSC. A decision will be made by two-thirds majority. In the event of a deadlock, P1 will have the casting vote.

The REWIRE administrative headquarters will be located at UMIL premises in Milano. Concerning the suitability to the tasks of the participants, the Principal Investigators (PIs) of each partner have long experience in their fields of knowledge and they hold senior positions of responsibility within their own organisations.

The role of the PC is mainly a coordinating role, while that of the PSC is of decision maker. PC is responsible for:

- supervising and controlling the research programme, including control of research progress towards the milestones;

- representing the REWIRE Consortium in the communication with the EU;

- communicating and negotiating with the EC after approval of the PSC;

- distributing funds among partners;

- preparing common formats and templates to be used by the partners for reporting activity;

- collecting and preparing the mandatory reports and submitting them to the EU;

- managing ethical issues, in collaboration with the EAB;

- organizing, convening and participating in the PSC meetings.

- managing technological risks by identifying and classifying them and by putting them in contingency plans.

- performing detailed planning and co-ordination of the work, taking the responsibility for the completion and quality assurance of each WP;

- providing a trimestral update on project development;

The PSC will have the responsibility for making all the decisions in the project, among which:

- setting the scientific priorities, within the existing objectives and budget framework;

- maintaining and implementing the Consortium Agreement:

- discussing the most adequate potential solution to risks and, in case, implementing them;

- monitoring and reporting processes and results, based on deliverables accomplished;

- proposing and approving corrective actions, when any problems occur that might affect achievements or delay activities and deliverables, thus ensuring the adherence to the project timetable;

As Robohome2.0 is deeply concerned of end-users need, an End-Users Advisory Board will be set-up early in the project. This body will include high profile members in the following areas: informal caregivers: relatives, elders, formal care-givers: nurses, physiotherapists, Psychologists and clinicians, and ICT personnel. They will be chosen by the PSC already at the first Project Steering Committee (kick-off meeting), taking into account partners suggestions, match with Robohome2.0 aims and nationality. The EUAB will meet during the PSC meeting to discuss and advice about functions defined and their implementation and the components realized to guarantee maximum compliance.

Matters related to Confidentiality and IPR handling will be explicitly defined in the Consortium Agreement that will address the following points:

• IPR related to developed processes and technologies;

• Definition of business rules for the exploitation of result;

• Rules for the exploitation and use of Robohome2.0 IPR by the partners.

In particular, the following principles will be respected:

• Foreground shall be the property of the partner that developed the Foreground. When Foreground has been developed jointly by two or more partners, these partners shall agree procedures for the joint ownership of the Foreground.

• A participant may publish or allow the publication of data, on whatever medium, concerning knowledge it owns or knowledge it generated under work carried out within the project, provided that this does not affect the protection of that knowledge.

• Participants shall grant access rights to the other participants to pre-existing know how necessary for the execution of the project, on a royalty-free basis.

• All partners will specify the Background to which partners are granted access, together with a statement that all other Background is excluded from access. Partners’ background will be specified within Consortium Agreement to be issued before project’s beginning.

Some of the information generated during the development of Robohome2.0 system has to be considered as confidential. In this regard, partners will be asked to sign a non-disclosure agreement as a specific article of the consortium agreement. Each partner will evaluate the potential for patenting the foreground developed in the project and the PSC reserves the right to patent all or part of its results produced during the course of the project.

As far as HW/SW will be imported from other projects the IPR will be saved as agreed in the other

projects. The parties of the consortium will respect the individual IPRs. If, in the course of carrying out work on the project, a joint invention is made and more than one partner contributes to it, the participants concerned may jointly apply to obtain the relevant rights together. Each party has the right to exclude specific pre-existing know-how from the other participants’ access, as far as the restrictions are announced before the signature of the contract with the EC. Knowledge and pre-existing know-how shall be used only for the purposes for each partner’s access rights to it have been granted and only for so long as it is necessary for those purposes.

### List of milestones

| Milestone number | Milestone name | Related work package(s) | Estimated date | Means of verification |
| --- | --- | --- | --- | --- |
| 1 | Set-up of end-users advisory board | 9,10 | M4 | All members have provided written agreement |
| 2 | Functional description of Robohome2.0 | 1,2,9,10 | M12 | Document containing the complete platform technological and functional specification |
| 3 | Running prototypes of the components endowed with a limited set of functionalities | 3,4,5,6,9,10 | M18 | Tests report on running prototype of the components endowed with a limited set of functionalities. |
| 4 | Running components of Robohome2.0 | 3,4,5,6,9,10 | M24 | Functional and technological documentation of the components and their testing that show that the components implement the specifications in WP1 and WP2 and run flawless. |
| 5 | Running Robohome2.0 platform | 7,9,10 | M27 | Functional and technological documentation of field testing the whole Robohome2.0 platform, documenting that it runs flawless. |
| 6 | Final report | 8,9,10 | M36 | Report on applying Robohome2.0 to single elders at home Report on results obtained from the analysis of all the patients. |

## 3.2.2 Explain why the organizational structure and decision-making mechanisms are appropriate to the complexity and scale of the project

The management structure guarantees the proper and prompt implementation of activities, as indicated in the contract terms with the EU. The management structure and operational functions are similar to those adopted successfully for the Rewire project. From a functional point of view, management will deal with the following sub-processes:

1. implementation of the project’s components;

2. knowledge management & reporting.

The structure envisaged is functional to exploit these two sub-processes.

A brief description of the main objectives, activities and responsibilities associated with managing implementation is described in the following Table.

| Objectives | Activities & responsibilities |
| --- | --- |
| To establish common operational procedures | P1 develops common templates and forms to be used by each participant in order to document the project’s progress (both scientific and administrative/financial). For example: common format for all the project deliverables, cost statement forms, risk analysis templates, task activity evaluation forms, etc. Non-paper deliverables will be always completed by a short paper description of their contents and aims (Task 10.2). |
| To ensure integration of the different research teams | Meetings at the health providers sites will be organized early in the project to build a shared view of Robohome2.0, and of its aims. Trimestral updates on project progress will be provided to all partners. The PSC establishes the rules for the day-to-day activities of the different research groups and defines the proper tools and infrastructures for implementing the co-operation between the different research groups. The constitution of a functional and technical committee will help the discussion among homogenous groups of partners. |
| To prepare and agree on the IPR and access rights. To maintain the Consortium Agreement (CA) | The PSC agrees on IPR, exploitation rights of the projects results, common knowledge access rights, etc. The partners adhere to the CA. A careful analysis of the deriving IPR issues will be carried out by the PSC and the rules for the management of IPR are agreed within the Consortium and included in the CA. The CA will also regulate any previous know-how |
| To organise periodic meetings of the PSC | P1 takes care of the organisation of periodic meetings to verify the development of the various project components and tune further development. |
| To monitor the project financial status | Every period, each partner prepares a cost statement, which declares the sustained costs broken down by type of activity; a justification of its overall costs incurred, linking these costs to the resources deployed and to the activity performed during the period. Each partner transmits to P1 the information. P1 evaluates and agrees with the cost statements received. P1 is responsible to collect the information and prepare the financial report for the EC. In the reserved area of the website, resources tables will be shared for internal monitoring of the overall resources consumed. An open source tool, like dotProject.net, might be used. |
| To assure complete and timely reporting to EC | Every period P1 prepares a periodic report that contains an overview of the activities undertaken during the period; a summary of the S&T results achieved during the period; a list of the deliverables published and of the milestones reached during the period; a description of the actions carried out in the “Monitoring” process, i.e. the measurement / evaluation / corrective actions carried out to ensure adherence to the project workplan; a financial statements provided by each participant; a summary financial report. After the end of the project, P1 prepares a final report including a final publishable summary report and the DUP. The PSC will agree the above documents and P1 submits them to EU. |

The PSC will meet at the start of the project (kick-off meeting) and 2 times per year or on an ad hoc basis as requested. The meetings will normally be scheduled to rotate between the principal contractors’ home bases. Technical meeting will be scheduled for the project’s progress and needs. These will be organized typically by clusters of partners and open to all the others. A plenary review meeting will be held at M12, M24 and M36 with Project Officer and reviewers. Meetings will be organized at the clinical partners site in the early phase of the project.

Regarding management of knowledge, it is worth distinguishing between:

“internal” knowledge, i.e. consortium access to the information needed to carry out the research programme;

study on the best ways to diffuse the tools developed through the Robohome2.0 project;

spreading of knowledge toward the scientific and industrial community, i.e. enlargement of the researchers base and dissemination activity;

knowledge transfer to the EU, i.e. reporting activity;

intellectual protection provisions;

exploitation plan.

A brief description of the main objectives, activities and responsibilities associated with managing knowledge is described in the following Table.

| Objectives | Activities & responsibilities |
| --- | --- |
| To guarantee that information is available where and when it is needed. | The PSC defines and implements access rights provisions to the documentation and the results achieved during the project. Within these provisions, P1 is responsible for deciding what information is needed and for collecting it from the partners. P1 is then responsible for publishing these internal documents, deliverables and reports on an electronic workspace that can be used by each partner of the Consortium to download documents and run discussions. |
| To support the dissemination / exploitation of the project results | The PSC approves the dissemination activities defined within the WP9 “Dissemination/Exploitation. PSC is responsible for revising draft Exploitation plan (Task 9.1). P1 is responsible to ensure the full functionality the project web site. To this aim, the partners submit their contributions to P1 and P1 structures and spreads the information / reports / deliverables received from the partners. |
| To prepare and organize diffusion material. | Each deliverable will be analyzed and eventually edited to become suitable for diffusion through conventional (press-release, newsletters and so forth) and non conventional (LinkedIn, YouTube, Facebook, and so forth) channels. Given the comprehensive nature of the project, major deliverables associated to milestones could be grouped to provide chapters to be published in major books of the area. |
| To assure complete and timely information to EC of dissemination activities | P1 will inform in due time the Communication Officer of all the Communications and Dissemination activities (Press Releases, website launch, articles, etc.) to enable a proper relay of these activities within Europa, the eHealth newsletter, Healthtech Wire platform, etc. |

To maximize the effectiveness of the result a good balance between fast publishing the results (requested by the research institutions) and thorough evaluation of their  innovative potential and their suitability to be secured through a patent, have to be balanced. For this reason, partners will be required to submit to the PSC an early draft of any publication or document to be diffused so that its novelty impact can be evaluated in due time.

The consortium is built such that industrial partners in the project can exploit the results of the research. For this reason, a right of first refusal will be granted to industrial partners of the project. However, to avoid that other interesting opportunities are lost, a time limit will be defined for this option.

No conflicts of interests are expected to arise during the project. Anyway, the CA will cover conflict situations. The first objective to resolve a conflict would be to reach a consensus. However, if over a reasonable length of time the conflicting parties have fully described and defended their conflicting positions but without resolution, then in order to avoid deadlock in the project’s operational progress, the approval of a two-thirds majority of the partners will be considered conclusive. P1 will have the casting vote.

## 3.2.3 Describe how effective innovation management will be addressed in the management structure and work plan

We may elaborate of having users asking functionalities and ICT providing solution and that we can provide the most effective solution through this continuos bidirectional translational research approach. This might offer to realize components that maximize efficiency satisfying particular needs of end-users not evidentiated for instance in functional specifications but provided by end-user advisory boards or highlighted in early testing.

To be done

FROM EC: Innovation management is a process which requires an understanding of both market and technical problems, with a goal of successfully implementing appropriate creative ideas. A new or improved product, service or process is its typical output. It also allows a consortium to respond to an external or internal opportunity

## 3.2.4 Describe any critical risk, relating to project implementation

A continuous monitoring of possible risks emerging during project development will be carried out.The Consortium will ensure an internal control of the project development to early identify critical issues and operational bottlenecks. The proposed methodology is based on a three-stage approach, the Risk Identification, the Risk Assessment and the Mitigation Plans. First, all risks will be identified (cf. “Table on critical risks for the implementation”) and evaluated on a qualitative scale. After the first risk identification, all risks will be plotted into a risk analysis matrix (        Figure 1a). This will highlight the two parameters used to characterize each risk: the probability and its but also their possible impact on the project. These two parameters provide to the PC all the information needed for a risk prioritisation. Furthermore, the Critical Risks Matrix will provide a sound basis to highlight the most significant potential risks and lead to the development of corrective mitigation action planning. The risk mitigation planning four-stage process described in         Figure 1b guarantees that corrective actions are chosen after a meticulous analysis of alternative options. WP leaders will constantly monitor identified critical risks associated to their WP. The results of these risk mitigation actions will be implemented only upon the approval by the PSC.

Figure 1a: Example of Risk Assessment matrix.			     Figure 1b: Mitigation planning

### Table of critical risks for the implementation

| Description of risk | Work package(s) involved | Proposed risk-mitigation measures |
| --- | --- | --- |
| Technical risk: Robohome2.0 features do not match expectations of the end users. Probability low: WP1 is completely devoted to transfer users’ expectations and needs in specific requirement for Robohome2.0. Futhermore, the adoption of participatory design in the development of the single system modules allows a continuous matching of Robohome2.0 features to users expectations. The end-users advisory board will also help Robohome2.0 to avoid this. Impact high: the system will have little used. | 1, 8 | Additional resources will be allocated to designing tasks to better collect users expectations. Early checking through living lab experiments, will allow to include them in the second cycles of refinement (cf. Pert diagram) |
| Technical risk: The technologies used to implement Robohome2.0 prototypes are not the most suitable for the project purposes. Probability low: WP2 will allow chosing the best technological solutions to implement Robohome2.0 functions. Impact Medium: the system is modular and components can be substituted later in the final prototype. | 2, 8 | The architecture design is modular and flexible allowing an easy addition or substitution of technological components throughout the development project phase. |
| Technical risk: The developed system has limits in usability and accessibility. Probability Low: Usability and accessibility rules are taken in account in design and development phases, with specific behavioral testing (Task 3.4, Tasks 8.1 and 8.2). Impact Medium: limit in usability will allow use only to particular groups of users. | 3, 8 | A continuous feedback from the end users, starting from early pilot in living labs, and from the End-Users Advisory Board will allow modifications of the weak interfaces all along project development |
| Consortium risk: Divergence among partners on project direction Probability Low: Consortium agreement rules every conflict situation. The research of consensus is the first objective. Impact Medium: Goals of Robohome2.0 are clearly described in this document. No major deviations can take place. | All | PC will put a strong effort in finding a solution most suitable to all involved parties. After a reasonable amount of time has been allowed for illustration and defence of conflicting positions, in order to avoid deadlock in project operational progress, the approval of simple majority of Partners will be verified. |
| Management risk: Unexpected delays in project development. Probability Medium: Due to the high complexity of the project, a few components may not be realized within the expected time. Impact Medium: A delay in the project may take place. | 3, 4, 5, 6, 7 | Robohome2.0 management is structured to maintain a continuous monitoring on all administrative and technical aspects. In case criticalities in the development of a component are detected, re-evaluation of the task duration is carried out. This delay may be compensated by other tasks. Last resort would be to discuss with the PO project prolongation beyond M36 |
| Management risk: Risks related to the protection of involved users data. Probability Low: All data collected within Robohome2.0 project are anonymous and the project is carried out in compliance with the Directive 95/46/EC about data protection. Moreover the Ethical Advisor Board will supervise all the project activities. Impact High. | 8, 9 | Robohome2.0 clinical partners are well experienced and will monitor all along project’s life with regards to ethics and privacy issues. Respective Ethical Committees will be consulted and ethical approval requested before any experimentation involving patients. |
| Technical risk: We will not be able to fit inside one PC both the game engine, the video processing required for tracking and the interfaces to the monitoring systems. Risk very low. The highest computational load is on the game engine. UMIL has accumulated a large experience on its game engine, that runs in real-time on a wide range of computers, also less power than the Core i7 mounted on Giraff. Impact High. Latency in the graphics with respect to elder movements would destroy amusement that is one of the elements on which gamification is built | 4, 7 | In this situation we will consider either a new generation PC to be integrated inside Giraff or an embedded PC for acquisition and processing data from Kinect camera that communicates in real-time (e.g. via GigaEthernet network) with the PC on Giraff. |
| There will be not enough exer-games to cover the needs specified in WP1. Risk very low: Exer-games will be developed upon IGER system that has allowed developing a total of 17 exer-games for REWIRE in one year. Impact medium: The impact depends on the criticality of the exer-games that could not be implemented. | 4 | We will allocate extra-resources to exer-games development during the second year of the project. |
| Technical risk: We will not be able to find enough elders for the pilot study. Risk low: PCL, SAS and MUNICIP serve a very large number of elders every year [Figures of SAS, PCL and MUNICIP]. Impact medium: Pilot duration needs to be prolonged. | 8 | We will reconsider the conditions set to enroll the patients and possibly contact other centers / hospitals. |

# 3.3 Consortium as a whole

### 3.3.1 Describe the consortium (no need to describe individual members of the consortium that are described in a separate Section 4).

The Robohome2.0 consortium is composed of 13 partners from 5 European countries (Italy, Spain, United Kingdom, France and Sweden). It gathers experts from the technological sector (UMIL, ORU, GIRAFF, UOP, SXT, POLIMI, BDIGITAL, SG, UMA), the clinical, psychological and assistance sectors (PCL, SAS, MUNICIP), the public administration (SAS, MUNICIP) and a large service provider (KORIAN). It joins the big industry (KORIAN), the small industry (SXT, SG, GIRAFF), the universities (UMIL, UOP, POLIMI, UMA), a private research center (BDIGITAL). Indeed, the consortium includes all the different perspectives involved in the remote elder assistance.

The technological development is led by UMIL. Monitoring systems will be developed by POLIMI with the collaboration mainly of BDIGITAL and SG; the activity center will be developed by UMIL with the main collaboration with BDIGITAL for the infrastructures and with UOP and PCL for the design of the activities. The virtual therapist and the service robot will be developed by ORU, mainly supported by UMA for navigation, SX for voice command, by UOP for interfacing and by SXT for assistance. The community will be developed by BDIGITAL with the support of UMIL for self-organization of the community and UOP for interfaces. The activities will tightly coordinated by UMIL as they are strongly interconnected. For instance, activities will be used by the virtual caregiver for evaluation and can be carried out with instrumented objects developed for monitoring. A strong effort will be carried out to maintain a unitary view, with standardized software and hardware interfaces and functionalities, KOIRAN will strongly participate in this effort, bringing in its over view of the system. Technological development will be continuously supported by the end-user partners: MUNICIP, SAS and PCL. These will be mainly in charge of the design of the Robohome2.0 functionalities and the interfacing modalities. Technology assessment, policy elaboration and exploitation evaluation will be carried out by KORIAN supported by PCL, SAS and MUNICIP.

Looking at the specific competencies, a multidisciplinary project always needs a “link partner” expert in enhancing dialogue and collaboration among clinical and technological experts. This role is covered by UML who has covered this role successfully in the projects FITREHAB and REWIRE. POLIMI has large experience in designing miniaturized devices for the biomedical field and will tightly collaborate with SXT in developing instrumented objects. UOP will work in tight connection with SAS and PCL to realize interfacing modalities with Giraff that would make it most acceptable to elders. UMIL will take care of the Activity Center, with its expertise on gamification in the rehabilitation domain, BDIGITAL will make available to the consortium their wide expertise in the setup of virtual communities of citizens taking care of the Robohome2.0 social network design and management. SG and UMA will bring specific competences. SG will support the development of voice processing for voice commands and for profiling of phone conversation. UMA will provide advanced ecological navigation capabilities.

Two living labs will be set-up, one in Malaga at [SAS please add living lab] and one in Orebro [MUNICIP please add living lab] in which early testing will be carried out. Pilot tests will be organized in elder’s homes in Malaga (by SAS), in Orebro (by MUNICIP) and in Milano (by PCL). All the three entities have already been involved international projects and are reference centers in their country.

Looking at the dissemination of the results, all the academic partners are strongly committed to spread their research results while KORIAN will supervise the exploitation with the help of SXT, SG and GIRAFF. KORIAN is aiming to incorporate Robohome2.0 technology to enlarge its range of assistance services to the elder. SXT and SG are interested in developing innovative solutions in their specific domains and GIRAFF will be the natural node through which provide the technology to KORIAN.

### 3.3.2 Describe the industrial / commercial involvement in the project

To be completed

### 3.3.3 Resources to be committed

A table showing the number of person / months required

A table showing other direct costs for paticipants where those costs exceed 15% of the personnel costs.

To be completed

- Table 3.4a: 	Summary of staff effort

- Please indicate the number of person/months over the whole duration of the planned work, for each work package, for each participant. Identify the work-package leader for each WP by showing the relevant person-month figure in bold.

|  | WPn | WPn+1 | WPn+2 | Total Person/ Months per Participant |
| --- | --- | --- | --- | --- |
| Participant Number/Short Name |  |  |  |  |
| ParticipantNumber/ Short Name |  |  |  |  |
| Participant Number/ Short Name |  |  |  |  |
| Total Person/Months |  |  |  |  |

To be done

Table 3.4b:	‘Other direct cost’ items (travel, equipment, other goods and services, large research infrastructure)

Please complete the table below for each participant if the sum of the costs for’ travel’, ‘equipment’, and  ‘goods and services’ exceeds 15% of the personnel costs for that participant (according to the budget  table in section 3 of the proposal administrative forms).

| Participant Number/Short Name | Cost (€) | Justification |
| --- | --- | --- |
| Travel |  |  |
| Equipment |  |  |
| Other goods and services |  |  |
| Total |  |  |

To be done

Please complete the table below for all participants that would like to declare costs of large research infrastructure under Article 6.2 of the General Model Agreement, irrespective of the percentage of personnel costs. Please indicate (in the justification) if the beneficiary’s methodology for declaring the costs for large research infrastructure has already been positively assessed by the Commission.

| Participant Number/Short Name | Cost (€) | Justification |
| --- | --- | --- |
| Large research infrastructure |  |  |

To be done

# Abbreviations

AAL – Ambient Assisted living

ADL – Activity of Daily life

AI – Artificial Intelligence

CA – Consortium Agreement

CHA – Continuous Health Alliance

COPD - Chronic obstructive pulmonary disease

DB – DataBase

DoW – Description of Work

EAB – Ethical Advisory Board

EUAB – End-Users Advisory Board

EC – European Commission

FP7 – 7th FrameProgram

FTD – Fronto Temporal Dementia

GP – General Practitioner

GUI – Graphical User Inteface

HRI – Human Robot Interfaces

HW – Hardware

ICER – Incremental Cost Effectiveness Ratio

IGER – Intelligent Game Engine for Rehabilitation

IPR – Intellectual Property Right

IT – Information technology

NUI – Natural Users Interfaces

PC – Project Coordinator

PCL – Fondazione IRCCS Cà Granda Ospedale Maggiore Policlinico

PO – Project Officer

PSC – Project Steering Committee

QMCI - Quick Mild Cognitive Impairment score (test)

RFID – Radio Frequency Identification Device

RGB – RedGrenBlue, a digital color image code

TRL – Technology Readiness Level.

SMS – Short Message Service

SOA – Service Oriented Architecture

SQL – Structured Query Language

SXT – SXT srl

SW - Software

TUG – Timed Up and Go, test used for physical assessment

UML - Unified Modeling Language

VC – Virtual Caregiver

VCA – Virtual Caregiver Avatar

# Implementation Section – Notes by the EC

3.1	Work plan — Work packages, deliverables and milestones

Please provide the following:

- brief presentation of the overall structure of the work plan;

- timing of the different work packages and their components (Gantt chart or similar);

- detailed work description, i.e.:

  - a description of each work package (table 3.1a);

  - a list of work packages (table 3.1b);

  - a list of major deliverables (table 3.1c);

- graphical presentation of the components showing how they inter-relate (Pert chart or similar).

Give full details. Base your account on the logical structure of the project and the stages in which it is to be carried out. Include details of the resources to be allocated to each work package. The number of work packages should be proportionate to the scale and complexity of the project.

You should give enough detail in each work package to justify the proposed resources to be allocated and also quantified information so that progress can be monitored, including by the Commission.

You are advised to include a distinct work package on ‘management’ (see section 3.2) and to give due visibility in the work plan to ‘dissemination and exploitation’ and ‘communication activities’, either with distinct tasks or distinct work packages.

You will be required to include an updated (or confirmed) ‘plan for the dissemination and exploitation of results’ in both the periodic and final reports. (This does not apply to topics where a draft plan was not required.) This should include a record of activities related to dissemination and exploitation that have been undertaken and those still planned. A report of completed and planned communication activities will also be required.

If your project is taking part in the Pilot on Open Research Data, you must include a  'data management plan' as a distinct deliverable within the first 6 months of the project. A template for such a plan is given in the guidelines on data management in the H2020 Online Manual.  This deliverable will evolve during the lifetime of the project in order to present the status of the project's reflections on data management.

Definitions:

‘Work package’ means a major sub-division of the proposed project.

‘Deliverable’ means a distinct output of the project, meaningful in terms of the project's overall objectives and constituted by a report, a document, a technical diagram, a software etc.

‘Milestones’ means control points in the project that help to chart progress. Milestones may correspond to the completion of a key deliverable, allowing the next phase of the work to begin. They may also be needed at intermediary points so that, if problems have arisen, corrective measures can be taken. A milestone may be a critical decision point in the project where, for example, the consortium must decide which of several technologies to adopt for further development.

3.2	Management structure and procedures

- Describe the organisational structure and the decision-making ( including a list of milestones (table 3.2a))

- Explain why the organisational structure and decision-making mechanisms are appropriate to the complexity and scale of the project.

- Describe, where relevant, how effective innovation management will be addressed in the management structure and work plan.

Innovation management is a process which requires an understanding of both market and technical problems, with a goal of successfully implementing appropriate creative ideas. A new or improved product, service or process is its typical output. It also allows a consortium to respond to an external or internal opportunity.

  - Describe any critical risks, relating to project implementation, that the stated project's objectives may not be achieved. Detail any risk mitigation measures. Please provide a table with critical risks identified and mitigating actions (table 3.2b)

3.3	Consortium as a whole

The individual members of the consortium are described in a separate section 4. There is no need to repeat that information here.

- Describe the consortium. How will it match the project’s objectives? How do the members complement one another (and cover the value chain, where appropriate)? In what way does each of them contribute to the project? How will they be able to work effectively together?

- If applicable, describe the industrial/commercial involvement in the project to ensure exploitation of the results and explain why this is consistent with and will help to achieve the specific measures which are proposed for exploitation of the results of the project (see section 2.3).

- Other countries: If one or more of the participants requesting EU funding is based in a country that is not automatically eligible for such funding (entities from Member States of the EU, from Associated Countries and from one of the countries in the exhaustive list included in General Annex A of the work programme are automatically eligible for EU funding), explain why the participation of the entity in question is essential to carrying out the project

3.4	Resources to be committed

Please make sure the information in this section matches the costs as stated in the budget table in section 3 of the administrative proposal forms, and the number of person/months, shown in the detailed work package descriptions.

Please provide the following:

- a table showing number of person/months required (table 3.4a)

- a table showing ‘other direct costs’ (table 3.4b) for participants where those  costs exceed 15% of the personnel costs (according to the budget  table in section 3 of the administrative proposal forms)

Mainetti et al.

Pirovano et al.

A. Kristoffersson, S. Coradeschi, A. Loutfi, User-Centered Evaluation of Robotic Telepresence for an Elderly Population. 2nd International Workshop on Designing robotic artefacts with user- and experience-centred perspectives, Nordi-Chi, 2010.

UML, Unified Modelling Language, is a visual language for specifying, constructing, and documenting the design of systems and processes. It was approved by OMG as a standard in 1997. Grady Booch, James Rumbaugh, Ivar Jacobson: Unified Modeling Language User Guide, Addison-Wesley 1999.

Joseph D. Novak & Alberto J. Cañas (2006). "The Theory Underlying Concept Maps and How To Construct and Use Them", Institute for Human and Machine Cognition. Accessed 24 Nov 2008.

Fried LP, Walston J. Frailty and failure to thrive. In: Hazzard WR, Blass JP, Ettinger WH Jr, et al, eds. Principles of Geriatric Medicine and Gerontology. 5th edition. New York, NY: The McGraw-Hill Companies;2003;1487-1502

http://now.aapmr.org/med-rehab/geriatrics/Pages/Geriatric- Frailty.aspx

Tinetti ME. Performance-oriented assessment of mobility problems in elderly patients. JAGS 1986; 34: 119-126

Puthoff M. (2008) Outcome measures in cardiopulmonary physical therapy: SPPB. Cardiopulmonary Physical Therapy Journal. March 19 (1): 17-22

Guralnik JM, Ferrucci L, Simonsick EM et al. Lower-extremity function in persons over the age of 70 years as a predictor of subsequent disability. N Engl J Med 1995; 332: 556–61

Tinetti ME. Performance-oriented assessment of mobility problems in elderly patients. JAGS 1986; 34: 119-126

Puthoff M. (2008) Outcome measures in cardiopulmonary physical therapy: SPPB. Cardiopulmonary Physical Therapy Journal. March 19 (1): 17-22

Guralnik JM, Ferrucci L, Simonsick EM et al. Lower-extremity function in persons over the age of 70 years as a predictor of subsequent disability. N Engl J Med 1995; 332: 556–61

Action Plan on “Prevention and early diagnosis of frailty and functional decline, both physical and cognitive, in older people” of the European Innovation Partnership on Active and Healthy Ageing (Bruxelles, November 6, 2012)

Zimmerli

QUOTATION REQUIRED

F.D. Davis, "Perceived usefulness, perceived ease of use, and user acceptance of information technology", MIS Quarterly vol. 13, no. 3, pp. 319–340, 1989.

V. Venkatesh, M.G. Morris, G.B. Davis, and F.D. Davis, "User acceptance of information technology: Toward a unified view", MIS Quarterly, Vol. 27, No. 3, pp. 425–478, 2003

Hamilton BB, Granger CV, Sherwin FS et al. A uniform national data system for medical rehabilitation. In: Fuhrer MJ, editor. Rehabilitation Outcomes: analysis and measurement. Baltimore, MD: Brookes; 1987. pp. 137–47; Hall KM, Mann N, High WM et al. Functional measures after traumatic brain injury: ceiling effects of FIM, FIM+FAM, DRS and CIQ. J Head Trauma Rehabil. 1996; 11: 27–39; Turner-Stokes L, Nyein K, Turner-Stokes T et al. The UK FIM+FAM: development and evaluation. Clin Rehabil. 1999; 13: 277–87

http://www.z-wave.com/

L Constantine and H. Windl “Usage-Centered Design: Scalability and Integration with Software Engineering.” In C. Stephanidis and J. Jacko (Eds.) Human-Computer Interaction: Theory and Practice. Proceedings of the 10th International Conference on Human-Computer Interaction, Crete, Greece, 22-27 June 2003. Mahwah, New Jersey: Lawrence Erlbaum Associates, 2003. L.Constantine, . Software for Use: A Practical Guide to the Models and Methods of Usage-Centered Design, Addison-Wesley, 1st ed. 1999.

http://www.theage.com.au/news/entertainment/when-fantasy-is-just-too-close-for-comfort, The Age, June 10, 2007. Mori, Masahiro (1970). Bukimi no tani The uncanny valley (K. F. MacDorman & T. Minato, Trans.). Energy, 7(4), 33–35. (Originally in Japanese). 48 J. Seyama, R.S. Nagayama, The Uncanny Valley: Effect of Realism on the Impression of Artificial Human Faces, Presence, Vol. 16, No. 4, August 2007, 337–351, 2007

Cf. Also: Mainetti R, Sedda A, Ronchetti M, Bottini G, Borghese NA. (2013) Duckneglect: video-games based neglect rehabilitation. Technology and Health Care 21 97–111 97. DOI 10.3233/THC-120712 IOS Press.

Mataric

(Broz et al. 2013)

Kolawa, Adam; Huizinga, Dorota (2007). Automated Defect Prevention: Best Practices in Software Management. Wiley-IEEE Computer Society Press.

http://www.osgi.org/

http://tyromotion.com/en/products/tymo/overview

J.L. Blanco, J. Gonzalez-Jimenez, J.A. Fernandez-Madrigal, "Optimal Filtering for Non-Parametric Observation Models: Applications to Localization and SLAM", The International Journal of Robotics Research (IJRR), vol. 29, no. 14, 2010

J. Gonzalez-Jimenez, C. Galindo, F. Melendez-Fernandez, J.R. Ruiz-Sarmiento, "Building and Exploiting Maps in a Telepresence Robotic Application", 10th International Conference on Informatics in Control, Automation and Robotics (ICINCO), Reykjavic, Iceland, 2013

E. Vargiu, L. Ceccaroni, L. Subirats, S. Martin, and F. Miralles. User Profiling of People with Disabilities - A Proposal to Pervasively Assess Quality of Life.  In ICAART 2013 - Proceedings of the 5th International Conference on Agents and Artificial Intelligence, Volume 2, J. Filipe, A. L. N. Fred (Eds.) Barcelona, Spain, 15-18 February, 2013. SciTePress 2013.

https://www.sticknfind.com/, http://www.thetileapp.com

Pirovano et al.,

Berends, Johan H. and Veldhuis, Gerrit J. and Lambeck, Paul V. and Popma, Theo J.A. (1995) Device equivalence in integrated optics. Journal of Lightwave Technology, 13 (10). pp. 2082-2086. ISSN 0733-8724.

Chakravarti SN, Weaver R, Iper SSK, Hook T, Sierakowski A, Winstel K, Spieck J, Prakash DP, Tian X, Robson N, Wang H, Stillman W, Rice J, Flietner B, Jung L, Iyer SS. Device equivalence of logic performance in 0.18 μm and extension to 0.13 μm embedded DRAM technology Proc. VLSI Technology, Systems, and Applications, 2001, pp. 101-104.

http://www.wi-fi.org/wi-fi-certified-miracast%E2%84%A2

http://www.bing.com/dev/speech

http://projects.ict.usc.edu/mxr/faast/

Cf. Also: Mainetti R, Sedda A, Ronchetti M, Bottini G, Borghese NA. (2013) Duckneglect: video-games based neglect rehabilitation. Technology and Health Care 21 97–111 97. DOI 10.3233/THC-120712 IOS Press.

Mataric

LOD simplification; Campadell itoo

Cf. Also: Mainetti R, Sedda A, Ronchetti M, Bottini G, Borghese NA. (2013) Duckneglect: video-games based neglect rehabilitation. Technology and Health Care 21 97–111 97. DOI 10.3233/THC-120712 IOS Press.

Pirovano et al.,, 2013

Malik and Perona

M. Pirovano, R. Mainetti, E. Surer, P.L. Lanzi and N.A. Borghese Melding Exercises and Games to Design Effective and Sage Exergames for Rehabilitation, to be submitted.

Schell J. The Art of Game Design: Book of Lenses. Elsevier, (2008). Raph Koster. A Theory of Fun for Game Design (2004). Katie Salen, Eric ZImmerman -Rules of Play: Game Design Fundamentals (2003).

### Baer R., Morrison H., Microcomputer conolled game, US Patent application, US19770834643

http://en.wikipedia.org/wiki/Whac-A-Mole

Mainetti R, Sedda A, Ronchetti M, Bottini G, Borghese NA. (2013) Duckneglect: video-games based neglect rehabilitation. Technology and Health Care 21 97–111 97. DOI 10.3233/THC-120712 IOS Press

Foley JD, Van Dam A, Hughes JF, Feiner SK. Computer Graphics: Principles and Practice, 2nd edition, Addison-Wesley,

2011.

Frosio et al.

M. C. González, C. A. Hidalgo, A.-L. Barabási Understanding individual human mobility patterns. Nature 453, 779-782 (2008). Mark S. Handcock and Adrian E. Raftery Model-based clustering for social networks J. R. Statist. Soc. A (2007) 170, Part 2, pp. 301–354.

Takayama, L., Dooley, D. and Ju, W. (2011). Expressing thought: Improving robot readability with animation principles. Proceedings of the IEEE/ACM International Conference on Human-Robot Interaction.

NA Borghese, M Pirovano, PL Lanzi, S Wuest and ED de Bruin (2013), Computational Intelligence and Game Design for effective home-based stroke at Home Rehabilitation. Games for Health Journal. April 2013, Vol. 2, No. 2: 81-88.

Fasola and M.J. Mataric, Using Socially Assistive Human–Robot Interaction to Motivate Physical Exercise for Older Adults, Proceedings of the IEEE Vol. 100,No. 8, August 2012.

. Venkatesh, M.G. Morris, G.B. Davis, and F.D. Davis, "User acceptance of information technology: Toward a unified view", MIS Quarterly, Vol. 27, No. 3, pp. 425–478, 2003

http://www.continuaalliance.org/

http://www.aal-europe.eu/

Large research infrastructure means research infrastructure of a total value of at least EUR 20 million, for a beneficiary. More information and further guidance on the direct costing for the large research infrastructure is available in the H2020 Online Manual on the Participant Portal.

Certain actions under Horizon 2020 participate in the ‘Pilot on Open Research Data in Horizon 2020’. All other actions can participate on a voluntary basis to this pilot.  Further guidance is available in the H2020 Online Manual on the Participant Portal.