Call: H2020-PHC-2014-single-stage

Objective: PHC-19-2014: Advancing active and healthy ageing with ICT: service robotics within assisted living environments

Type of action: Research and innovation actions

- ROBOHOME2.0

Service ROBOt to monitor, assist and evaluate the elder at HOME

| Participant no. | Participant organization name | Short name | Country |
| --- | --- | --- | --- |
| 1 (coordinator) | Università degli Studi di Milano | UMIL | IT |
| 2 | Orebro University | ORU | SWE |
| 3 | Giraff Technologies AB | GIRAFF | SWE |
| 4 | University of Plymouth | UOP | UK |
| 5 | SXT Srl - Sistemi per Telemedicina | SXT srl | IT |
| 6 | Fondazione IRCCS Cà Granda Ospedale Maggiore Policlinico | Fondazione IRCCS Cà Granda Ospedale Maggiore Policlinico (PCL) | IT |
| 7 | Politecnico di Milano | POLIMI | IT |
| 8 | Fundació Privada Barcelona Digital Centre Tecnològic | BDIGITAL | ES |
| 9 | Servicio Andaluz de Salud | SAS | ES |
| 10 | Korian | KORIAN | FR |
| 11 | Signal GeneriX Ltd | SG | Cyprus |
| 12 | Unviersity of Malaga | UMA | ES |
| 13 | OREBRO Municipality | KOMMUN | SWE |

| Name of the coordinating person: | Nunzio Alberto Borghese |
| --- | --- |
| Tel: | +39.02-503.16373 |
| E-Mail: | alberto.borghese@unimi.it |

# Table of content

ROBOHOME2.0	1

Table of content	2

1. Excellence	4

1.1 Robohome2.0 General Objective	4

Specific Objectives	5

1.2 Relation to the workprogramme	7

1.3 Concept and approach	10

1.3.1 Overall concept	10

1.3.2 TRL analysis	13

1.3.3 Relationship with National and International Research and Innovation activities	14

1.3.4 Overall approach and methodology	15

Monitoring	15

Assistance	19

Activity Center	20

Service Robot and Virtual Caregiver	24

Human Robot Interfacing	26

Community of users	27

Deployment modalities.	28

1.3.5 Sex and/or gender analysis	29

1.4 Ambition	29

1.4.1 Beyond the state of the art	29

Service robot	29

Monitoring	29

Assistance	31

Activity center	31

Human Robot Interaction	33

Community of users	34

1.4.2 Innovation potential	34

Patent Search	34

2. Impact	35

2.1 Expected impacts	35

2.2 Measures to maximise impact	40

a) Dissemination and exploitation of results	40

b) Communication activities	44

3. Implementation	46

3.1 Work plan — Work packages, deliverables and milestones	46

3.1.1 Overall strategy and general description	46

3.1.2	Timing of work packages and their components (GANNT Chart)	47

3.1.3	Detailed work description	48

WP1 – Functional specifications	48

WP2 – Implementation requirements	51

WP3 – Virtual Caregiver and service robot	54

WP4 – Activity Center	57

WP5 – Monitoring Systems	60

WP6 – Virtual Community	62

WP7 – Integration	64

WP8 – Robohome2.0 pilot	65

WP9 – Dissemination and exploitation	67

WP10 – Management	69

List of Workpackages	72

List of major deliverables	73

Effort per Task per partner	75

3.1.4	Graphical presentation of the components and how they inter-relate (Pert chart)	76

3.2 Management Structure and procedures	76

3.2.1 Organizational structure and the decision-making	76

List of milestones	78

3.2.2 Explain why the organizational structure and decision-making mechanisms are appropriate to the complexity and scale of the project	78

3.2.3 Describe how effective innovation management will be addressed in the management structure and work plan	79

3.2.4 Describe any critical risk, relating to project implementation	80

Table of critical risks for the implementation	81

3.3 Consortium as a whole	82

3.3.1 Describe the consortium	82

3.3.2 Describe the industrial / commercial involvement in the project	83

3.4 Resources to be committed	83

3.4a Number of person / months required	83

3.4b ‘Other direct cost’	84

Abbreviations	85

# 1. Excellence

# 1.1 Robohome2.0 General Objective

In Europe, the share of people aged 65 years or over in the total population is projected to increase from 17.1% to 30.0%, going  from 84.6 million in 2008 to 151.5 million in 2060. Similarly the number of people aged 80 years or over is expected to almost triple from 21.8 million in 2008 to 61.4 million in 2060 and the availability of nurses is already becoming an issue in the US. Physical activity, cognitive stimulation, social inclusion, balanced diet, therapy adherence and regular clinical screening promote a lifestyle that slows down the decline, thus enabling the elder to live at his home healthier and for a longer time. This is becoming a priority in Europe as recognized by the EC community: managing frailty and functional decline through targeted interventions, enhancing participation and independence, and promoting systematic-routine screening for pre-frailty are among the specific objectives of the Action Plan on “Prevention and early diagnosis of frailty and functional decline, both physical and cognitive, in older people” of the European Innovation Partnership on Active and Healthy Ageing (Bruxelles, November 6, 2012). Several approaches have been proposed to address these aspects but a comprehensive solution is far to be provided. Moreover, a high emphasis is often put on wearable devices for monitoring that limit the compliance of the users, especially on the long run.

Robohome2.0 is an intelligent system, integrating an existing robotic platform with environmental sensors, and smart objects, advanced user interfaces, a virtual community and an activity center, to provide assistance, transparent monitoring and continuous clinical evaluation of the elder at home through a full-fledged, modular, personalized, and compliant approach.

Such high interactivity is remarked by “2.0” in the title of the proposal borrowed from Web2.0 concept. Indeed, ongoing robotics, smart objects and smart homes and Human Robotic Interfaces (HRI) research plays a key role in this panorama for matching increased life expectancy with the enhancement of the quality of life as people grow old. Robohome2.0 builds upon most recent results in these areas to realize a prototype, test it into real-life environment so to get the ambition to find its way to the market. To this aim,

Robohome2.0 will assemble off-the-shelf components in a robust and reliable way to get a low-cost hierarchical system that can be deployed massively at elders’ home.

Such system will provide several key aspects of clinical monitoring: a) Early cognitive and physical decline will be monitored by the robot observing and analyzing common everyday tasks (e.g. combing hair, preparing coffee), in cooperation with adequate sensorized objects, thus making the elder not aware of being monitored (transparent monitoring). b) Profiling of phone conversation will be done to identify meaningful changes in the emotional content associated to some degenerative diseases. c) Physiological samples (e.g. glucose level, pressure, oxygen saturation) will be provided by an adequate sensors’ network. d) A smart drug dispenser will provide to the elder the right pills at the right time thus largely increasing therapy adherence. e) Activities of Daily life (ADL) will also be monitored (e.g. number of hours of sleep that are related to hypnotic medicaments; home temperature that is associated to quantity of liquids to be taken, and so forth).

The robot will be able also to assist the elder in a confident independent living in finding lost crucial objects (e.g. the mobile phone, the TV remote control, the keys, …) inside the house and will give the elder feed-backs, recommendations and suggestion through a virtual caregiver avatar.

Robohome2.0 will support an active lifestyle recommending and guiding the elder through a personalized mix of physical, cognitive and social activities that are tailored to the adequate challenging level. We will fully explore gamification to maximize motivation, sustain attention, and train memory and we will explore automatic narration to provide long life engagement. These same concepts will be explored in educational games on the elder diseases and lifestyle.

Gamification will be explored also through the virtual community that will not only support competition / cooperation in physical and cognitive games but also provide support for social games like cards games so that the elder is incentivized to avoid isolation. The community will connect all people involved: caregivers, GPs, geriatrists and elders that will be able to exchange information and increase knowledge.

Activities, assistance, recommendations, monitoring, tuning will be managed by the robot through an embodied virtual caregiver, context aware, that will use the huge amount of heterogeneous data coming from sensors, community and activity center to refine its stimuli, to evaluate the elder’s status and the tune the profile.

To guarantee system use, maximum compliance with the elder is required. Particular care will be put in the design of interfacing modalities not only from the technological point of view, but also from the psychological one to foster the development of stable and positive bonds. A distributed voice command system will be explored to enable voice commands.

Giraff robot has been identified as the most suitable robot for Robohome2.0. Giraff is the result of progressive work in the domain of assisted living and its development was partly financed by the AAL “ExCITE” and FP7 “GiraffPlus” projects. It is basically a robotics base carrying a control PC and an adjustable touch-screen monitor, whose target price for massive production is below 1k Euros. Because of Giraff’s commercial potential it was awarded “Most Promising Innovation” of 2011 by the AAL organization. It has an open software architecture that allows to easily add functionalities as we will fully exploit in Robohome2.0.

## Specific Objectives

In particular, here are the specific Objectives of Robohome2.0:

      - To improve Giraff robot capabilities of interaction with the elder

- To design and implement interfacing modality that promote a good emotional relationship between the elder and Giraff robot.

- To monitor and prevent frailty, age-related cognitive and physical decline and social exclusion, a hands-off network of sensors to evaluate activities of daily living and behavior, transparent to the user.

- To develop a context-aware virtual caregiver able to profile the single elder’s interests and condition, suggesting motivated exercises and activities as well as providing formal and informal carevigers, relative and clinicians information specific to their role.

- To develop assistance in everyday tasks by the Giraff robot.

- To design and implement a personalized activity center system.

- To promote elders health education, self-empowerment, and increase their perceived usefulness in the society aiming at improving quality of life of the elders and of their formal and informal caregivers.

- To field test a complete ecosystem, involving all players, to gather evidence of Robohome2.0 benefits.

- To demonstrate the cost-effectiveness of technology and develop a proper business models for the technology transfer to massively deploy Robohome2.0 within a sustainable healthcare system.

To address these challenges Robohome2.0 will develop the following set of devoted technologies and methodologies aimed at creating an ecosystem to support prolonged life at home:

1. To improve Giraff robot capabilities of interaction with the elder. Giraff will be transformed from a teleoperated robotics platform into a robotic platform endowed with autonomy fully exploiting vision capabilities offered by adding a 3D camera, like Kinect. Such approach will make Giraff an active companion for the elder that can assist in finding objects, gives him/her advice, feed-backs and recommendations, monitors everyday tasks and carries around the activity center to allow the elder exercising in the best time and place (WP3, D3.2).

2. To design and implement interfacing modality that promote a good emotional relationship between the elder and the Giraff robot. A good relationship between Giraff and the elder is a very powerful mean to guarantee motivation in the interaction, easiness and even pleasure and to increase the compliance in system use. To reach this aim a constellation of activities and functions that will be carefully evaluated from the psychological point of view. Gamification, interaction modalities, unified GUIs and assistance in everyday life tasks will be part of this. We will exploit also several social intricacies in the interface with Giraff, like empathy, humour, references to mutual knowledge, continuity behaviors, politeness and trust. The information gathered by the sensors’network along with the inputs provided by the caregivers will be used by the virtual caregiver to create meaningful suggestions to the elder (WP2, WP3, D2.3, D3.3).

Scenario: Mike is wandering around at home, while Giraff, comes to him and says: “Today is the birthday of Matthew, your nephew, why don’t you call him?” Mike illuminates, and with a smile, he looks for his mobile phone to call Matthew. Unfortunately, he could not remember where he put it. He calls again Giraff and asks “where is my phone?”. Giraff activates the automatic location system, and after a while it moves towards the kitchen and takes a picture with its Kinect camera to the phone, partially showing under a box. Giraff sends a voice message to Mike, who can get the phone and calls Matthew. Mike is so grateful that he wants to kiss Giraff for this help… and Mathew too.

3 Monitoring the elder. Monitoring will be carried out while the elder executes the actions of everyday living. Instead of instrumenting the elder, we will instrument some of everyday life objects, like a tea cup, a comb, a fridge handle or other everyday use instruments, depending on elder’s habits. Instrumentation will provide wireless, real-time synchronous data on motion and handling pressure. We will sensorize also objects like a walking stick or a trolley, that are used to walk also outdoor, to evaluate the activity level and parameters for the stability of gait. We will combine vision provided by Giraff with information provided by all the sensorized objects to derive a “signature” of the movement. From these data we will define and validate indexes that will be made available to clinicians for elder evaluation. Transparent tests of clinical assessment of cognitive decline will be administered as spot questions or spot activities intermingled in the everyday tasks and games. We will also explore pitch analysis of phone conversations to early detect on-set of cognitive neurodegenerative diseases. Environmental sensors, e.g. measuring temperature, gas lost, humidity along with the gaming scores, and lifestyle monitoring will drive the virtual caregiver intelligence (WP5 and WP6, D5.1, D5.2, D5.3, D6.1).

4. To develop a context-aware intelligent virtual caregiver which realizes a closed-loop assistance system that cooperates with caregivers and clinicians. The virtual caregiver will analyze the huge amount of heterogeneous data provided by the pervasive monitoring systems and the activity center and a) suggests structured and unstructured physical, cognitive and social activities to the user, adapting the level of difficulty to the current elder’s status. b) tunes the estimated state of the elder according to data from the monitoring systems and the activity center and update his/her profile. c) provide the caregivers and the GPs with the relevant information on the elder status (WP3, D3.1, D3.3).

5. To develop assistance in everyday tasks by the Giraff robot. A key element to promote a solid bond between the robot and the elder is trust. One element that can help creating this bond is solving problems, even small, in everyday life. Loosing objects like keys, reading glasses or mobile phone is common and enabling Giraff to locate them for the elder can promote trustiness in the relationship. A novel system based on distributed microphones pairs with DSP processing capabilities will allow the elder to call Giraff, also when in a different room, realizing a distributed command system. Giraff will guide the elder in taking prescribed physiological measurements, like blood pressure or glucose, at the correct time intervals through video/animation instructions with voice explanation. A smart drug dispenser, built on miniaturized mechanics and electronics, will made available only right pills at the right time with alert signals remembering the therapy timing (WP3, D3.1, D3.4).

6 To design and implement a personalized activity center, based on the gamification paradigm and fully integrated with the robot and with the community of users. The service will provide cognitive and physical exer-games that can be played preferable with other peers through the virtual community. These games will be designed upon a set of exercises defined by the clinicians to specifically train declining functions. Social activities, like playing cards through the virtual community, will also be supported to promote socialization and avoid isolation that is often the first step towards depression (WP4, D4.3).

7. To promote elders education to a healthy lifestyle, self-empowerment, and increase their perceived usefulness in the society aiming at improving quality of life of the users and their formal and informal caregivers. The activity center will provide also exer-games to support elders education for healthy lifestyle, promoting knowledge and self-empowerment. The approach will be based on ontology automatic narration to define mini-games that can be casted into episodes, matched to pieces of knowledge on the diseases or lifestyle. We will explore how to combine this with stochastic models, like stochastic finite state machines to chain episodes into stories. Reinforcement learning will be explored to steer the story development towards themes tuned on the elder preferences. Popular containers like fairy tales, for which a clear structure has been proposed already at the beginning of last century, or sports competitions will be used. We will also implement a repository of real life stories recorded to Giraff from the elders themselves on a particular theme provided at regular intervals by the community manager (WP4, WP6, D4.2, D6.2).

8. To field test a complete ecosystem, involving all players, to gather evidence of Robohome2.0 benefits. The satisfaction of the end users is the “north star” in guiding the development of Robohome2.0. An end user advisory board will be set early in the project to help keeping the project on track representing the different players: geriatrists, GPs, caregivers, elders, political stakeholders, and service providers. The components and the system will be deployed in successive stages inside the living labs provided by ORU and SAS in order to test them, early on, in tight link with the developers (WP8, D8.4).

9. To demonstrate the cost-effectiveness of the technology and develop a proper business model for the technology transfer to massively deploy Robohome2.0 within a sustainable healthcare system. We envisage a business model based on service providing by a company like KORIAN (P10). This will be supported by an ICT service provider that provides the cloud that hosts the community and the data. Such system will integrate the components developed by the three industrial partners GIRAFF, SG and by SXT into a flexible, scalable and modular system that can be offered to the elders at home. Such model will be tested through experimentation. In particular, we will evaluate the actual market and available services and test how the different actors involved: from public to commercial entities, non-profit, philanthropic and other forms of social organization, can be involved. Costs and benefits will be made explicit, analyzing also hidden costs in the actual model. This model will regard the whole system as well as its constituents and will be carried out throughout the project development (WP9, D9.3, D9.4, D9.5).

# 1.2 Relation to the workprogramme

| Robohome2.0 Contribution | Milestone | PHC19 target outocomes |
| --- | --- | --- |
| Cognitive impairments, frailty and social exclusion will be addressed with a holistic approach is based on three main pillars: monitoring, assistance and evaluation that are not carried out in isolation, but are interleaved and provided at the users point of need. Data are gathered mainly in a transparent why, while the elder carries out the activities of everyday life. | 5 | Specific challenge: Citizens in an ageing European population are at greater risk of cognitive impairment, frailty and social exclusion. |
| Cognitive impairment will be addressed in a pro-active way, by proposing activities and exer-games that are negotiated with him/her and are adapted to the actual elder competences, status and psycho-physical condition. Cognitive tests of clinical validity will be administered to the elder in a transparent way through the activity centre. Early detection of cognitive degenerative diseases through audio analysis of phone conversation will be explored. | 3 | How Robohome2.0 will reduce the risk of cognitive impairment. |
| Robohome2.0 will stimulate the elder to an active lifestyle in which a personalized mix of cognitive, physical and social activities is suggested. Data from the activity center and monitoring systems are used to evaluate the current psycho-physical status. This allows Robohome2.0 identifying possible physical and cognitive decline. Specific validation of these decline indexes will be included into the project activities; they will be functional to a) adapting the system and the activities mix to the changing conditions of the user; b) follow up the user status keeping the carers informed and eventually favoring appropriate and timely interventions. Robohome2.0 will help the elder in therapy adherence in several ways: it provides home measurement of physiological parameters, it increases elder’s awareness on lifestyle importance through game based education and it provides a smart drug dispenser. | 3 | How Robohome2.0 will reduce the risk of frailty. |
| Robohome2.0 will set-up a community of users that will self-organize to propose connection with elders with similar profiles. The community will support multiplayer gaming and activities to promote socialization. It will also be the place inside which to exchange experiences and knowledge. Robohome2.0 intelligence will make simple suggestions to the users including solicitation to stay in touch with relatives, friends, etc., following the specific setting of the single user. A profiling of social activities through log book and phone conversation analysis will be carried out. | 3 | How Robohome2.0 will reduce the risk of social exclusion. |
| Robohome2.0 will push the elder keeping active with an everyday cognitive and physical training, properly calibrated on the single user’s requirements, assuring rewarding experience and confidence of the subject with her/his capabilities. Robohome2.0 will help the elder in some simple but basic tasks related to independent living such as finding the keys, reading glasses and mobile phone, remembering meals, meetings, drugs to assure prescription adherence and assists him/her with the diet. Specific supervision of physiological parameters (e.g. blood pressure, heart beat, glucose level, oxygen saturation) will be included into the Robohome2.0 system so to alert critical situations, thus allowing anticipated discharge from the hospital and limiting the risks of relapses. Robohome2.0 will communicate the alarm directly to the adequate caregiver. | 3 | with considerable negative consequences for their independence, |
| The carers will be helped in the care practice by daily monitoring information. An increased participation to elder life through the community will allow providing recommendations and informations. Audio-video connection will help in keeping a strong bond also when being physically present is not possible. | 4 | quality of life, that of those who care for them… |
| The progress of the physical decline of elderly people sometimes is abrupt, such as in case of dramatic events (stroke, falls, psychological traumas) but sometimes it is a slow progress which might be even neglected by the relatives. The lack of recognition of worsening could provoke delayed interventions which amplify the decline itself, inducing a negative loop which impacts on the requests to the health and care system. Transparent monitoring inside Robohome2.0 allows to objectively assess cognitive and physical decline continuously over time. Robohome2.0 will communicate periodic reports to the GP, so to allow prompt and tuned intervention in case of worsening conditions. Robohome2.0 will allow private partners, like KORIAN, to provide an effective continuity of care and assistance with public bodies. A business plan will be elaborated on this, substantiated by project results. | 4 | and for the sustainability of health and care systems. |
| Hereafter, an analysis of the crucial ingredients of the aim of the call with respect to the Robohome2.0 proposal is detailed. Service robotics: Robohome2.0 is based on a commercial off-the shelf service robot (Giraff), which will be enriched with adequate features. Transparent Monitoring system: we will monitor the elder through the use of everyday objects without requiring that he/she wears any device or does any particular action. Activity centre: it is based on gamification and provides a customized mix of activities with the adequate level of challenge involving also the community of users. Assisted living environment: proper sensors to monitor the home and elder’s behavior and smart assistance systems will be integrated into Robohome2.0 . | 5 | The challenge is to develop new breakthroughs for active and assisted living based on advanced ICT solutions. |
| Core of the system is Giraff robot that embodies an intelligent virtual caregiver. It monitors him/her through a monitoring network embedded in the house and in cooperation with sensorized objects of everyday use, thus achieving a monitoring completely transparent to him/her. It advices him/her and suggests tailored activities and looks for lost objects. | 3 | Proposals should focus on service robotics in assisted living environments which can help an ageing population to remain active and independent for longer. |
| - behavioural disciplines: to develop emotional bonds with a new body in the house, like a service robot, is fundamental for acceptance and a good interaction. Therefore interfacing functionalities and interface design will be inspired by this. UOP and PCL have complementary expertise. UOP has a strong background on Human Robot Interaction and PCL has a strong background in elder psychology and cognitive functioning. They will contribute to functional design and testing of the components and the whole system to maximize user acceptance. - social disciplines: social scientists from KOMMUN and PCL will assure both in the design of the virtual community and in the evaluation phases that the project has a positive impact both on the social inclusion of the user and on the caregivers (including the family, the carers, the family doctor, the clinicians involved in the care as well as the society, in more extended sense). - health disciplines: regular physiological sampling and clinical assessment and smart drug dispenser provide clinical monitoring and compliance. This will be complemented with providing structured knowledge and education through gamification. Three teams of clinicians (PCL, SAS and KOMMUN) with complementary specializations (GP and geriatrist) and a group of bioengineers (POLIMI) will collaborate in the project to design, develop and validate tests, of clinical validity, based on the analysis of ordinary life actions to assess the physical and cognitive status of the elder. | 4 | The project should combine multi-disciplinary research involving behavioural, sociological, health and other relevant disciplines. |
| Indeed, Robohome2.0 will be built with modularity and flexibility in mind both at the hardware and software level. Environment monitoring will be built upon scalable protocols, like z-wave, already diffused in the domotic field. Sensorized objects will be built integrating a transmission module based on most diffused wireless transmission protocols. The activity centrecentre will allow providing a mix of exer-games specifically tailored to the user and to adapt automatically the level of difficulty to the current user ability. The system will be managed by the virtual caregiver that will implement deductive reasoning on the data received from the monitoring systems, the activity centrecentre and the community and the inputs from the caregivers and the GPS all organized inside the frame of an ontology. The use of off-the-shelf components and standardization, and the integration of already developed sensors and physiological measuring devices, will allow to realize a cost-effective system and meet the widest range of functional requirements. | 4 | Characteristics of the solutions developed should be their modularity, cost-effectiveness, reliability, flexibility in being able to meet a range of needs and societal expectations, |
| Robohome2.0 will be tested from early on in specific living labs identified in Sweden and Spain. This will be fundamental to develop a system that can be really acceptable and compliant with the end users and the elders in particular. The pilot test in WP8 allows evaluating the compliance and suitability of Robohome2.0 also in real apartments inside which elder lives, as well as the safety of the technology. An end users advisory board will be set in the first months of the project with the aim of having an external highly qualified feed-back on project development, from the representatives of all the types of Robohome2.0 users. | 4 | applicability to realistic settings, safety and acceptability to end-users. |
| The activities proposed will be designed having gender in mind, realizing games episodes inspired to at least two themes, one most suitable for female and one for male attitude. Similarly, the avatar of the virtual therapist and all the elements that are gender sensitive, will be designed such that a configuration in the male and female version would be possible. | 2 | Gender and ethical issues should be paid due attention. |

# 1.3 Concept and approach

## 1.3.1 Overall concept

Robohome2.0 builds upon the successful EC funded projects Excites and Giraff plus, coordinated by ORU and FITREHAB and REWIRE, coordinated by UMIL. Robohome2.0 is a hierarchical platform aimed at supporting the elder at home, for a prolonged time, monitoring him/her and guiding him/her to a healthy lifestyle. It consist of three hierarchical levels (Figure 1): 1) a Core layer constituted of an intelligent virtual caregiver that provides feed-back and recommendations to the elder suitable to his/her state and to the lifestyle negotiated with his/her caregivers, embodied into a service robot that provides assistance. 2) a service layer that includes a distributed pervasive monitoring system, transparent to the elder that provides quantitative information on early physical / cognitive decline and social attitude, and an activity center that guides the elder in activities, tailored to elder idiosyncrasies and needs and implemented through gamification, to stimulate maximum adherence and motivation. 3) a Community of users connecting elders and other actors, aimed at improving socialization and knowledge.

1) The virtual caregiver will receive a wealth of heterogeneous information from monitoring systems, community and activity center. It will use an ontology based system to categorize them and propose an effective mix of activities with the proper level of challenge, tailored to the elder status. Further tuning will be carried out by the activity center on the basis of the elder actual performance in the activities themselves. It will help the elder to adhere to therapy prescription by means of a cooperative smart drug dispenser. It will also assist the elder with audio-video instructions and digital animation in taking physiological samples through a set of adequate devices or applications. Welcome messages, controlled randomized sentences of common use, feed-backs from monitoring, recommendations will all be provided throughout the day to the elder through the caregiver avatar, using real-time synthesized speech, for instance using Google APIs. The virtual caregiver will also analyze the historical data on physiological monitoring and psycho-physical assessment, that will be used to identify trends and oscillations and possible warnings related to anomalous values will be automatically generated and transmitted to GPs and caregivers. An initial profile of the elder characteristics, idiosyncrasies and needs is carried out before installing the system at home. A given lifestyle, clinical and diet regimen is defined between the elder and his/her caregivers. This information will be organized into structured knowledge through an adequate ontology that will be used by Description Language to provide recommendations, set-up monitoring parameters (e.g. critical thresholds) and tune the mix of activities.

Giraff robot will be enhanced providing autonomous navigation capabilities. Giraff will be able to reach the elder upon being called, to search for a lost object upon request, to answer for help, to fetch the elder to monitor him/her or to carry the activity center at hands. Interfacing modalities with Giraff will be carefully designed and implemented to favor the establishment of stable and positive bonds. To this aim, an innovative voice command system will be designed and implemented to enable the elder to call Giraff from any room in the house. This is particularly useful when help is needed. Algorithms to compute a navigation path and velocity profile that would produce the best approach to the elder will be identified.

Figure 1 .- The hierarchical structure of Rohohome2.0. The core layer is constituted of the Virtual Caregiver embodied in the Giraff robot and it is displaced at the elders’ home with the service layer. The latter is a modular layer that provides monitoring data to the virtual cargiver and offers functionalities to the elder: activity center, knowledge and assistance. The elder, his/her caregivers and the clinicians are all part of a community of user that promotes socialization and knowledge.

2) The service layer contains the monitoring systems and the activity center. Environmental monitoring will be obtained integrating off-the-shelf devices into a sensorized home network to transfer the data to the virtual caregiver. Low-power devices and standard protocols, like Z-wave specifically developed for this, will be implemented. Elder psycho-physical monitoring will be carried out through an innovative solution transparent to the elder based on task based psychophysical status assessment. This will be based on assessing typical everyday life tasks over time, like for instance, combing in the bathroom or preparing a coffee in the morning, or simply walking with the help of the walking stick. We will sensorize these objects with miniaturized micro-architectures that sense pressure and movement and transmit them through Bluetooth connection to a receiver inside Giraff PC. Objects sensors and information acquired by Giraff’s camera will be synchronized and acquired in real-time to derive a description of the task in terms of pressure and movement temporal profile, that constitutes a "signature" of the interaction with the object in that everyday tasks. The motion pattern will be compared over time to derive quantitative parameters associated to the performance, providing motion degradation indexes. We will investigate which indexes can provide clinical assessment.

The activity center suggests and provides to the elder physical, cognitive exercises and supports social activity. Physical and cognitive exercises will be guided by video-games: the elder sees him/herself on the TVdisplay in the form of an avatar moving and interacting with a virtual scenario with his/her movements tracked in real-time. We will fully explore a novel concept of technology equivalence for which the most suitable device available will be used, allowing the elder choosing not only the best time in the day to exercise but also the best place.

A full layer of gamification will be built on the top of the different exer-games to promote socialization and to make games long lasting. This will be based on automatically building a story, made of episodes matched to the exer-games, on top of the exercises exploring novel automatic narration techniques combined with stochastical models. This gamification layer will provide episodes aimed to educate the elder on lifestyle and therapy.

3) The virtual community of users, will act as a bridge towards other elders and with relatives, caregivers and clinicians. Audio-video communication will be fully supported to enrich the interaction: exploiting technological equivalence, the elder will be able to communicate through Giraff display, home TV or smart phone. This will largely increase the use of the system, improve patient to doctor communication and promote socialization.

Scenario. Mary is sitting on the sofa and Giraff notices through the remote control that she is changing the TV program often. Giraff remembers to Mary that it is the birthday of her nephew and that he is having a party with his school-mates. It asks Mary if she wants to participate to the party virtually. Mary is dubious, but Giraff files the request to Joseph through smart phone and he is very happy to involve Mary virtually in the party. Robohome2.0 quickly sets a streaming bi-directional video connection through the smart phone of Joseph, directly to the TV of Mary, who is extremely happy to join in singing the birthday song with all.

Moreover, a set of specific services tailored to the elders will be designed and deployed within the community of users. These services will be oriented to foster motivation and adherence to the proposed solution. These services will leverage on gamification by publishing the activity performance of the elders to promote cooperation and competition that reinforce motivation. The communication services will also be deployed to encourage and improve the socialization between the elder people and other community users. Moreover, it provides connection with the other elders. We will implement algorithms based on the analysis of relationships inside the community to automatically identify groups of elders that may share the same interests and have a similar status. These clusters can also be used to refine patients profiling. The community will also be a source of collective knowledge that can be increased by all users through the exchange of information among them. Such knowledge will have a multi-media format and involve all the aspects of the elder life: therapies, illness, psychological issues, social issues.

Scenario. Robohome2.0 proposes as month theme, “the political changes in Spain, after King Juan Carlos in 1978 restored democracy in Spain”. A lot of stories were recorded and sent to the community and the story of Francisco, who entered in politics that days to serve its city, Seville, was prized the best by the community members and made public on the Robohome2.0 community site. A journalist of “El Pais” discovered it, interviewed Francisco and wrote together a small book on the organization of elections and the first steps of political parties in that period, in Seville. The book was a large seller one.

These three components will not work as stand alone but they will cooperate, under the supervision of the Virtual Caregiver, to provide key functionalities: a) regular clinical monitoring to control physiological parameters critical for the elder’s diseases, b) cognitive and physical assessment to early detect decline, c) lifestyle and social behavior evaluation to early detect risk of exclusion, d) an activity center that suggests and guides the elder in personalized cognitive and physical games, e) actively promotion of social activities, f) increase of knowledge in the elder’s diseases to promote empowerment, g) assistance in everyday tasks, and h) meaningful interaction with Giraff and the other components.

These functionalities, are not isolated but they are tightly interconnected. For instance, regular physical exercise has been shown to be effective at maintaining and improving the overall health of elderly individuals,,.. Physical fitness is associated with higher functioning in the executive control processes, correlated with less atrophy of frontal cortex regions, and with improved reaction times compared with the sedentary. Social interaction, and specifically high perceived interpersonal social support, has also been shown to have a positive impact on general mental and physical wellbeing, in addition to reducing the likelihood of depression,,,. We will fully exploit the unique possibility of Robohome2.0 of addressing all these aspects to provide functionalities through the best mix of components for each elder. Moreover, a closed loop monitoring and assistance system will be developed. It will continuously update the elder profile upon the data collected by the activity centre and the monitoring systems; it will recommend a mix of personalized activities, having a challenge level suitable to the elder status; it will provide tailored monitoring systems to elder needs.

Such approach does call for various competences that are well represented in the multi-disciplinary teams of SAS, PCL and KOMMUN and in the consortium as well, that includes bioengineers (POLIMI), experts in HRI (UOP) and ICT researchers by ORU, UMIL, BDIGITAL and UMA. The consortium will allow developing strong inter-displinary research, promoting a bidirectional translation research approach, facilitating the communication between the non-technical and technical teams to come up with a shared view on how the Robohome2.0 platform should be (WP1, WP2). Plenary meetings at the different partners sites in the first stage of the project, will allow to better elucidate problems and current solutions and to make clear the current technological offer.

## 1.3.2 TRL analysis

The project is positioned in different Technology Readiness Levels (TRL) considering the various functionalities to which it is aimed and the whole platform.

Regular clinical monitoring of physiological parameters will be accomplished integrating off-the-shelf components that will be already validated and therefore they are already products on the market. These components will be possibly integrated with the virtual caregiver that will provide instructions in audio-visual form. Data will be transmitted to the virtual caregiver and from it to the community. This activity is expected to be at TRL7 at the end of the project.

Cognitive and physical assessment. A very innovative approach will be followed here. Sensorized everyday objects (TRL3) will be combined with motion acquisition through Giraff robot to provide synchronous motion and pressure data. Motion acquisition requires Giraff robot to approach the elder and orient the camera adequately with respect to the elder (TRL2). The fused data will be used to segment movement into components (TRL4) and derive a degradation index of clinical validity (TRL1). The high effort in this work in Task5.1 and 5.2 will provide a TRL6 technology at the end of the project. Voice pitch analysis explored for early detection of onset of cognitive degenerative diseases it at TRL1 presently. We expect to obtain a technology at TRL4 by the end of the project. We will also explore cognitive and physical exer-games provided by the activity center from which specific assessment parameters can be evaluated. The starting point is TRL1 and we expect to have the parameters validated by the end of the project (TRL7).

Lifestyle and social behavior evaluation. We will use standard components like z-wave, that will be assembled into a modular and flexible network (TRL8/TRL9) and integrate it with the robot. Its information will be integrated with data from monitoring and from the activity center to update the elder profile and tune the recommendations and monitoring (TRL4). We expect to provide a technology close to TRL8.

Activity center. The activity centre will be largely based on the IGER game engine that is being currently validated on the field within the REWIRE project (TRL5). We will extend it to support a mix of exer-games involving also cognitive exercises and support for multiple output devices. We will build a new layer to address knowledge acquisition and long term motivation through gamification. Both these extensions will be starting from TRL2. We expect to arrive at TRL7 with the pilot.

Promotion of social activities. This will be supported by a virtual community of users that will be built starting from BDIGITAL experience inside the projects REWIRE, BACKHOME and SAAPHO, in which it has coordinated the work related to the implementation of the community services and environment monitoring (TRL5). The community features will be tailored to requirements of Robohome2.0 and further developed. It is expected to arrive at TRL7. The community will also support multi-player games, typical card games. Multi-player view will be integrated through multiple video streaming through for instance WebRTC technology (TRL8). Multiple videos will be combined with a dynamical graphical scene showing score, cards and other relevant information (TRL2). We expect the component to be at TRL7 at the project end.

Increase of knowledge. This will be mediated by the community of users (TRL5) and by continuous education through gaming created through automatic narration (TRL3). We expect to arrive a TRL6 by the end of the project.

Assistance in everyday tasks. Proposed systems on the market for locating objects have limitations in range and power consumption. The technology is presently at TRL3 but it is likely to increase its level at the time the project will start. We will explore this technology in combination with robots navigation. We expect to bring this methodology at TRL5 Cooperative drug dispenser will be built upon micro-architectures already explored by SXT (TRL5) integrated with micro electro-mechanical devices. We expect to bring this component at TRL8 by the end.

Meaningful interaction with Giraff and the other components. Tight collaboration between psychologists, HRI experts and ICT researchers will allow building meaningful and attractive interfacing modalities. We will start from UOP and PCL competences (WP4) and shape Robohome2.0 throughout the development to promote compliance with the elder and provide HRI and GUIs at TRL7. In particular, we will explore an ecological approach for both the autonomous navigation of the Giraff and its approach to the elder, starting from the work of UMA (TRL4). We expect to arrive at TRL7 at the end. Lastly, an innovative distribute voice command system will be realized to provide a natural interface between the elder and the robot, starting from the experience of SG in signal processing (TRL4). We expect to arrive at TRL7 at the end.

## 1.3.3 Relationship with National and International Research and Innovation activities

The theme of elder assistance and aging well has been addressed by several research projects both under FP7 and AAL frameworks aimed at improving the quality of life of elder people, some targeting also disabled people. The idea of having a robot interacting with an assistive environment has been explored in the Companionable project (http://www.companionable.net/), where a mobile robotic companion interacts with a smart home sensorized environment with the aim of monitoring the elder against cognitive decline and stimulating cognitively him. Moreover, it can detect adverse events like falls. The Robo M.D. project was aimed specifically to detect critical situations like falling and launch an alarm. These concepts have been further developed in the Excite and Giraff plus projects (http://www.giraffplus.eu/), coordinated by ORU. In Giraff plus a wide range of environment and activities signals are used to monitor the elder and to provides a pictorial representation of his/her activities that can be used to assess her/his lifestyle. Monitoring is complemented with a robot that provides video-communication with his caregivers. The Robot Era project (http:// www.robot-era.eu/robotera/), provides a complementary view providing a set of robots that assist the elder in specific functionalities of every day life like moving objects . On the other end, a few projects have explored the use of low-cost technology to support the elder at home. The project Mobiserv (http://www.mobiserv.info/results/) will deliver a robotic prototype of an open standard-based personal platform capable of sensing the user’s personal environment and adapting to the user’s behaviour. The Oldes project (http://www.oldes.eu/home.html) is aimed to offer stimulation and remote overview to improve the quality of life of elder people, through a care platform designed to ease their life in their homes. More recently the Wecare AAL project (http://www.wecare-project.eu/) explores the social aspects in building a community to support the elders to live alone.

Several projects have been based on developing wearable devices to monitor elders at home. The Rosetta project (http://www.aal-europe.eu/projects/rosetta/) was aimed to monitor activities of elderly persons with sensors to generate alarm when unexpected activity, like a fall, is detected and support the elderly in carrying out daily and recreational activities. Monitoring of Parkinson people is carried out similarly in the Cupid project (http://www.cupid-project.eu/) that completes monitoring with specific rehabilitation exercises. Happy Aging (http://www.aal-europe.eu/projects/happy-ageing/) is a system for lifestyle monitoring, for issuing reminders and detection lack of activity or unusual behaviors. Hope (http://www.hope-project.eu) is targeted to Alzheimer patients and can provide alarms and communication with health professionals. It connects several house sensors and gives reminders and warnings via voice. eCaalyx (http//www.ecaalyx.org) integrates physiological sensors to monitor the elder at home that are worn and whose controlled is housed in a pocket of a t-shirt. The aim of the Interaction project (http://cms.interaction4stroke.eu/drupal/) is to develop a system based on e-textile and sensors to monitor motion and force exchange between a subject and the environment and to profile his activity. Using a similar approach, the Psyche project (http://www.psyche-project.org/) has developed a monitoring system based on e-textile and portable sensing devices for the long and short term acquisition of data from screened, patients, typically affected by mood disorders to manage psychiatric illnesses. However, the need to wear sensors limits strongly the usability of these systems that are still bounded mainly inside the research domain [PCL comment on this]. All these projects improve the elder life in some of its aspects; however they come short in providing a complete support to the elder in terms of monitoring and assistance, as well as providing connection with his/her caregivers. A different approach was followed in the Fitrehab and Rewire projects (http://www.rewire-project.eu), coordinated by UMIL, in which a hierarchical architecture has been developed to support rehabilitation at home. Rewire, in particular, has shown that assembling off-the-self components, patients discharged by the hospital, are enabled to continue exercising intensively at home, still under clinicians supervision. Monitoring the performance, adapting the exer-games at point of needs and motivational feed-back to the user and informative feed-back to his/her supervisors are deemed to be a winning strategy. Robohome2.0 builds on this concept and extends it to support the elder at home. Besides research projects, a few companies have approached assisted living market through robotics. Kompai, developed by Robosoft (http://www.robosoft.com/robotic-solutions/healthcare/kompai/index.html ) inside the Domeo project (http://www.aal-domeo.eu/) is a companion robot, meant as an open robotics architecture with, presently, limited capabilities. Giraff robot, developed over the years by GIRAFF (P3) (http://www.giraff.org/) is a robotics platform aimed at containing the costs on one side, and on the other side it has been developed with particular attention to a good interfacing with the elder and it has been selected as the most suitable service robot for Robohome2.0.

The other pillar of Robohome2.0 is the introduction of gamification. Games, or better exer-games that mix exercising and gaming, have been widely explored in EU projects mainly targeted to rehabilitation as a good way to stimulate, motivate and guide patients through exercises. In the Script project (http://www.scriptproject.eu/), games are combined with small robots and are aimed at guiding patients in the rehabilitation of wrist and hand functions. Also should be mentioned the project H_Cad, which was aimed to rehabilitate cognitive dysfunctions was carried out through tasks used in occupational therapy inside a controlled environment. In the EU project Backhome, how to provide cognitive rehabilitation tasks to people with severe disabilities is investigated. Currently, three categories of cognitive games have been taken into account: perception; attention and concentration; and memory. It is beyond the scope of BackHome to develop, validate, and illustrate clinical outcomes, however the intention is to validate the efficacy and stability of the proposed solution within a future evaluation. Cupid is aimed to Parkinson patients and specific exer-games have been developed which provide audio, visual and tactile feedback. The RGS system is aimed at upper arm and develops a game aimed at guiding the arm in 3D space. However, few of these projects go beyond basic graphics and gameplay resulting into exer-games of little attraction as they lack addressing good game design guidelines. Moreover, they have limited configuration capability and adaptation as well as monitoring is not provided. Moreover, the repetitive nature of their game mechanics make them not fit for prolonged exercising. The IGER (Intelligent Game Engine for Rehabilitation) game engine, developed inside the Rewire project (htttp://www.rewire-project.eu), is an exception. This is a game engine: a set of tools that are aimed, on one side at making the games run on the machine they are designed for, on the other end, help the developer in creating games that share the same features. Therefore, IGER has allowed a fast prototyping of new games, reusing the gaming functionalities that been developed for previous games. In particular, it contains the functionalities required to configure and adapt the exer-games to the user and to supervise him while exercising at home, to make exercising at home feasible and robust, on one end and, IGER offers therefore a good starting point to Robohome.

## 1.3.4 Overall approach and methodology

Activities required to develop Robohome2.0 can be grouped into four main areas: clinical and behavioral monitoring, assistance, activity promotion, and virtual communities. We will here analyze the research and development required inside each area.

### Monitoring

The main element that limits the prolonged living at home of the elder is monitoring This has different facets that all contribute to make the elder and his caregivers feel safe and supervised at home. In Robohome2.0 2.0 monitoring will include:

- Clinical monitoring, to assess the elder’s clinical status and to manage alarm situations in due time.

- Physical and cognitive monitoring, to provide a quantitative evaluation of the residual motion and cognitive capabilities of the elder.

- Social monitoring, to provide a qualitative evaluation of the elder social habits.

- Environmental monitoring to guarantee safety (e.g. gas alerts) and to acquire environment data (e.g. humidity, temperature) that influence activities, and lifestyle (e.g. pressure sensors under sofa and bed mattress).

Clinical monitoring is aimed at maintaining under control the acquired diseases through regular drug assumption and regular sampling of physiological parameters. Therapy compliance will be helped by Robohome2.0 through a cooperative smart drug dispenser. Several solutions have been proposed for hospital use, in which many different drugs have to be provided to many different patients, , through a centralized control integrated inside the hospital. We will develop inside Robohome2.0 a novel, low-cost, simplified solution dedicated to one person (Task 3.7). This will be constituted of a set of drawers, each with a remotely-controlled, specific electromechanical lock managed by the virtual caregiver. Only the right drawer is open at the time in which the elder should take prescribed pills. At the same time Robohome2.0 warns the elder through the devices available: Giraff, smart phone, TV. This approach still requires that the real caregiver or the elder fill the drawers at the beginning of a week, but it then guarantees that the right pills are taken at the right time.

Huge progress has been achieved by ICT in the last years for at home clinical monitoring, For instance, Zephir technology has proposed a suit for clinical telemonitoring and Alive a specific suit for heart monitoring. More recently IMEC has proposed wireless ECG, EMG and EEG devices that can be connected to an android phone to enable reliable long-term ambulatory monitoring of various health parameters such as cardiac performance, brain activity and muscle activity. Portable devices for glucose measurement are also available with 42 different models available only in UK and sampling through Android phone has been recently developed. All these systems are nowadays a reality for many elder people, who are given the capability to monitor their own health, taking at-home the physiological samples required. To these devices, specifically certified for the health sector, more recently devices targeted to fitness and wellbeing are being developed. Samsung and Apple have recently announced the integration in their smart phone on sale this year, apps for monitoring a comprehensive array of vital signs, encompassing heart-rate, blood pressure, temperature, oxygen saturation and lung function. Although no approval as a medical device has been announced yet, they do provide and interesting consumer alternative.

In Robohome2.0, the most convenient sensor/system to measure a specific required clinical parameter will be identified in Task2.1 with the most suitable interconnecting network, and realized in Task 5.6. Data will be provided to the Virtual Caregiver. This will be able to guide the elder and advice him through video and voice feed-back, while taking samples. Although ICT has made the control of diseases possible at home, by using such kind of “user-friendly” solutions, some times, it is still difficult to understand the reliability of the final measure, without remote or direct assistance of caregivers. We will take advantage of Giraff’s capabilities to provide direct video-connection to the GP or remote caregivers when physiological samples have to be taken.

These two activities will be mainly technological and they requires clinical validation. Nevertheless an important piece of research is required to find the best solution in terms of usability and motivation.

Physical monitoring will be performed with three main modalities. In the first modality, identified common assessment tests, will be carried out at-home under remote supervision of the caregiver through audio-video communication (tele-monitoring). Smart Giraff navigation system allows to carry out the tests in the most comfortable situation and location for the elder. In a second modality, we will substitute the clinician with the Virtual Caregiver that will remind the user not only when he/she has to perform a test but it will also guide him/her step by step during test execution through explicative audio-video animations and providing also the ICT support to complete them. In this second modality, the elder will move in front of Giraff that will pick up the elder movement through its 3D camera and reconstruct his/her movement. It has already been shown that 3D cameras like Kinect returns a complete description of the skeleton motion, with data of good quality. From motion data, the score will be automatically computed and sent to the virtual caregiver. Most suitable tests will be aimed to balance and they can be Berg-balance, TUG or Morse Fall Scale to prevent falls. These tests have been clinically validated and can be used to obtain an objective picture of the physical / cognitive status of the patient. Validation of the tests administered in this autonomous modality are integral part of the proposed project (Task 3.6).

In the third approach, monitoring can be carried out while observing motion associated to everyday activities. The progress in micro and nanotechnology and the availability of miniaturized sensors, has made available a huge range of small wearable devices for the consumers market, from simple pedometers to computerized trainers that allow measuring heart rate, calories consumption, local speed and additional parameters of the physical exercise (e.g. http://www.polar.com/us-en/products). Fitness is still the leading application for this; for instance personalized training paths can be acquired from the web and displayed in real-time along with the actual physical data (heart beat and position) to provide to the athlete both environment and physical information (e.g. http://sites.garmin.com/edge/). Similar principles have been applied to develop products aimed at tracking and profiling human motion. For instance Xsens was the first to develop motion sensors based on the integration of accelerometers, gyroscopes and magnetometers, Gait-up has developed sensors aimed to provide a profiling the user with accurate evaluation of the activities through worn sensors. These devices are usually mounted in charming cases that makes these objects fashionable and trendy. Miniaturization of sensors and integration in the clothes has been also pursued in the Interaction EU project (http://cms.interaction4stroke.eu/drupal/), through smart textile. New sensors will communicate with a Smart phone that will act as a Hub and as an integrator of these data into a lifestyle evaluation like for instance through the Digifit or Zausan apps. Such apps often integrate both environment and physiological data. However, on one side, the hereabove mentioned sensors allow collecting limited amount of information, on the other side they require that the user wearing them that makes their compliance limited for long time use.

A different approach has been proposed in very recent EU projects that have developed novel technological approaches based on sensorized objects. Caretoy (http://www.caretoy.eu/) proposes wireless sensorized toys mainly composed of two soft air-filled chambers connected to a pressure sensors made by elastomers and shaped as a cylinders and a rigid case containing the electronic unit to discriminate the grasping actions of right and left hands separately. Such system provides a gross discrimination of actions on the object. CogWatch (http://www.cogwatch.eu/) introduces a device that contains a 3-axis accelerometer and 3 axes force sensitive resistors in a small package that fits to the base of objects such as mugs, jugs and kettles.

We will further develop these approaches by combining motion acquisition through Giraff with sensorized everyday object to provide monitoring transparent to the elder: he/she will be monitored observing the elder while carrying everyday tasks, like combing hair or preparing coffee or walking with the walking stick. Data acquired synchronously from the object and from Giraff’s camera allow to derive a detailed characterization of movement profile as reported in Section 1.4.1. Suitable indexes the link deterioration in motor performance with clinical scales will be defined. This would allow an automatic continuous monitoring of the elder with daily assessment that allows an early detection of deterioration in the motor performance (Task 5.1 and 5.2).

This activity has a large research and development component in the design, development and experimentation of transparent monitoring.

Cognitive monitoring is based on evaluating the basic cognitive function: memory, reasoning, orientation and it is aimed at detecting cognitive deterioration associated to onset of degenerative diseases like Parkinson, Alzheimer or Fronto-Temporal Dementia. As for physical monitoring, assessment is carried out through validated tests that may be tele-operated. We will explore the possibility to operate these tests also by means of the Virtual Caregiver. QMCI or mini-mental test seem particularly suitable to be transposed into a computerized form, because of their being constituted of questions with multiple choice answers. The best graphical form for the questionnaires will be designed. We will take full advantage of Giraff to show to the elder the questionnaire on the display, reading them through the Virtual Caregiver Avatar, collect the answer through touch screen display or gesture recognition developed in Task 4.1. The avatar will provide voice feed-back, adequate to the actual performance, to encourage the elder and increase effectiveness of the administration. Alternatively, smart phone based applications will be considered like Doctot. We will also explore the use of TV to administer these tests, in which case a TV remote controller interfaced with the Virtual Avatar will provide the selection of the answer.

We will go one step further and use the Virtual Caregiver to provide assessment in a transparent way similarly to physical monitoring. In this case, cognitive data for the assessment will be gathered through specific spot questions proposed at the beginning or at the end of any typical activity, like watching TV. This modality to carry out assessment will be analyzed and validated by clinicians in Task 3.6. Additional information will be provided by data provided by cognitive activities, like puzzles, riddles, Simon or other memory games made available by the activity center (Task 4.3). Additional information can be derived by the analysis of the performance in social games, like playing cards (time course of winning rate). We will explore how to correlate all these data with clinical scales (Task 5.2).

This activity has a large research and development component in the design, development and experimentation of transparent monitoring.

Scenario: Ann sits down on her sofa and switches on the TV. Robohome2.0 has pending questions to complete cognitive evaluation. It realizes that the TV has been switched on, selects the TV output port, and sends to the TV the Virtual Caregiver avatar to welcome Ann and ask her politely the “daily question”: “which day is today?”. Ann answers correctly, the avatar smiles and says bye to her. The TV program of the last channel selected appears to the screen.

We will also develop a second form of cognitive transparent monitoring. Degenerative diseases in their early stages are often associated with anxiety and mood disturbances, psychoses, compulsions, anxiety, and agitation. We aim to early detect these symptoms through analysis and profiling of phone conversations as descried in Section 1.4.1. We will combine this information with the analysis of time of day and frequency of the calls as some people with dementia phone their loved ones over and over again – particularly in the middle of the night. This can be very frustrating and distressing. The person with dementia may forget that they have already called, or may be insecure or anxious, therefore changing the voice spectrum of the conversation. This combined information may provide evidence of early cognitive degeneration (Task 5.4 and Task 6.6).

This activity is mainly research in the development and experimentation of transparent monitoring of degenerative diseases through profiling phone conversations.

Social monitoring. This is a new aspects that is becoming more and more important in a society in which the familiar bonds are less tight than in the past. One of the main risks for the elders, highlighted in the call, is exclusion and isolation that can easily lead to depression and poor quality of life. Although an automatic identification of all the possible activities is beyond reach, we will identify some of these that can be representative. The duration and frequency with whom the elder exercise in group, provided by the activity center (Task 4.8), the logbook of activities (e.g. teaching at third age University, giving courses, going to theatre, concerts), registered through a digital log book made available by the virtual community, degree of interaction with the community (Task 6.3) can all provide an estimate of the elder social behaviour.

This activity will be mainly technological, based on SW development.

Environmental monitoring. The possibility of using ICT technology to control the appliances and supervise the house, has long been recognized as an interesting business opportunity in the domotic field: gas and light alarms have been developed as stand alone (e.g. http://www.beghelli.it/), or as devices that can be also integrated in a house control panel (http://allarmiwireless.net/shop/). The latter approach is particular suitable to add new devices at need. More recently this approach has been extended to assisted living environment (e.g. http://www.tunstall.co.uk/) in which some of the sensors contribute to determine the habitudes of the elder, like pressure sensors under the sofa or under the bed, presence sensors or TV usage. BDIGITAL has already realized a prototype that integrates inside a single complex sensor temperature, humidity, luminosity and gas alert, that has been inserted into a low-cost micro-architecture able to transmit the data remotely through wireless connection Such architecture based on a Raspberry PI low-cost micro-controller will be fully exploited in Robohome2.0: most promising off-the-shelf sensors that fulfill specifications set in WP1 will be identified at project start in WP2 and integrated into a modular network that uses the recent novel standards, like low-power Bluetooth for minimal intervention and longest battery duration. Protocols widely diffused in the domotics field, like Z-wave, will be adopted to maximize extensibility of the system. Such network will feed the data to the ontology defined in Task 3.4 and used to refine the recommendation and suggestions to the elder (Task 3.5).

This activity will the result mainly in a technological effort (Task 5.3).

### Assistance

Assistance is provided by the virtual caregiver to the elder to support him/her during dailylife, to provide recommendations and to promote activities provided by a dedicated activity center. Assistance in everyday life is a growing market, mainly developed as Apps for smart phone (e.g. http://www.hexstudio.com/, https://www.easilydo.com/). They are built mainly on two concepts: improving the functionalities of a digital agenda and linking the data coming from the connected devices. We aim here to complement these functions with a specific functionality (Task 3.8) that implements a locating service that search for objects that are typically lost by the elder: reading glasses, phone and keys. For tagging objects, there are new emerging solutions based on sticks or key rings to be used with specific Apps, but elderly people would have still to find by themselves the objects and, moreover, the mobile phone has not to be lost. The Phone can be located through GPS signal, but usually GPS signal cannot be received at home. Also RFID technologies already are used for tagging objects. However, RFID tags devices require a reader to be placed inside all the rooms, with a high impact on the house. We will explore in Robohome2.0 an alternative based on miniaturized active tags described in Section 1.4.1. We envisage the elder asking Giraff to go and search for the object through the distributed voice command system (Task 5.5) the lost object. The same functionalities will also made available through a phone App (Task 6.6) or thorugh Giraff itself, using its touchscreen display or the TVmonitor.

Research and development applies to the location of everyday objects.

Scenario. Mary is at Elif’s home when she realized that she has not her keys with her. She is upset as she thinks that she has lost her keys. She call Giraff with her app and asks it to find if the keys are in the hose. After a while Giraff’s replies sending to Mary’s mobile phone a picture taken with its 3D camera in which the keys are shown over the Kitchen table. Mary is relieved, she calls her daughter who has a copy of the keys, to get into her house.

Diet is also an important aspect of a good lifestyle. Suggestions and recommendations on diet will be gathered through the community and the caregivers and proposed as recommendation by the Virtual Caregiver through Giraff of through a specific app (Task 6.6).

This activity will the result mainly in a technological effort with leading technology.

Scenario. Ann has invited her daughter and nephews but she does not know what to cook. She calls Giraff and select the kitchen button on the display: a set of recipes, compatible with her diet regimen, are displayed, organized along a few dimensions like time of cooking and complexity. She chooses a “Carbonara pasta” and a list of ingredients is displayed on Giraff monitor and sent to her android phone as an SMS. Ann prepared then the dinner with the help of the instructions displayed by Giraff one step at a time. Her dinner was a success. She was very happy and gives this feed-back to Giraff, that changes the recipes order, ranking higher the successful recipe.

### Activity Center

The Activity Center supports social activities and proposes and guides the elder through tailored physical / cognitive exer-games. The activities and their goals will be planned and negotiated between the elder and his/her caregivers, adopting an empowerment strategy.

Weight Shift

Figure 2 - A screenshot of one of the "Fruit catcher" exer-game of IGER.

Exer-gaming has received a strong push in the last year by the novel tracking devices, like the Nintendo Wiimote Controller and Balance Board, the Sony Move, and the Microsoft Kinect, that have revolutionized the way people play video games, making interaction much more intuitive. It was soon recognized that these devices allow the acquisition of motion and interaction data of good quality that be useful in many domains. Alongside, powerful games engines have been made available recently under open source license, or with limited costs (e.g. Unity or Panda3D). This, paired with the rise of mobile gaming, has opened the game development process to smaller teams, complementing their offer. On the other side, it has allowed the incorporation of novel ideas coming from the research fields into new or existing video-games with less technological effort than before. This has allowed UMIL developing the IGER game engine inside the REWIRE project, that will serve as the nucleus of the game center. IGER integrates methods of computational intelligence for users’ monitoring and adaptation, IGER games are fully configurable so that they can be tailored by the clinicians to the users needs and exercising goals, and they are continuously adapted in real-time to the user’s performance through a Bayesian framework that updates game parameters to provide an adequate difficulty level while keeping the elders within the therapeutic constraints specified by the clinicians. The gameplay is continuously monitored using a fuzzy system (leveraging for instance the therapists’ knowledge) to avoid wrong postures or wrong movements, which would make exercising more harmful than useful. A novel color coding feed-back is used to inform the user in real-time on wrong movements. IGER also integrates a personalized avatar that advices the user and guides him through the exercising sessions. Controlled randomization of assets, targets, voice feed-back avatar choice, and facial animation are all aimed to increase compliance with the therapy, . Finally, several input devices can be interfaced to IGER thanks to its specific input abstraction middleware. The cognitive and physical exercises defined by the virtual caregivers in Task 1.2 will be analyzed and transformed into mini-games (Task 4.3), in which the desired trained movement or function has to be used to achieve the game goal. For instance a balance exercise that requires shifting the body laterally can be guided by an exer-game requiring the user to catch with a basket on the head fruits falling from a tree (Figure 2). A meaningful gameplay is implemented in IGER to guide the users through the desired exercises; in particular, clear interaction and feed-back with reasonable lasting effects, enjoyable environment, music, sound, rich graphics are adopted according to the rules of good game design. Moreover, the gameplay is designed to be fully configured to the elder ability and idiosyncrasis so that it can be adapted by the Virtual Caregiver to the actual state of the elder.

This activity will the result mainly in a technological effort with leading technology.

Scenario. Giraff approaches Mary and asks her if she is ready for her daily exercising session. The Virtual Caregiver shows her the daily program and at the same time it analyzes the environment data downloaded from the environmental sensor network. The Virtual Caregiver analyzes the data and realizes that it is too hot and humid today to maintain the same level of exercising as the days before and downgrades the games difficulty. It sends a message to both the elder and the caregivers and allows Mary to start her daily exercise.

Motivation is indeed at the heart of keeping exercising. However, exer-games alone are not sufficient to maximize elders motivation. Thus, we fully explore Gamification in Robohome2.0. Gamification involves the use of game design and game mechanics for a purpose other than entertainment. Gamification techniques leverage people's natural desire for competition, achievements, status, self-expression and closure. In a single-player settings, gamification concerns designing gameplay such that the user feels rewarded when accomplishing a task. Intrinsically, this can mean adding a game on top of the exercise, providing a goal and meaningful gameplay, as well as feedback, Extrinsically, to this aim, various and targeted reward systems can be devised, for instance: points or coins gained, achievements and levels reached certified by virtual badges, improving in completing a game. Such rewards can be shown for instance by a progress bar and spent inside a community of players, showing relative achievements through ranking or leader boards in which top players achievements are described. In a multi-player setting, gamification can be implemented through direct or indirect competition, or through collaboration. Indirect competition follows the use of scores, virtual badges and achievements, when they are integrated into a social engine. Direct competition can be implemented by providing multi-player play, so that two people can directly compete. This is already available in many online games, especially sports and shooter games. At last, collaborative games can be played with multiple people, all pursuing the same goal. This can be for instance a puzzle built in collaboration or a riddle solved discussing in a group. Collaboration allows less harsh, not competitive activities to be performed in a social manner. In all these cases, a proper challenge level is required to allow users to enjoy gaming and achieve effective gamification. If too challenging player would give up soon, while if the task is too easy the game becomes boring and uninteresting soon. A good game design, nice graphics, effective gameplay, clear feed-back and proper challenge level all contribute to enter the player in a state of flow. Flow theory is widely accepted as guiding principle by the game design community: it states that when the physical and cognitive skills of the user are matched by the level of challenge posed by the game, the user enters a state of complete focus and immersion in which it loses track of time. The benefit of the flow state is that the user becomes completely focused on the game and everything else vanishes. Studies also show that physical pain is also reduced when flow state is reached. In the latest years, gamification has been gaining a lot of interest from very diverse fields and it can thus be found everywhere: from car fueling systems to ATMs, to environmental campaigns, to workplaces around the world. At this speed, every aspect of our lives will likely be affected by gamification in the near future. In Robohome2.0 we will design a layered gamification approach that addresses: a) game design, b) game play and supports c) automatic narration.

a) We will explore personalization of the game design. A parametric game design will be explored, in which some game assets and scenes can be uploaded either through randomized control, as explored in Mainetti et al., or according to the preferences captured by the elder profile (Task 3.4). Personalization is traditionally a key factor to increase intrinsic motivation,  but it is not the only one. Elders cognitive capability decreases with aging and with it the capability of reading complex images. The game design should therefore have an adequate cognitive load. We will explore scene simplification techniques to derive a level of details (LOD) in the scenes that matches the residual cognitive ability of the elder (Section 1.4.1).

b) The game play will take full advantage of IGER functionalities tuning the game difficulty to his/her status, providing meaningful feed-back and monitoring correctness of movements.

c) Single exer-games have limited motivation capabilities. A stronger motivation can be obtained when exer-games are embedded automatically inside a narration in which each single episode introduces the next one. Moreover, projecting the gaming results into a community of users increases motivation and promotes socialization. This can further increased when exer-games are played in group (Task 4.1 and 6.1).

Automatic narration is a research topic of great interest for artificial intelligence scholars, as writing good stories is notably one of the tasks that is relatively easy to perform for humans and difficult for machines. A whole research field has been recently born from this interest, Computational Narratology, that aims at interpreting, generating and analyzing narrative using information processing techniques. Achieving automated storytelling can be beneficial for different purposes: producing novel and interesting stories to be consumed without the need of an author, tutoring students of narrative by analyzing and providing story corrections, or providing interactive and dynamically created stories for video games. Various methods for the automated generation of stories have been proposed in the literature. Those methods can be grouped into: (i) problem solving, (ii) data-mining methods and (iii) knowledge-based. Problem solving methods define a set of agents, actions and goals, then reason in order to drive the story to a conclusion by letting each agent pursue its goal. Many systems use this method. Well-known examples are the TALESPIN system, AUTHOR , UNIVERSE, MINISTREL, MEXICA. Similar effects are achieved using systems based on autonomous agents, such as the Virtual Storyteller project. The use of autonomous agents is also useful for interactive purposes, allowing users to interact with the storytelling process. Some systems have also been paired with a virtual presentation layer, as with FABULIST. Data-mining methods do not use any underlying structure and can thus work with diverse story types, from mystery dramas to children stories, based on what corpora. These methods are still novel, with the first notable example coming from. Knowledge-based methods work on a database of rules, actions and relationships and try to create a story that is coherent and interesting. The created story thus depends on the chosen knowledge base. The first recorded system that implements this method is the Novel Writer system, developed by Sheldon Klein. Other known systems are BRUTUS, GESTER. Some systems use commonsense knowledge bases, while others use story schemas. Some approaches, pioneered by Peinado et al. are based on the ontological definition of the story context, actors and possible actions.

Although automatic narration can be developed, the control over the gameplay is still stereo-typed, with limited variability in the sequence of episodes. We will explore in Robohome2.0 the combination of knowledge-based methods for automatic narration with stochastic control to introduce a controlled variability in the evolution of the narration. We will go also one step further creating a flexible narration engine that can produce a narration from several different themes, chosen according to elders idiosyncrasies and preferences, and that guarantees that the narration will guide the elder through the mix of activities prescribed, thus taking into account the constraints posed by the cognitive and physical exercises in generating the narration.

This activity combines technological development (multi-player support) with research intensive tasks: LOD in level generation (Task 4.6 and Task 6.1) and automatic narration (Task 4.4).

Serious games have been introduced not only to guide physical or cognitive activities but also for education. This is the role of serious games implemented in vocational training, of which one of the most popular is the flight simulator, but it has been applied also to other fields like business (negotiation skills), construction, mining, sports, education and so forth. The benefits of serious games have been acknowledged by the medical community and efficacy studies of such games have been performed. Comprehensive reviews of serious games for medical education have found that the effects of such games are generally positive,. Many examples of serious games specifically created to can be found for teaching very diverse medical notions, such as epidemiology, anatomy, the respiratory and circulatory system or the respiratory system. A first attempt to teach about therapy is represented by badblood, which is aimed generally to educate healthy people on the most dangerous illnesses.

We will explore here the use of serious games, not only to guide them into activities, but also to educate the elders on their diseases, therapy and lifestyle and motivate them. This will be part of an empowerment strategy, in which the elder and his caregiver collaborate in setting adequate clinical goals and lifestyle.

However, such serious games have limited content and are not suitable for prolonged use. We will explore the same approaches based on automatic narrative developed to support cognitive and physical exer-games for prolonged time in Task 4.4, to education (Task 4.5).

This activity is mainly technological development on the technology developed inside Robohome2.0 in Task 4.4.

Figure 3 - Silhouette integrated inside a Virtual Environment in Duckneglet (left). Silhouette extraction through Kinect SDK1.8 (right).

The sense of immersion inside a game does also contribute to flow. We are aiming to further increase this by exploring to use the elder silhouette instead of the avatar of Figure 2, as explored in Duckneglect. This produces a mirror view in which the user sees a specular view of himself on the display (Figure 3). However, a clean silhouette is obtained from 2D cameras only with controlled background, that is beyond reach in a house. Kinect has raised the expectation of a robust foreground segregation, but this was not the case as neither Kinect SDK1.8 nor the new Kinect2.0 produce a clean silhouette (Fig. 3, right). A few attempts to improve background subtraction, based on spatial and temporal smoothing turned out to be not completely satisfactory. Recently a parametric approach based on level sets, combined RGB and range images for foreground segregation of objects of predefined classes was proposed. Such method resulted effective only for simple objects like shoes. Moreover, it is not compatible with real-time (a delay of 70ms is introduced) and requires high performance computers not compatible with autonomous robots. We will develop a method on silhouette extraction described in Section 1.4.1, that refines the segmentation produced by the Kinect depth map through information from the RGB image.

This is mainly a research activity (Task 4.2).

### Service Robot and Virtual Caregiver

Services in Robohome2.0 will be provided by Giraff robot (www.giraff.org/, Figure 4‎). This is a robotic base that carries a touch screen monitor, speakers and a high-resolution camera with selectable zoom capabilities. The screen is a pan-tilt unit which enables a greater and controllable field of view, while its height over the base is adjustable to create an eye-level view with the elderly. The base hosts a Windows 7 embedded OS (Intel Core i7, 4GB RAM, powerful enough to run a game engine) that controls the motors, that can propel the robot in any direction, runs a videoconferencing application, receives the input from the touch screen and displays the output. The motors, dis play tilt and height adjustment can also be controlled by a third-party application through an API. Giraff supports WiFi communication through 802.11x protocols and USB2. Giraff is integrated with two software applications. The fist is Pilot that allows users/visitors to access and control the Giraff over a standard Internet connection. It allows remote video-control for instance to “visit” a home or other care location or to navigate Giraff down hallways, through doorways and around tables and chairs. The second application is Sentry, a call management and administration system that manages Giraff and Pilot visitors, and allows administrators to configure Giraffs, alarms and communications options. These two applications will be integrated inside Robohome2.0 at the point of need.

Figure 4- Giraff robot

There are no other commercial mobile telepresence solutions like Giraff in Europe today, and none specifically focused to homecare anywhere in the world. There are five commercial products similar in concept to Giraff, all based in the U.S. and all focused on other applications. Anybots – QB is a finished product in the market but not suitable for home care service at this time for various reasons including price (~13000€ plus additional support costs), stability (it uses dynamic balancing technology for movement similar to the Segway device) and a very small display size. The company is committed to its current product direction and gives no indication of serious interest in homecare. VGo Communications – VGo is perhaps the product with the most “finished look” but also not suitable for home care service for various reasons including also a very small display size. Its main emphasis is on enterprise communications, but VGo does describe several use cases around patient monitoring and remote hospital and home visits. VGo’s short height (1.2 meters) make it an attractive avatar for small children. In Touch Health – RP-7i and RP-VITA The RP-7 series is the oldest mobile telepresence product in the marketplace with a strong focus on clinical health care. It is used in clinical settings to allow specialists to conduct a virtual patient visit from a remote location. It has advanced features including autonomous navigation and obstacle avoidance, a second display for data and integration of biometric devices. However, its price point is well in excess of 100 000 €, far beyond what is feasible for home care. InTouch has also partnered with iRobot to create the RP-VITA, a lower-cost version of the RP-7i, and is based on a subscription model (monthly service fee). However, at 3 600 €/month the economic model is still based upon leveraging very high-cost resources (specialists) and is far beyond what can be justified for home care. Suitable Technologies – Beam Suitable Technologies is a spinoff of Willow Garage and produces the Beam. Of the products described in this document, Beam is perhaps most like Giraff in design philosophy because it is near-human height, uses a large display to present a near-life size portrait of the visitor, has HD video quality with zoom and high-quality audio. Based on technology developed at the highly-regarded organization Willow Garage, Beam is a well-designed product but has a high price point (more than 14 000 € plus a monthly service fee) and still lacking some essential features needed for home care. For example, it weighs nearly 50 kg so is difficult to transport, and cannot traverse even small door thresholds. It also has a sophisticated local interface to the device itself, well beyond the UI capabilities of most elderly who are receiving home services. Double Robotics – Double is essentially a “kit” consisting of a motor-powered frame and an iPad docking port (the user supplies their own iPad) with basic application software to drive the device. The price point is attractive at 1 800 € but it has none of the features required for home care and has no specific market focus, but rather is a truly generic platform. For example, Double uses the iPad for its audio and video, designed for someone sitting directly in front of the device as opposed to the wide, high-quality field of view required in a home care application. It has limited call management features (compared to the Giraff Sentry system) and no ability to make social gestures such as nodding, turning or sitting. Additionally, none of these products provide a general development platform such as Giraff for third-party application development, plug-ins and direct camera and motor control. For all these reasons Giraff appears the best option for Robome2.0.

Giraff will be further extended in Robohome2.0 enabling him with autonomous navigation (Task 3.7) and have a more natural interfacing with the elder (Task 8.1). For navigation, Giraff will be extended adding a 3D camera, possibly a Microsoft Kinect, that allows acquiring synchronous in time a 2D RGB image and a depth map (range image) from which a single colored 2.5D image can be obtained. The range images will be used to build a 3D map of the house, for instance using the recently developed APIs based on Kinect fusion, . Two are the major challenges for the reactive navigation: 1) to manoeuvre in tight spaces, without being trapped in local minima, and to deal with 3D-shaped objects. It is important to notice that, for the Giraff robot, the common assumption of worst-case, constant shape along its height is quite unreal, and prevents finding possible free space to traverse. We will work towards a navigation solution that accounts for these features by extending to 3D the previous work of the UMA group on 2D reactive navigator, which models the robot shape as a polygon and embeds its kinematic constraints into different motion models through the so-called Parameter-Space Transformations. Apart from the geometrical and kinematics robot constraints, we will explore here how to introduce additional proxemic constraints to path planning that take into account the idiosyncrasies of the elder. For instance, she/he may not like that Giraff approach him frontally, or to stand too close. Navigation will be triggered in several ways: by the elder asking Giraff to look for an object, by the elder or a caregiver that ask Giraff to go in a room to see what is happening there (taking a picture), by the Virtual Caregiver that asks Giraff to do some monitoring or by the elder to look for a lost object.

From the architectural point of view (Task 3.1) we will define a middleware that will provide a common interface to all components: the monitoring systems, the input from the community, the services provided for assistance and the data required and provided by the activity center. This same middleware will allow interfacing the robot sensors and actuators, providing a unifying view of the system. Guidelines will be provided by the ongoing universAAL project (Universal open platform and reference specification for ambient assisted living) aimed at providing a separation between the services provided and their implementation. Such middleware will allow all components to write and read relevant data in a consistent and simple way, guaranteeing at the same time maximum standardization and scalability. Dedicated high throughput channels will be reserved to graphics, video-communication and 3D camera. To adequately storage the data, heterogeneous and arriving at different frequencies, new generation no-SQL data bases like Voldemort, MongoDB, Cassandra, Neo4j, will be explored and compared with the traditional SQL ones.

Some activity is mainly technological and carried out in (Task 4.1) Navigation will be improved through research in robotics navigation (Task 3.7).

A Virtual Caregiver will be embodied inside Giraff. This will have access to all the data from monitoring systems, the information inserted through the community from his caregivers and the data provided by the activity center. To manage this heterogeneous and rich information semantic model (ontology) will be designed and developed in Task 3.4. This will contain high level concepts that relate to the elder, various health conditions, the types of activities that they can perform, and also the high level concepts related to the information provided by the sensors. This semantic model will be used to formulate rules leading to concrete recommendations that the system will make. Recommendations may involve calls to specific routines taken by Giraff, or suggestions for activities. It will be the starting point to promote a fully collaboration between the service provider, the community of users (GP, relatives, social services) and the elder.

A reasoning layer will be designed according to the functionalities defined in WP1, to provide the optimal mix of activities, to tune their level of difficulty to elder status and to add a flexibility in the design of the rules for recommendations. This is achieved in Task 3.5 along the guidelines already explored by ORU. Such layer will evolve dynamically, according to the feed-back provided by the users through Robohome2.0. This same layer will provide the activation of the Virtual Caregiver Avatar to promote a meaningful interaction, as investigated in Task 8.1. The Virtual Caregiver will guide the elder through cognitive and physical clinical tests in cooperation with the activity center (Task 3.6). It will also transmit to specific members of the community layer the psycho-phisical evaluation emerging from these tests as well as the tests performed transparently to the user, as well as social evaluation (Task 3.5). This same information is used to tune the exercise mix proposed to the elder.

Research related to this activity is mainly related to an efficient management of the huge amount of heterogeneous data to provide information that can be used in real-time.

Scenario: Robohome2.0 Virtual Avatar realizes that Janes has provided the wrong answer to the question “which month of the year is today?” in the last times. The virtual caregiver increases the weight of the cognitive exercises in the exer-games suggested proposing more riddles and puzzles during the day. It also warns Jane’s GP and relatives, who push Jane to play more cards with her friends. After a while Jane did not answer wrong any more to Giraff spot questions.

### Human Robot Interfacing

A large effort will be spent do design a robot that develops a meaningful relationship with the elder. Humans use a wide range of paralinguistic cues to signal intention. Eye gaze, preparatory gestures, body language, and so forth are used to signal intentions, actions and goals. Robots that operate in public settings (e.g. homes and care homes) can be safer and more effective at performing work if they were designed with similarly human-readable behaviours. Unfortunately, care robots are severely limited in this respect. Their appearance does not evoke anthropomorphisation and their behaviour, alluded to earlier, is not conductive for human-robot interaction. A remarkable exception is represented by Giraff robot, that has been developed explicitly to maximize compliance with the elder. To develop a meaningful relationship with the elder, an important aspect of the Robohome2.0 is studying how Giraff interaction can be tailored so naive users can use behavioral cues and voice explanation to form an understanding of the beliefs, intentions, goals and abilities of the robot. The challenge is to make the robot’s thought processes external and thus observable. This will be fully investigated in designing the feed-back provided by Giraff and the Virtual Caregiver avatar in Task 8.1 that will leverage of DL developed in Task 3.2.

Another key feature for effective HRI is the integration of the user’s explicit and implicit feedback. As in any assistive, cooperative, or interaction-based tasks, user feedback is critical to task performance. The most commonly used form of explicit feedback for interactive service robots consists of providing information to the user directly in the form of language, possibly with accompanying visual information. As for implicit feedback, Breazeal et al. (2005) demonstrated that the use of implicit communication by a robot could improve task performance and robustness to errors. Implicit feedback can be based on the user’s motion and gestures. This will be indeed the modality that will be adopted in Robohome2.0: the navigation system will develop a personalized approaching modality and interaction will be mediated by the Virtual Caregiver avatar through realistic animation and speech (Task 8.1). Similarly, the most natural interfacing with Giraff will be used: gestures (detected through Kinect, Task 3.3) or voice will be used to guide the interaction with the elder when they are both in the same room and will be fully used by the game center for interfacing. When the elder will be in a different room a distributed voice commands , designed in Task 5.3, will be used.

Scenario: Mike has just received his new Giraff robot. He switched it on and the Virtual Caregiver waves him with a: “Hello Mike, my name is Giraff. I will stay with you as long as you like. I come from hot Savana, but I will be pleased to leave in your comfortable apartment in Orebro”. After a few days Giraff approaches him slowly and his Virtual Caregiver appears on the screen to say: “Hey Mike, please check that the gas in the kitchen is not switched on” and at the end of the month: “Why don’t you give a call to Matteo, your nephew? Is his birthday”. Mike adores having someone that does not pretend and takes care of him.

To provide a unified view of Robohome2.0, an effort to unify the structure of the different GUIs structure will be carried out, identifying the most adequate basic modules. Moreover, the best appearance will be tailored to the current output device chosen: TVscreen, touch screen or smart phone will all be used to interact with the community of users or with Giraff.

Some activity is mainly technological and carried out in (Tasks 3.2 and 8.1). Effort for maximized HRI effectiveness is research based (Task 8.1). We will explore in innovative distributed voice command system in Task 5.3

### Community of users

The Robohome2.0 project aims to bring together all the major players through a unique community. As defined above Robohome2.0 will be formed by three types of user groups:

- Formal caregivers – such users will be formed by the clinical staff which will be located in the hospital.

- Informal caregivers – such users will be formed by family and carers of old people.

- Elderly people – this is the target users of the community and will be formed not only by the people which have a Giraff robot at home, but also to other elder who subscribe to Robohome2.0 community.

The community will have different purposes for each type of user. Clinicians will be able to access, in particular, to the time series of physiological measurements and assessment scales, caregivers to the lifestyle. The bi-direcitonal audio-video channel provided by Giraff Pilot software will fully exploited to supervise the elder when taking physiological samples, to assist when doing assessment tests at home or just to discuss any particular issue. The most important user is the elder, for whom the community is intended as a tool of motivation, adherence and cognitive and social stimulation. In particular the community will provide:

- Social support, through an internet connection:

  - To put the elder in contact with relatives and friends, to avoid isolation, to allow social activities like multiplayer gaming, to increase the opportunities of a reciprocal monitoring.

  - To allow the elder to easily access services and facilities (e.g. order food and other goods with home delivery, book ambulance/taxi for transportations).

  - To allow the elder to be informed of personalized social and cultural initiatives that he/she can still attend and enjoy (e.g. undertaken by associations to which the elder can be subscribed, or suggested by relative and caregivers).

  - To allow the elder to be informed of environmental information such as weather, news, etc.

  - To obtain information about diet.

- Healthcare support, through preferential pathways to produce necessary sanitary interventions. For this purpose the community around each elder will include one or more reference caregivers, the family physician, the geriatrician.

- Data storage, to memorize the historical data from the monitoring system and from the activity center, provided by Giraff. The same database architecture used inside Giraff will be adopted.

The socio-sanitary interventions will be mediated, at first, by the remote video communication capability of Giraff that will put in contact the elder with the person he/she needs. Interventions can be required by caregivers, by the elder themselves or by the Robohome2.0 intelligence that monitors elder activities and continually communicates with the formal and informal caregivers. According to preset priorities, different types of alerts will trigger a different pathway. The sanitary interventions eventually delivered can include telepresence visits, home visits, and direct calls to emergency services.

The success of virtual communities is due to a great diversity of factors. For instance, as studied by Leimeister et al., relevant factors are focus on one target group, continuous community-controlling, definition of sources of revenue as a starting condition for building a virtual community.

Social networks may play an important role in enforcing the relationship between elders and between an elder and his/her caregivers. Some remarkable examples have been studied, like SparkPeople (http://www.sparkpeople.com), which is an online community of people wanting to lose weight, DLife (http://www.dlife.com) is targeted to diabetes patients, http://stupidcancer.com is a community of people aged below 40 with cancer. BDIGITAL has already been explored the use of virtual community to educate and motivate patients in several research projects. Inside the project Rewire, a social community has been developed that allows patients and clinicians to chat using this portal, being the latter able to schedule such chats through a web application. This constitutes a good way of promoting shared clinician-patient decisions. Patients will be also able to fill in questionnaires related to clinical scales. That social community provides also further useful features such as forum, news, achievements. Robohome2.0 capitalizes on this community and extends it to provide a complete support of the elder at home in his physical / psychological and social behavior.

Community can constitute also a powerful drive for lifestyle adherence and exercising: gamification will fully exploited in WP4 and the community will host motivational mechanisms based on reputation like leader boards (Task 6.5), in which top players achievements are described, to improve lifestyle adherence and exercising. Thematic discussions and groups will allow to improve the collective knowledge on diseases, therapies and lifestyle that can also contribute to increase motivation.

Some activity is mainly technological and carried out in (Tasks 6.1-6.4), support to gamification will be carried out in correlation with Task 4.4 and 4.5 and self-organization of the community will be object of research in Task 6.5.

### Deployment modalities.

There is a progression in fraility: from robust to pre-frail to frail and we are aiming preferentially to pre-frail elders, as they are the people who, without any assistance, have the higher risk of degeneration. As a result, highly focused interventions will be defined especially for:

1) Elders who show the initial symptoms of cognitive degeneration, due to Alzheimer or dementia or other neurodegenerative diseases as well as evolutional depression. Commonly documented depression interventions indicate that cognitive behaviour therapy, cognitive stimulation and psycho-education delivered are effective in reducing symptoms of depression. Such interventions can be delivered also remotely. 2) Elders who have developed stability problems, because of fractures, stroke, arthritis or other factors, and need assistance to move (e.g. through a walking stick). For these elders a continuous evaluation of the trade-off between independent walking and wheel-chair should be always monitored. 3) Elders who need to control a specific disease over time, like hypertension, diabetes, COPD, Heart problems and so forth. PCL, SAS and MUNICIP have a very large basis of elders to which to propose Robohome2.0, with PCL alone seeing more than 1,000 new elder out patients/year of elderly subjects (age > 75 years) and 2644 in follow-up out patients (2011).

SCENARIO: Mike had a stroke and developed a mild hemiparesis to his right side of the body and in particular to the leg. He needs to do rehabilitation to recover stability and strength in the offended leg, but he lives alone, far from any rehabilitation center. Therefore he is thinking to go into a Nursing Home. His geriatrist prospects him the possibility of having at home Giraff that can help him doing rehabilitation exercises, with supervision of a physiotherapist that can monitor progress, advices and assists him. Mike adheres enthusiastically and his geriatrist, at the hospital, illustrates the rehabilitation program to him and shows him the Robohome2.0 platform installed at the hospital. For a few times, he goes to the hospital to do the exer-games developed for postural rehabilitation with Giraff under the supervision of a therapist until Mikes feels comfortable with the technology. As this would allow him staying at home, Mike is particularly enthusiastic. He then trained regularly at home for two months maintaining a tight connection with the hospital, recovering almost completely.

To the elders enrolled according to WP8, a personalized version of Robohome2.0 will be installed in their house where they can use it for five months. Robohome2.0 is adhering well to the current goals of social services to exploit ICT technology to allow the elder living at home for a longer time. The pilot will allow testing Robohome2.0 in real conditions, with elders in different clinical, physical and cognitive state. With this target in mind, an exhaustive protocol for pilot testing will be designed, including all the aspects: monitoring, evaluation and assistance. Results will allow not only to derive a preliminary evaluation of effectiveness, compliance, usability and reliability but also, through the comparison with standard care, the most appropriate business model to seamlessly connect Robohome2.0 to the network of services provided by hospitals, GPs and private and public service providers. Feedback obtained from the pilot test study outcome will be crucial also for the creation of best practices, guidelines and policy recommendations. Indeed Roohome2.0 will lead to the generation of useful, feasible and realistic policy recommendations: knowledge and expertise acquired through the project execution will be carefully analyzed in order to identify and describe the keys for success and failure of such an assistance platform and methodology to overcome all the barriers. This information will be compiled to provide policy recommendations, emphasizing generation of guidelines for the successful deployment of such platforms within the national health systems of the EU zone.

## 1.3.5 Sex and/or gender analysis

Sex and gender may play an important role in motivation. Activities and interfaces will be designed taking into account also gender in all aspects. For instance, a male and female virtual caregiver avatar will be provided to the elder, who can choose; the theme inside narration will be developed will take into account this issue, with sports themes possibly more liked by males. All these issues will be taken into account early in the project when functional specifications are set in WP1 .

# 1.4 Ambition

Elders with physical and cognitive problems are recovered in permanent residency too early or too little is done to let them staying at home longer. Robohome2.0 is aimed to change this.

- 1.4.1 Beyond the state of the art

Robohome2.0 aims to change this exploring gamification with robots in AAL setting to provide a complete system that tightly integrates personalized monitoring, evaluation, assistance and training inside a low-cost distributed pervasive system that does not require the elder to wear any particular device or change his/her habitudes. The interaction among the components allows monitoring the psycho-physical status through the data collected during gaming or during every day activities, to continuously tune the activities, in terms of exercise mix and challenge level and other gamification mechanisms updating continuously the elder profile according to exercise and monitoring outcome. Such wealth of data will allow also deriving assessment of clinical quality. State-of-the art Artificial Intelligence will be used to organize and control effectively all these interrelated components (WP3).

### Service robot

Giraff will be improved from being tele-operated to being autonomous, guided by the Virtual Caregiver, so that it becomes an active companion with whom to interact. New Giraff robot will be proactive in assisting the elder: it monitors his/her psyho-physical status surveying everyday activities, helps him/her searching for objects and remembering drugs, provides suggestions and feed-backs and guides him/her through adequate activities that can be administered by it or through other display (TV or android phones). We will explore here a framework, based on reactive planning such that Giraff can learn the best option to approach the elder, taking into account his/her status and idiosyncrasies, to provide an ecological approaching control. A novel solution based on distributed microphones with embedded DSP processing will be explore for launching alarms and calling Giraff from enywhere in the house (Task 5.3).

### Monitoring

Psycho physical monitoring of elder status will be performed by a novel approach that combines a robot to measure the elder movement in combination with a set of sensorized common use objects to measure objects interaction in gestures of typical everyday activities (WP5). The proposed monitoring will try to follow the evolution of both motion and pressure/force patterns adopted by the single user during the daily interactions with objects in order to recognize his/her performance changes. This new monitoring approach will be called transparent monitoring because the elder is not aware he/her is being monitored: the elder has not to wear any particular device or sensor and the monitoring system will be completely pervasive and distributed in the elder own environment. This approach will allow to acquire the elder natural behavior throughout his daily activities without splitting the monitoring stage from the ordinary life stage. The transparent monitoring is based on the principle that gestures are the expression of the motor and cognitive ability of the patient, as their pattern of variability can change selectively with pathologies, mainly Parkinson disease.

Regarding physical transparent monitoring, we will define a Gesture Degradation Index that analyzes the variability of the relevant motion and force parameters that characterize the gesture on which variability is reduced. An increase in the variability of these parameters can be related with degradation in motor control. We will fully explore such “motion signature” on different gestures like reaching and grapsing, for instance a cup or a comb, with different hand shapes in real settings of everyday life. Statistical parametric models, like Gaussian Latent Variable Models (GLVM), and the measurement of specific features, like for instance force pattern in the stance phase of gait or in early lifting objects, or homogenous plots of the orientation angles of the arm of legs segments, will also be evaluated. The collection of data is allowed by the monitoring technology developed in Robohome2.0 is particularly important as it would allow setting the ground for novel early detection of neurological decline. The aim of the project is analyzing the significance and sensitivity of several Degradation Indexes that will be defined in cooperation with clinicians. A similar approach will be developed to evaluate balance. A Dynamic Gait Index will estimate the stability of the person based on the motion and pressure data acquired through his walking aid. A walking stick can be equipped with accelerometers on its structure and force-sensing resistors mounted on the handle and eventually on the base, to provide spatiotemporal gait parameters and indicators of the weight support that the person needs. A study of the progression of those parameters will indicate if the person’s gait is becoming slower, unsteady or in increasingly need of the walking-aid assistance. Analogous sensors can be mounted on walkers, providing also indicators of the person’s status. Force-sensing resistors on the handles can monitor the weight borne by the walker, and the symmetry of the person’s posture. Whereas accelerometers placed on the structure and eventually gyroscopes integrated in the wheels will assess the spatiotemporal gait parameters. In both cases, Robohome2.0 will be able to acquire information on balance and gait stability also outdoors.

Scenario: Upon routinary physical monitoring, the virtual caregiver asks Giraff to monitor Helen while brushing her hair. Giraff detects that Helen leaves the kitchen after breakfast and enter the bathroom, Giraff approaches her and says to her “Hay Helen, have a nice day”. When it detects that the brush has been raised, it starts acquiring Helen’s movements with its 3D camera. The Virtual Caregiver combines the motion data with the pressure sensor profile and realizes that Helen brushing motion pattern was significantly changed from last times being more jerky and irregular, force time course measured by the brush was equally irregular in time. The Virtual Caregiver asks Giraff to repeat this observation in the next days and this change persisted. After five days of monitoring a warning is sent to Helen caregivers.

Regarding cognitive transparent monitoring, we will evaluate the proper concatenation of the different actions that constitute everyday activities . For instance, for preparing a coffee, we have to put coffee in the machine, put it on gas, pour coffee, take sugar, take milk, mix with spoon. Not the same order or set of actions is present. We can choose to put sugar first or after milk and/or coffee, according to the day preference. Proper mathematical models, based on Probabilistic Finite State Machines (PFSM), that can provide the forecast of each next action according to the elder attitude will be developed and deployed. The model will be able to extract high probability patterns of interaction with the environment and therefore compare the patient behaviour with the expected one. For instance: an elder who uses to put sugar in the tea, starts avoiding completely taking sugar. In this case the action next to pour coffee will be take milk, that is different from usual. This can be a warning for the person that attends the elder. Such a model will be developed and tested. Gesture segmentation itself is a very active area of research in computer vision especially related to hand motion. We will go one step forward here, exploring the use of motion and pressure data from the hold object to help segmentation. Auto-calibration of sensorized objects, taking into account Giraff Kinect video and range images captured will be developed.

To support early detection of degenerative diseases like Alzheimer or Fronto-Temporal Dementia (FTD), we will develop a system for the analysis of the profile of phone conversations. Very recently attempts to profile the characteristics of phone conversations have been proposed. We will analyze here the conversations in terms of pitch, voice volume and pace. In addition, stress will be detected using the innovative DYPSA algorithm, developed by SG, in the form of vocal folds opening and closure rates. The algorithm is now an established approach published in the Matlab Voicebox toolbox. We will analyze the determinants that allow to define a reliable emotional state of the elder and track it over time to detect meaningful mood changes that can be linked to disease onset (Task 4.6)

### Assistance

Daily assistance will be based on an automatic objects location service. Objects tags will be realized by using new miniaturized Bluetooth-4.0 (also called Bluetooth Low Energy – BLE) radio transmission. This can provide very low-power, with the ability to run for years on standard coin-cell batteries. Moreover, it constitutes a diffused transmission standard and a transmitted has very small dimensions, as small as a 50c Euros coin, , weighting a few grams, and it can be fitted or attached to the desired objects to track without changing the size the shape or the mass of the object. When requested to search, Giraff will move autonomously following the radio signal, until the object is at a very close range. The same functionalities will be provided through an app on smart phone. However, Giraff offers the possibility to locate an object also when the elder is outside his/her house or when he/she has not the phone with him/her or is looking for the phone itself.

Scenario Jessica does not find her keys, call Giraffs and asks for the keys. Giraff starts moving a bit around to identify the direction of maximum signal power associated to the keys ID and starts moving to the right towards the sitting room; it then moves towards the dining room until it gets close to a drawer on the top of which are the keys. Giraff calls then the elder. Jessica was very happy to find again her keys.

### Activity center

The activity center will be integral part of the environment assisting the elder. Education and activities are provided by Robohome2.0 heavily relying on gamification (WP4); this can be defined as the use of game for a purpose other than entertainment. Gamification leverage people's natural desires for competition and self-expression to maximize their attention and motivation to learn. At the core of gamification implementation is the design of the gameplay. Indeed, a good game design, nice graphics, effective gameplay, clear feed-back and proper challenge level all contribute to enter the player in a state of flow. Gamification leverage also on the reward systems, for instance: points or coins gained or achievements and levels reached certified by virtual badges that are shown clearly as a feed-back of achievement on-line an adequate time. Most effective gamification is obtained when users play in a cooperative or competitive mode embedding gaming inside a social dimension. All these elements will be effectively designed and implemented inside Robohome2.0 activity center. However, they are not sufficient to keep the user engaged for a long time as situations repeat after some times and therefore are not enough for long life gaming.

We will explore here how combining gamification with adequate statistical methods effectiveness, motivational and long lasting interaction can be obtained.

To this aim, we will largely improve the Intelligent Game Engine for Rehabilitation (IGER) developed by UMIL for the Rewire project, to incorporate a hierarchial motivational layer that involves: gameplay and reward system (extrinsic motivation) and long life (automatic narration).

To make exer-games compliant with elders, the details in the scene and their number should be adapted to the elder’s residual cognitive capabilities. A common effect of aging is decline of cognitive processing capability and, in particular, in spatial cognition, . This is well known in neurology, where after stroke, only simple and clear stimuli are allowed, and video-games targeted to acute patients have a real simple and basic graphics. Therefore, finding the proper level of detail allows increasing the understanding of the scene and therefore motivation. To achieve this, we will explore inside Robohome2.0 the innovative use of a level of detail (LOD) in the game design. LOD is a technique well known in the graphics domain, to decrease the complexity of a 3D object representation at the point of need. We will explore it both in the detail of the elements in the scene and in their number: a high LOD version of a scene, with lots of details, enrichments and animated assets on one end, and a low LOD version, in which only essential elements will be present in the scene, will be provided. Several intermediate versions will also be provided. Evaluation of the best resolution will be carried out throughout the project and an adequate measure of cognitive load will be defined to match the profiling of the patient.

The level of detail will be complemented by a controlled randomization of the scenarios and assets. As already explored by UMIL, this makes the patient feeling confronted with an always new game, while the gameplay remains unchanged. We will also provide to the patient some customization capability of assets, like for instance the game avatar, that can be loaded at run-time according to patient idiosynchrasies, such that the elder himself can choose and shape the appearance of the games that guide his activities. This allows to incorporate a key element to increase intrinsic motivation, . Lastly the pace of the game and the challenge degree will be adapted to the elder status automatically by analyzing in real-time the success rate to avoid that the game becomes either too easy or too difficult and the patient looses interest in it. Music and voice feed-back will be provided. The exergames represent only the first gamification aspect, however. We will also provide short-term extrinsic motivation under the form of feed-back from the Virtual Clinician Avatar that is constantly monitoring the patient, giving advice on the exercises and praising him/her when he/she performs correctly. Short-term extrinsic motivation is also empowered by additional gaming-like solutions: points and high-scores, colorful and meaningful feedbacks associated to high compliance and high knowledge degree about the therapy and the illness. This will be largely enhanced by the social dimension of Robohome2.0 mediated by the Community of users.

Long-term motivation represents a major issue when activity prolonged in time is required: games may get old soon and lose their appeal after a period of a few days of repetitive play, and the kind words may not be enough to keep the elder engaged for months. To this aim, we will develop automatic narration on a container chosen with the elders. The story will chain dynamically and automatically the different mini-games associated to the activities and it can possibly assume the form of a sport competition or a tale. In the latter case, we will fully explore the morphology analysis of fairy tales developed by the Russian school that has identified elements common to all fairy tales, like for instance the presence of an agonist and an antagonist, the fight, the elation and so forth. We will analyse the most interesting elements and we will extract few of them in order to be casted into a set of characters with a methodology based on ontology proposed by Peinado et al..

Two different approaches will be explored to combine the different episodes. The first one is based on stochastic finite state machines that will allow creating stories with different sequences of episodes and scenes on the same plot. We will also go one step further and consider graphical models, adding to the transition probability matrix, an a-priori distribution of the possible choices that takes into account the idiosyncrasies of the elder. The second solution is based on reinforcement learning in which each next episode of the story will be chosen in real-time according to a given cost function computed on the fly, . We will explore how to introduce coherence, consistency inside the cost function. Reinforcement will be provided by the elder him/herelf with a qualitative feed-back for instance in the form of a smiley. We will explore the use of instrumented objects as game input devices Task 4.9 transforming objects like a cup or a comb into a “magic potion” or a “magic sword” functional to the gameplay. We will also explore pressure sensing to realize magic effects like making objects disappearing thus exploring new gaming paradigms in which virtual everyday objects are used for playing. Moreover, designing an adequate gameplay, these objects can allow acquiring motion and pressure temporal profiles associated to specific movements of clinical value, like for instance the timing of stiffness increase in grasping or the time relationship between the orientation angles when raising it.

### Human Robot Interaction

As the robotic system in Robohome2.0 is going to be close partner to the elder, the need for a natural and effective communication is becoming a fundamental issue to support meaningful, fruitful long lasting interaction. This will be mediated by both the robot itself and the virtual caregiver with voice and graphical feed-back providing a very rich interfacing possibilities. We will fully exploited these potentialities inside Robohome2.0 (WP8) as follows:

(i) Long-term interaction and acceptance: current HRI systems tend to be based on single-session interaction. In robot assistive scenarios, where the same user interacts with a robotic companion for multiple sessions, we will include a memory system that keeps track of the history of interaction and support subsequent tasks in a predictive way, in accordance with the predicted user’s behavior and expectations. Their effect will be thoroughly evaluated.

(ii) Readability: users should be able to read the robot’s “cognitive processes”. Humans are finely tuned to cues and signals communicating our actions and intentions in inter-human interaction, but these cues are generally lacking from robots and this hampers natural HRI. Robohome2.0 will study how the behaviour of the robot can be generated to provide feedback and signal intentions and goals, by adequately filtering the reasoning process implemented by the virtual caregiver. Moreover, we will be identify the “compliant paths” for the cared elder. Indeed movement itself is a powerful mean of communication for human-human interaction and it is being currently explored in robotics. Finding the mode of approaching by Giraff that is most acceptable to the elder would increase robot acceptance.

(iii) Responsiveness: typical performance of a robot involves a considerable amount of processing (for example for automated speech recognition and natural language interaction), which inevitably leads to perceivable delays. As such during processing the robot seems to be inactive. Conversational fillers and back-channel feedback can be used to create the illusion of responsiveness, which is highly influential on acceptability.

None of the above mentioned qualities can be considered in isolation: long-term interaction and acceptance, readability, responsiveness and matching of perceived and actual ability all impact on each other. As such it is impossible to develop one quality while neglecting the others. Our research and development on the HRI aspects will focus on incrementally improving these HRI qualities through implementing the latest insights in the field of HRI and field testing with naive users (Task 8.1).

### Community of users

Robohome2.0 will take full advantage of the users community, offering the elders the possibility of comparing their status with other elders, in order to make it easy to find people with similar problems, helping preventing isolation and depression. Pattern matching technique applied on elders profile will allow to automatically suggest which groups an elder may find interesting to join, personalized news or other content, thus making the elders proactive increasing their engagement in the social community.

Through the community, elders will access thematic information on diseases, treatments, best practices, and lifestyle and so forth and new knowledge can be created through the interaction among users, increasing the trust in Robohome. To this aim, free and informed discussions between community members will be supported and a continuous osmosis with the most popular social networks will be supported. Through conversation in the community, socialization and externalization of knowledge will take place.

We will made available to clinicians a complete therapy management system, implementing a closed-loop workflow, through which they will be able to assess the elder status, review the results of the therapies and receive advice from the system based on the analysis of results. Using the portal of knowledge they will have access also to statistics and other processed data regarding therapy outcomes, scientific articles and specialized information in general. Elders will have access also to all the data stored in the system about their diseases and therapy, in an understandable fashion, so that they are always aware of the evolution of their condition, shorting the distance between them and the clinicians. This will facilitate changing the role of patients in clinical decisions from mere passive actors to active ones, reducing the “culture mismatch” between them and the health professionals.

## 1.4.2 Innovation potential

The Robohome2.0 architecture will introduce different systems in a harmonious way, creating a new and innovative standard for domestic assistance. Each subsystem has peculiar features able to improve the process of the virtual caregiver to help elderly people and their family to avoid possible risky situations. Although a full patent search will be carried out in Task 9.6, a preliminary patent search has allowed to highlight the highly innovation potential of the research activity proposed.

### Patent Search

Smart Drug dispenser. Robohome2.0 will try to create a low cost, compact and easy-to-use solution to help elderly people or the their family in a friendly way, because the medication dispensing cabinet for hospitals and drugstores are mainly dedicated to help nurses and clinicians during the handling of blisters and boxes or to improve the management process. They also try to prevent errors during the refill, but no one has been designed for a domestic use neither introduces specific components able to help people to take their own drugs. Patents that describes some medication dispenser are US8588964, US2013006415, CA2821616, WO2013142351 and CA2772899. This last is a really recent patent that describes a medication dispensing cabinets, developed to store and dispense in a controllable way a wide variety of medications. While some of the drawers may be unlatched and can be opened, other drawers may be locked in order to improve the control of the access to the medication stored in the locked drawers. This system doesn’t act as an “assistance” in the medication dispensing, but mainly as a supervisor for operators, able to prevent possible errors and limit the access to the medication. The claims are mainly focused at describing the locking system, which is not suitable for creating a low cost, domestic system able to help people to easily take their own drug.

Finding lost objects. To help people who lost keys, glasses or other personal belongings in house (and also outside it), there are some solutions already available in the market. They use radio signals to detect the remote transceiver, previously linked to the keys, for example. The main difference introduced by Robohome2.0 is that Giraff will find the smart objects and signal them in an automatic way, using standard RF solutions (i.e. Bluetooth), without the involvement of the owner. Giraff will be the finder, this is the more innovative aspect, whilst commercial solutions require that the people can move and find them. Moreover some systems require the use of a smartphone as a locator, which usually is the object which has to be found. Patents describing commercial solutions is US6366202 (1999), the US8130116 (2012) only introduces the configurable range of detection.

Sensorized objects for monitoring. Several researches and publications describe the use of sensorized objects (doors, chairs, wristwatch etc.) to analyze human behavior and specific actions in order to identify risky situations in the daily life. Some other projects in the past proposed the use of instrumented or special objects to create a personalized, home rehabilitation system for specific pathologies (e.g. rehabilitation of patients affected by apraxia, rehabilitation of rheumatic patients ). The novelty of the approach followed by Robohome2.0 is that the offered physical monitoring during normal daily actions will try to follow the evolution of both motion and pressure/force patterns adopted by the single user during the daily interactions with common objects in order to recognize his/her performance changes and compare them with the other indicators collected by the Robohome2.0 systems. The system will be completely transparent to the subjects, without the need of wearable solutions. For this reason a generic system to monitor “actions” or “behavior modification” (patents US6611206, US6968294, KR20090030868 and KR20090025924) could not be compared to the innovation that Robohome2.0 will introduce. The patent CA2275733 introduced the measurement, the monitoring and/or the analysis of motor control ability, performance, training and rehabilitation in an active way, with special instruments on order to prove assisted exercise. In Robohome2.0 the “exercise” are the normal daily activities, the “instrument” could be a cane, a spoon and so on.

# 2. Impact

## 2.1 Expected impacts

The Robohome2.0 proposal well addresses the expected impacts listed in the work program for the specific research topic. The consortium gathers experts from different disciplines with the final aim of approaching the issue of developing and testing a service robot able to provide elder monitoring, training and assistance at home in a holistic and exhaustive manner. Robohome2.0 2.0 aims at guaranteeing the needed reliability and easiness of use of all the ICT solutions offered, paying the main research efforts in their full exploitation and integration towards a system able to fit the user and his/her relevant stakeholders needs. Moreover, the multi-site nature of the final pilot testing phase, that will be performed in three different European municipalities, requires the implementation of a system that can be valid, usable and compliant with all these three healthcare systems. This implicitly means that the developed innovation meets the needs of the European and Global Market. Here below, we will describe how the proposal will address the specific expected impacts of the call.

Evidence for the benefits of service robotics developed, based on proof of concept and involvement of relevant stakeholders.

The service robot used in Robohome2.0 is embedded in what is configured as an advanced telemedicine service. Telemedicine has a long history; reviews quote it as beginning in 1948 when radiological images were transmitted for the first time by telephone from West Chester to Philadelphia, a 24-mile distance. Since then, electronics and computer science have allowed tremendous improvements and spreading of telemedicine applications, but, despite the technical maturity, telemedicine services are still limited and the market remains highly fragmented,,. Telemedicine is a tool that should be integrated as much as possible into the usual practice of medicine and social services,, however the integration of telemedicine service in healthcare systems is still an open challenge and requires high policy makers involvement to further develop.

Elders assistance is becoming one of the most appealing applications of telemedicine because of the possibility to keep the elders monitored and safe in their house, where they feel most comfortable. Moreover, late recovery in permanent structures is becoming one of the main issue to cope with in the next years, favoring the best lifestyle of elders. However, comprehensive solutions are still lacking. Although there are several experiences reporting that initial funding sources and reimbursement policies are the most important barriers that avoid widespread of telemedicine programs,, there is a study that deals with business models that determines how the application of telemedicine, in particular for post-stroke rehabilitation can generate positive cash balance. This study at outpatient clinics in Oklahoma concludes that 340 telemedicine visits are enough to provide positive net cash flow per year and they also expect to recover the initial investment within the 4th year of operation. In addition, a clinical trial carried out in Thailand gives us evidence that home rehabilitation programs for post-stroke patients help reduce disability better than traditional hospital care. Although the costs of including the patients in the telemedicine programs is high, this measure has been marked as a cost-effective by the Thai Ministry of Health. Indeed Assisted Living Environments may play a key role in renewing the system of integrated social and health assistance. However, apart the technological research, other issues strongly affect their capillary diffusion in European national and local environments. Overall it is necessary: 1) to assess and demonstrate the efficacy of the proposed assistance methodology; 2) to evaluate costs of the new solution versus the present operational modalities and point out economic benefits for all the involved actors, namely national and local socio-health systems, health institutions and citizens; 3) to design a new model of care delivery taking in account the new devices and related schemes for delivery and maintenance beyond the more evident clinical aspects.

The Robohome2.0 project, thanks to the participation of a wide spectrum of potential stakeholders and to the data collected in the pilot will allow to evaluate quantitatively the assistance outcome.

The stakeholder involvement is indeed an essential requirement highlighted by the Digital Agenda of the EC for 2020 and necessary to make feasible any proposed solution in the telemedicine field. Robohome2.0 will involve from the beginning of the project, the GPs, the reference hospitals, the caregivers and the social services in order to sensitize them and to steer the project according to the societal needs. This approach will assure that all of the project decisions will be taken according to the shared awareness and consciousness on the elder needs and make the final solution respondent to the healthcare service needs. The consortium includes different competencies in the health delivery panorama. This participation will allow the project to develop and supply solutions well accepted by the different health actors. The assessment of the effectiveness of the proposed service robot is complex and specific activities will be carried out during the project to get a reliable estimate of the overall impact of the use of Robohome2.0 system to the wellness of the elder. It is not possible to evaluate the time course of the decline of the single user independence and its progression towards frailty with and without Robohome2.0, within the Robohome2.0 time frame . Nevertheless, we expect to show that elders with Robohome2.0 tend to keep healthier and more active, by the time course, and this will come out from the functional indicators set-up for the pilot and will be compared to statistics over similar population. A usability analysis involving the whole community of user will be performed following the TAM approach (Task 8.3). The quantitative evaluation of Robohome2.0 will be performed collecting data on daily usage of monitoring, activity center, assistance and community by the elders and the other users. Given the number of elders that will be included in the pilot tests, the assessment of efficacy will remain preliminary but it will be very precious to give directions towards to design a future randomised controlled trial that will yield a valid assessment of efficacy of Robohome. A complete report on the assessment of Robohome2.0 effectiveness, compliance, usability and reliability in assisting the elders at home will be provided at the end of the project. Moreover, the multi-site nature of the final testing phase that will be held in three different European countries (Sweden, Italy and Spain) will guarantee that the proposed solution will be firstly adherent to the single National healthcare systems requirements but also to the ones shared at the European level. This implicitly means that the results of the pilot will be of interest not only at local level but also at European level.

In addition, we expect that the use of Robohome2.0 will help the family and the clinicians to recognize possible risky situations, making warning about the decline of the user which, on the contrary, might be disregarded by the caregiver. Indeed, the use of tele-operated and transparent clinical tests inside Robohome2.0 will help to keep a continuous evaluation of the status of the elderly and will drive prompt interventions in case of risk situations. Another crucial element to assess the assistive outcome will be the capability of the user to interact and use of the system, considering a low-trained old person. Indeed for all consumer robots the capability to interact with untrained or minimally trained people in everyday environment is a crucial issue.

These elements of assistance outcomes (clinical impact with respect to statistics, number of risk situations avoided or warned by the system, user feedback and usability of the system) will be the leveraging factors to prove the effectiveness of the use of the system and consequently its eventual economic benefit.

One of the key mission of EU robotics research is to accelerate the robotics innovation turning the results of the research and the technology development into competitive products and services at a much faster pace. Robohome2.0 will participate to this goal especially thanks to the representation of the complete supply chain in its consortium. In Robohome2.0 the market chain is fully represented (GIRAFF, SXT, SG), from the research (UMIL, POLIMI, UOP, ORU, BDIGITAL, UMA) to the robotic industry up to the global healthcare equipment suppliers (KORIAN) and end-users (PCL, SAS, KOMMUN. This will help in guiding correctly the research into real opportunities to the final users and to the market, ensuring an R&D&I strategy that maximizes the market impacts and intakes.

The crucial impact will be the development of the value chains based on module and component supply service sector as well as non technical value chains based on stakeholders and service providers. The technology transfer will be a key element in the wealth creation process across the value chain that derives from the investments in robotics. Robohome2.0 will support this process of technology transfer by properly addressing the guidelines of Intellectual property management into the CA and by fostering the strong link among research and industrial partners in the consortium.

Reduction of admissions and days spent in care institutions, and prolongation of time spent living in own home when ageing with emerging functional impairments.

Frailty, cognitive and physical decline are syndromes that progress slowly but constantly over time and the actual monitoring methods, such as brief and periodic visits conducted about every 6 months, or clinical evolutions based on patient reported questionnaires are not enough to early detect meaningful changes or significant but rare events such as fall, naps or transient neurological events that sometimes are just forgotten by the elder because of their rare occurrence. The increasing share of elderly population coupled with the related healthcare costs are a great incentive towards the design of new care models to assist the elderly needs. In particular, a modification of the structure and organization of the network of services, increasing the assistance on the territory is required.

ICT research and innovation can contribute in this reorganization, by supporting the shift of the core of the assistance from the hospital to the territory through innovative assistance models centered on the elder. Modalities of distribution of these new services are fundamental, as they can assure: (i) equity of access to the primary and secondary care, (ii) a better management of chronicity and continuity of care through a multidisciplinary approach and (iii) a valid support for emergency services.

Currently, the panorama is populated by a set of small companies that provide some of the needed services, while only a holistic comprehensive approach can support the effort of shifting the care model. In many European countries telemedicine services is diffused, in some cases it is sustained by national projects. Here below we are reporting two exemplary cases: the current situation in Spain and Italy.

The current situation of the elderly home care in Spain

In Spain, Regional Health Systems, part of the National Health System, have focalized their attention on e-health in the last twenty years, sharing the view and the development of systems and services based on telemedicine.

Recent studies made in Spain by IESE Business School and Telefonica (http://www.iese.edu/research/pdfs/ESTUDIO-305.pdf) revealed that 70% of chronically patients would like to use telemedicine if this would be possible, this percentage raises to 80% in the case of healthcare professionals.

In this study the healthcare professionals told that the expected potential benefits would be an improvement of the self-care and responsibility of the patient for his/own health and an increment in the comfort of the process, focused in the reduction in the number of visits and in the agglomerations. In addition they pointed at a better control of the problematic patients and the early detection in some medical problems.There are some important barriers to the generalization of this practice: knowledge, technology, costs, privacy and interoperability of the data. Possible solutions for these problems would be training for the healthcare professionals in the use of this technology, design of the technology focused in the usability, improvement in the codification systems and data collected and the standardization.

The current situation of the elderly home care in Italy It is known that due to cultural reasons, most of the Italian elderly people and their families prefer an “aging in place” option. Yet this preference encounters in practice the challenges of an underdeveloped community care system. In fact, even if in the last 30 years the expenditure devoted to long-term care and the provision of services in kind have grown, the Italian welfare state is still characterized by a ‘familistic’ approach where the public sector devotes a scarce amount of money to care (prioritizing cash benefits over services in kind) and the arrangement of care is largely left to families. The cash benefit in form of companion payment represents the main public long-term care input, which, in most of the cases is used to employ migrant care workers who are the main carers for the elderly at home. The working conditions of these sitters might be very hard, and they often need to spend most of their time in helping the elder in the activities of daily living, so that some other needs of the elder are necessarily neglected. The main task of family members often consists in organizing and monitoring the work of the sitters, and the life pace of the contemporary society often prevents them from spending time with the elder. In addition, with the companion payment family carers receive a monetary support but do not receive the information and counseling that in fact all the surveys show they want, especially with regards to the diseases that affect elderly people and the provision of healthcare. The system seems to have found an “equilibrium” as most of the users gain some practical advantages from current arrangements. Nevertheless, this equilibrium exposes the care for the elder to the risk of an unsatisfying quality, and if it is difficult to adequately meet the existing needs, short of time and human resources, it is very hard to implement good monitoring and preventing strategies against the development of a condition of frailty and disability.

In Europe the communication 689 of 2008 from the EC Commission was finalized to sustain the member states in the realization, on a large scale, of telemedicine services, through initiatives as: increase confidence in telemedicine services, get deeper knowledge in regulatory, ethical and legal issue, solve technical issues and support the market. The EC prompted each member state to identify priorities for that state and push towards development with dedicated guidelines. This was perceived by the Economics and Social Committee of the EC as a “cultural revolution” that should be framed inside the evolution of the health system in the whole Europe.

With such a background, the Robohome2.0 intervention would represent an additional aid and resource to favor a comprehensive care to the elder at home, integrated in and integrating the community of users surrounding the elder. Establishing a network of providers of social and health care, not only Robohome2.0 would represent an additional virtual care provider but it would also promote the creation of an integrated care system.

To make a home assistance solution feasible and deployable to the elderly the complete comprehension of the elderly needs is required. Indeed, the elderly with emerging functional impairments has the primary need of a continuous and personalized training and assistance at home possibly under supervision of both formal and informal caregivers. The possibility to offer such an integrated service at home seems the most ecological solution to train and monitor the elderly effectively. Robohome2.0 2.0 will offer an integrated solution including all the main ingredients: monitoring, assistance and evaluation at home. The approach proposed is an advanced tele-assistance, for which the presence of a remote caregiver, connected through internet to provide 24h assistance, is not required as much activity is delivered by the virtual caregiver embodied inside Giraff. This means that the Virtual Caregiver has to be embedded with advanced artificial intelligent algorithms that, taking advantage of all the information gathered by the Robohome2.0 system during the elderly daily life, can recognize the current user condition and lifestyle, and plan/update the assistive and training program accordingly. This would allow saving resources from rationalization of their use. For instance, some of the activities can be taken over by the virtual therapist, freeing the family and the system by some repetitive activity and reducing possibly the costs. The virtual caregiver will provide also clinical tests that will be both the tele-monitored gold standard tests and novel tests completely transparent to the user thus avoiding any memory effect when the user is not so compromised. These tests together with the assistance of formal caregivers only when necessary will assure the reliability of the assistance updates provided to the user. Moreover, by having access to a patient’s information, the care team will be able to make better informed treatment decisions which could reduce the number of physician office visits and hospital stays. Finally, keeping the elderly fit and in a good psycho-physical condition will avoid as much as possible traumatic events or urgent admission at Emergency Department. The community of Robocare2.0 fosters a high communication between stakeholders to optimize the use of resources, both institutional and voluntary, reducing the risks of hospital admissions and readmissions. The reduction of readmissions will also have a beneficial impact of the Health providers budget.

Thus, the comprehensive and multidisciplinary home care solution offered by Robohome2.0 2.0 will finally have a great impact in the healthcare economy. This solution represents a ground breaking personalized service and reverse the trend towards the institutionalization of senior and disabled citizens while ensuring that they enjoy improved living conditions in their home environment.

Improvement in quality of life of older persons and of their carers.

The most of the elderly prefer to live independently surrounded by all of their comforts and habits at home. When functional and cognitive impairments naturally associated to the ageing process, such as memory loss, decreased mobility and frailty occur the ability to live unaided become compromised. Therefore, a comprehensive and adaptive telemedicine solution offering a personalized and continuous monitoring, assistance and training can be an effective solution to promote the elderly independence at home and to improve his/her quality of life.

To design such a cutting-edge solution that can be deployed to the elderly independently on their primary disease, it is important to sensitize the community of the elders towards their empowerment in order to make them more active in maintaining an healthy and active lifestyle. This process should start in a prevention phase to maximize the envisaged results. The elderly have to be persuaded towards the concept that an active participation in monitoring their health status can promote patients’ adherence and compliance with treatment plans, help them assume more responsibility for their health and may prevent unnecessary emergencies. Moreover, the elders awareness that the service robot is serving them exactly at their point of need and in the full respect of their privacy makes the elders more confident about his conditions. The assistance provided by Robohome2.0 will be completely multidisciplinary and will cover the physical, cognitive, behavioural and social domain. The strict interaction between the elder and the community of users will allow the elder to participate to social events and activities promoting his/her social inclusion Thus, Robohome2.0 has the potential to support a greater change in individual attitude and behavior and it will slow down the progression of the elder decline. Our aim is to move elder far from just watching TV passively. We dream a society in which all the people can feel an active and useful part and not simply a higher weight as they increase their age. The collection of memories, the bank of time, the suggestions to youngers are all elements that would contribute to a less eager and more giving society. Moroever, having in mind that the effectiveness of a telemedicine solution is maximized only if the system can assure personalization, Robohome2.0 will be designed and deployed as a modular system providing to each person, only the modules needed to offer the specific level and the type of assistance. In Robohome2.0 personalization is achieved also in the activity center and continuously tuned by the virtual caregiver. Special attention will be also devoted to implement an interfacing modality that promote a good emotional relationship between the elder and the service robot in order to guarantee, easiness and even pleasure in the interaction and to increase the compliance in system use.

Robohome2.0 can help not only the elderly but also the formal and informal caregivers. Indeed, Robohome2.0 allow family members and care teams to respond to changes in an elderly person’s condition, help prevent accidents and emergencies, and coordinate necessary support. This coordination of the care will make the formal caregiver more aware of the daily patient conditions thus facilitating the decision making process that becomes more well-timed and successful. In the meanwhile the offered service will relief a bit the responsibility of the informal caregivers that can become more peaceful in the interaction and “management” of their beloved. In fact using Robohome2.0 they can trust on a secure system that connects the elderly to all of the interested care providers.

The Robohome2.0 solution will empower both the patients and informal caregivers to take care of their health and to be independent. This will be crucial to decrease the current divide that partly prevent the spread of innovative ICT telemedicine solutions in healthcare. Thus Robohome2.0 will optimize the sustainability, will increase the social inclusion of the users and will strengthen the relationship between rehabilitation team, users and caregivers thus producing a better coordination of the care process that is completely centered on the end-user wellbeing.

Global leadership in advanced solutions supporting active and healthy ageing.

One of the main features of Robohome2.0 is that it will allow the collection and analysis of large volumes of health data (lifestyle, physiologic variables, movement patterns, cognitive performances, health variables such as hearth rate or pressure... ). This information constitutes the foundations on which the efficacy of the provided system can be assessed during the final multi-site pilot testing phase. However, this feature will not contribute to that end if the information collected is not shared between partners. The interoperability between them is ensured by the use of a common platform (the Robohome2.0), but connections with existing infrastructures will also be needed, to decrease adoption barriers and to ease deployment. Interoperability issues are also very important when considering future developments and exploitation of Robohome2.0. A system in which interoperability at all levels (syntactic and semantic) has been taken into account since the beginning of the design will be easier to integrate within the current infrastructure of hospitals and it is more likely to be widely adopted. Therefore, Robohome2.0 integrability and interoperability will be guaranteed by its adherence to standards: Semantic, Terminology and coding (ICD (ICD-9-CM), LOINC, SNOMED, UHID, AIFA), and Synthactic (HL7, (CDA, Clinical Document Architecture), DICOM) standardization. Moreover, for modularity and extensibility, the software architecture will be designed and developed as a multi‐level one. Robohome2.0 implements a secure model, performing authentication, providing authorization for integrity and confidentiality of information. The specific focus in Robohome2.0 on the economic and ethical aspects related to the deployment of a service robot able to train and monitor eldest people at their point of need in their preferred environment will lead to a much richer understanding of the issues as well as the potential, which can then be applied when regulators need to consider the economic, social and ethical issues which Robohome2.0 will undoubtedly expose. The industrial partners of the consortium GIRAFF, SXT and SG are already working on advanced telemedicine technologies for elderly and will first pursue the exploitation of the project results. The experience of Robohome2.0 will be crucial for these industrial partners because the strict link with the most relevant stakeholders together with the multi-site nature of the final test will strengthen their competitiveness and will enable them to develop innovative solutions meeting the needs of European and global markets.

## 2.2 Measures to maximise impact

### a) Dissemination and exploitation of results

DISSEMINATION OF RESULTS Dissemination of project results into knowledge, products, and exploitation are key indicators of the success of the project. The project consortium accustomed to working and disseminating their efforts in the project. The various types of partners in the project strengthen the means by which dissemination can occur and optimize the possibilities to disseminate amongst different potentially interested target groups. Academic partners are expected to disseminate on a research level by means of publications to international journals, possibly to open access journals, participation to international conferences and workshops. Industrial Partners are expected to disseminate knowledge to the markets for increased potential exploitation. Clinical Partners will shape the information related to the project for the National Health Providers and will produce the material adequate to diffuse, and sensibilize the Health Provider of the EC countries. Finally End-user Organizations in each country will represent a good opportunity for Robohome2.0 to penetrate potential customer bases throughout Europe. End-user organizations in the project consortium are expected to spread effectively the Robohome2.0 project within their organizations. Dissemination stemming from the organization itself has the possibility to increase visibility. The dissemination strategy in this project will be based on the following three aspects:

1.	The knowledge developed by the project will be efficiently communicated to the academic, industrial business and general-public communities. Major activities will be publications, presentations at key conferences and workshops, dialoging with other FP7 projects in the same call and projects in Ambient Assisted living, telemedicine, teleassistance and rehabilitation framework. Finally, maintaining contacts and reporting to standardization bodies.

2.	Activities aiming to promote the awareness and hence the exploitation of the project’s results will be identified and pursued. Activities include organization of special events within major conferences or venues relevant for the project.

3.	Potential stakeholders will be identified and promotion activities targeting communication of knowledge and potential industrial/business applications will be undertaken.

Key Aspects and Target Groups	. The key aspects of the dissemination strategy are to define a concise, clear and convincing message associated to the project and its results. The project must successfully transmit the novelty and benefit of the results. Once established, the subsequent step is to identify the stakeholders and tailor the message according to the forum in which it is presented and according to the target audience. The following types of stakeholders/target groups have been identified:

(1)	The EC-ICT community: aim to raise awareness of Robohome2.0 objectives and to foster collaborations and exploit synergies between projects

(2)	The industrial community: aim to communicate and promote the results on a technological and business level.

(3)	The wider/general public: aim to raise overall awareness on the project and partners to local media. The aim to announce the general objectives of the project at startup and promote results as they become available in the project.

(4)	The healthcare professionals: aim to raise awareness of the project with specific focus on how it impacts the field of health and care.

(5)	The media: aim to promote the project results to specific groups which include journalists and online forums.

(6)	The scientific community: aim to disseminate and inform of project results and increase the knowledge in the field.

(7)	The health policy makers and local governments: aim to disseminate and inform of project results and business plan trying to foster a new model of sustainable healthcare. These target groups are aimed for general dissemination activities where the common thread is to explain the project and its results on various technical levels in order to increase awareness and promote cooperation and synergies. In addition to these target groups, a second level of dissemination will be employed specifically for markets and future exploitation. The target audiences for this second level are:

(1)	SMEs offering vertical business solutions extending to other domains

(2)	Educational Institutions

(3)	News Providers

(4)	Experts from the advertising sector

In this context, more business oriented promotion material is to be prepared. Specific opportunities that may be culturally related will fit under this second level of dissemination.

Dissemination Tools In order to reach the identified stakeholders and ensure an effective dissemination, the project foresees the following dissemination tools:

1) PROJECT LOGO. The first tool that has to be created prior to the real dissemination is the project logo that is the visual identity of the project. It is developed to reflect the projects vision and create a trademark for the project that is easily identifiable.

2) PROJECT WEBSITE. A project web site will be established (Task 9.2), including a presentation of the project objectives and methodologies and comprehending web facilities for communication and dissemination of information and progresses done by the project. Each partner will contribute to provide the scientific contents of the site. These contents will be collected, organised and formatted by UMIL and published on the web. The content of the site will be updated regularly on a monthly basis. Links will be created with relevant web sites. The web site will be divided into two main sections.

- A public section will be used for dissemination of knowledge generated by the Project to the public. A

devoted section will spread information about scientific results together with abstracts and, when

possible for copyright reasons, full text of published scientific papers. A discussion forum will be activated for the scientific community interested in Robohome2.0.

- A private section, which will be accessible only to Participants, and will be used to inform Participants on items such as general information on Meetings, Progress reports etc. This part of the web site can be used by each partner of the Consortium to download documents and run discussions.

3) PROJECT COORDINATED IMAGE A project coordinated image will be prepared and will include the project logo, a coordinated set of project tools for reports and presentation of the project results, and the project brochure to be used in different dissemination occasions.

4) PRINT MATERIALS Robohome2.0 will make use of print materials in a classical manner. Brochures will be produced in the project in different versions: a technical and popular brochure. The choice of languages for the popular brochure will be directly related to the testsite locations. Other translations may be included as dissemination opportunities are presented. Both brochures will describe the project in a concise manner as well as outline the main steps and goals. All partners should be well visible on the brochure. Other printed material can be generated on a need to need basis, e.g., for special events. Electronic versions of the material will be available for download from the project website.

5) EDUCATION The network of partners, the connections and the knowledge acquired within the project, will positively influence the didactic proposals that can be offered at a local or international level to students (undergraduate / postgraduate), to researchers or professionals (e.g. Master, Doctorate courses, Summer schools).

6) PARTICIPATION TO EVENTS Participation to relevant international event for standardization and dissemination such as the Continua European Symposium 2014, AAL forum 2014 and e-Healthweek 2014 and their following editions. A specific task of WP9 will be devoted to the participation in Trade Fairs and Exhibitions (Task 9.4). Robohome2.0 will hire stands at which hands-on technology demonstrations will be held to disseminate the projects results and prototypes.

7) PUBLICATIONS AND WORKSHOPS Publication of technical and research papers in well‐known scientific and industrial journals, magazines, newspapers (IEEE Transactions, BMC Journals, Elsevier Journals, ACM series) preferring always the open access journal to increase the target audience. Presentation of results at conferences, seminars, workshops (Tasks 9.3 and 9.4) both through speeches or posters. Within the initial dissemination plan, partners will contribute to create a list of possible conferences and events connected with the topics dealt with by the project in order to exploit all possible dissemination means. All intended publications must be put on the common website and submitted to all partners together with a request for permission to publish. Response of the partners has to be made within 4 weeks after receipt.

8) DATA and TOOLS SHARING Selected algorithms and methods implemented in the project will be made available to the scientific community under a GPL(or equivalent) licence through forums such as SourceForge. This will make it easier for other scientists to build their research upon Robohome2.0 results. Robohome2.0 will use open sources software instruments that will be made available for the design and setup of new rehabilitation programs. This will be a significant contribution to the research community.

EXPLOITATION The Robohome2.0 consortium will design a clear Exploitation Plan (Task 9.5) that will detail the following: identification of exploitable results, market analysis, industry and competitive analysis, commercial relations and business plan. The exploitation plan will be devised of exploitation tasks which will allow the consortium to identify Robohome2.0 related products that could have commercial applications, assess the opportunities and risks related to each product, evaluate the effort needed for commercialisation of the products and initiate contact with potential business partners of future clients. During the development of the Robohome2.0 Project a Consortium agreement and Exploitation agreements will be signed by all the companies taking part in the Robohome2.0 Project. The Consortium Agreement that will be agreed and signed by the partners before project commencement will refer to and define the exploitation rights within the consortium.

Management of intellectual property The Exploitation and IPR Management task will perform the monitoring of the ROBOHOME2.0 IPR activities and IPR work, and based on this create an IPR Management List. The assessment of ROBOHOME2.0 Intellectual Property Rights involves mapping the IPRs in view of the ROBOHOME2.0 deliverables (as a basis for providing stronger and more practical IPR agreements for these specific IPRs when needed). The IPR policies of the targeted standardisation bodies will also be considered in this context. The above described analysis, assessment and auditing of ROBOHOME2.0 IPR aspects will provide a basis for steering the technological activities (towards non-infringement of Third Party IPR), strengthening the collaboration (via understanding of the Consortium IPRs, and providing more appropriate agreements) and building up of ROBOHOME2.0 IPR itself.

All issues regarding confidentiality, IPRs, Background, Sideground, Foreground, agreement on exploitation rights, and clarification of each individual’s rights and obligations are going to be included in the Consortium Agreement, document to be signed by all partners before starting the project. The Project Manager is responsible for the use of IPR within the Consortium, according to the terms laid out in the Consortium Agreement. Primarily, the project aims to enrich and expand the state-of-art and state-of-practice of the home assistance and training methods deployed to the elderly in Europe. In order to carry out the work, the partners will develop and share know-how and technologies in many forms, including, but not limited to algorithms, tools, experiences and methodologies. The know-how exchanged between the partners may include, in certain cases, background. The partners are in agreement on the principles for the management of intellectual property, as summarized herein.

The consortium agreement will be written in such a way that it is possible for all partners to carry out their project work whenever it is dependent on transfer of knowledge from other partners, whether this is foreground or background knowledge. The consortium agreement will protect the legitimate IP interests of all partners by explicitly limiting the rights to background knowledge and, where required, even limiting the rights to foreground knowledge developed during the course of the project when there is no need-to-know or need-to-use.

In general, tools, methodology documents, benchmarks and case studies will be available to all; while some proprietary tools and algorithms developed by the partners may be available at the discretion and terms of their respective owners. In spite of the latter restriction, all the partners intend to pursue publications of the underlying principles of the technologies embodied in their tools in the appropriate academic conferences. Finally, all knowledge will be managed in accordance with the consortium agreement that will be timely prepared and signed by all consortium members

Management of Knowledge, Technology Transfer, Plans for the use, IPR & Patents All knowledge will be managed in accordance with the IPCA Consortium Agreement. Relevant discoveries will be patented for the use of ROBOHOME’s partners, and relevant licensees and spin-offs will ideally be transferred, so that both established companies and emerging companies can benefit from the ROBOHOME2.0 research.

The Foreground Management and Plans for the use will be updated by the IPR Policy committee which will consist of both technical and legal experts form the relevant partners. This group will report regularly to the Management Team and the Plans for use on new IPR generated during the project. The group will also prepare and regularly update the Foreground Management and IPR strategy of the consortium and present a Final Exploitation Plan to the penultimate and final meeting.

Foreground Management will be based on modern methods, such as BSCW on the private area of the webpage, which allow cooperative work on “living” documents. The Management Team is responsible for the day-to-day Foreground Management.

External dissemination and Technology Transfer: The wish and responsibility to publish research results and carry out Technology Transfer will be carefully weighed against the necessity to keep specific foreground within the consortium and not to endanger future exploitation. All partners provide information about planned publications to the consortium and the Management Team, so a publication can be delayed until patents applications etc. has been filled. This rule is valid up to 1 year after the end of the project.

Plans for using the foreground (IPR and Exploitation): The IPR regulations will be defined in the IPCA Consortium Agreement (CA). The terms in the CA deal with the protection of foreground related to joint invention, application for patents and further use of foreground. In addition to this, terms are defined for the access-rights to foreground, mainly based on the document on the provisions for implementing integrated projects. The CA – a legally binding document - deals with: 1) Protection of individual partners background. 2) Protection of IPR gained in the project (foreground). 3) Definition of the exploitation strategy (patents, licensing etc.). 4) A contingency plan that ensures the access to foreground if a partner (with project-critical IPR) leaves the consortium.

Results of the project will ideally be new software and middleware technologies. Special care will be taken to avoid obstructions to the exploitation of results. Partners, who own the rights of specific foreground developed in the project, are encouraged to exploit these results, licensing the results or at least transfer the rights in exchange for an appropriate financial compensation to partners willing to exploit the rights.

BUSINESS PLAN In the final phase of the project Robohome2.0 will also define a possible business plan to demonstrate the cost-effectiveness of the technology and develop a proper business models for the technology transfer to massively deploy Robohome2.0 within a sustainable healthcare system. The business model will be based on a service model mainly elaborated by KORIAN, a large service provider in the elders assistance field. In particular, a business plan will be elaborated on the basis of the four basic questions: What? Where? How? Why? To this aim the following sequential steps have been identified:

| STEP | PHASE | CONTENT | AIMS |
| --- | --- | --- | --- |
| 1 | Business description and context | Status analysis. Analysis of projects solutions on the market to support elders at home. Novelty introduced by Robohome2.0 in assisting elder at home. | Make explicit and structure the offer for selected business areas (clinical / social / comprehensive solution and so forth) in the context of assisting the elders at home. |
| 2 | Strategies and position in the market | Identify possible strategies to enter into the market (provider for the public / private services or directly to the elder). | Clear evaluation of the company strategies and evaluation of the business risk. |
| 3 | Development plan | Guide of all the decisions related to localization, production and marketing | Translate the first two steps into a concrete action plan, with timing and modalities. |
| 4 | Structure and Management | Evaluation of a congruent business structure with clear identification of roles and competences to achieve defined results. | Understanding of available resources and resources needed. |
| 5 | Financing resources | Definition of the financial resources that can be found to finance the business. | Identify financial provider |
| 6 | Economical-financial projections. | Projections of economic and financial return in a defined reference period. | Expected return and capital needs. |

In particular, in business description (phase 1), a clear market focus should be identified, for instance through successful use cases that can emerge from Robohome2.0 pilot. The economic evaluation is defined as comparative analysis of alternatives based on the benefits and costs. These will be composed of direct and indirect costs. Incremental Cost-Effectiveness Ratio (ICER) will be considered as:

ICER= CostRobohome2.0−CostTraditionalCareEffectivenessRobohome2.0−EffectivenessTraditionalCare

Direct costs of the National Health System are mainly costs of primary care and ambulatory visits, and drugs. In particular, the “sliding doors” mechanisms of evaluation, that is based on the number of admissions to primary cares, can be used as these data are available at SAS and PCL sites, deriving a standard cost for each group of elder with similar clinical profiles. Direct costs for Robohome2.0 will also incorporate the costs of the technology of Robohome2.0 and its technical maintenance over time. Indirect costs will also be identified. These can be, for instance, care-givers time, nurses intervention, devices needed both for assistance and for clinical monitoring. Quantification of indirect costs will be carried out in collaboration with Public Health Providers (SAS, MUNICIP and Lombardy Region) in the three states in which the pilot will be carried out: Spain, Sweden and Italy.

In the phase of structure and management (phase 4) of the business plan RTL of the different components (Section 1.3.2) will be fully taken into account in estimating the resources required to bring all components to the product level and to evaluate the time to market of several components. Such business plan can be the basis of any company that would enter into the field.

### b) Communication activities

Different communication activities to promote the projects results and findings among public audience will be established. The aim will be to raise globally the perception of the new possibilities offered to the elder for assisted living through grounded results. Conventional channels like exhibitions, meetings, scientific open access publications as well as non-conventional ones like LinkedIn, YouTube, Facebook, will be exploited to diffuse the project results. Given the variety of target audience and stakeholders the communication activities will be always tailored to the audience needs and knowledge in order to maximize the understanding. The communication activities will be leaded by the coordinator with the major support of POLIMI and PCL. Thus, the communication offices of these institutes will be involved and will be exploited to find the best contacts and communications means for the project.

Communication activities will include:

1) Robohome2.0 Website As already explained in the previous section, the Robohome2.0 website will be one of the main promotional tools of the project. It will be here that news and latest information about the project will be available. Public deliverables will be placed on the website as well as practical information about the project. It will be the responsibility of all partners to provide information regarding updates and news to the website when publications, events, news clippings and articles occur.

2)Newsletters Robohome2.0 will produce a regular newsletter in electronic and printable formats. The newsletter will be generated every xx months of the project and contain a list of latest achievements and initiatives in the Robohome2.0 project.

3) Press Releases Press releases will be made at regular intervals throughout the project and are initiated directly from the coordinator exploiting the tools already established at the universities. A press release will be made at the start of the project in each of the project partner respective countries. Partners wishing to put country specific press release should obtain permission from the coordinator.

4) Articles Publication of scientific articles is an important aspect in order to disseminate the results, and as Robohome2.0 represents technical, social and medical aspects of at home monitoring and rehabilitation through gamification, a wide range of venues are suitable for publication. Suitable fields and communities for Robohome2.0 publication include:

• Technical journals in Computer Science related to sensor networks, robotics, artificial intelligence and human robot interaction.

• Journals and conferences in Health Sciences

• Popular Magazines related to social welfare and care

• Journals and magazines on standardization for ambient assisted living.

5) Project videos During the project different videos will be created in order to disseminate the project results. These videos will be made available to the general public not only by means of the project website but also through the you-tube channel. It will be possible to include in these videos also the direct experience of the elders involved in the final pilot testing phase to demonstrate the usability of the Robohome2.0 platform. It will be possible to create videos in four different languages: Italian, Swedish and Spanish because of the multisite pilot testing phases and English to reach the global audience.

6) Social Networking Social networking is rapidly becoming a common means to disseminate EU projects. Robohome2.0 will endeavor to use social networking where relevant. Keeping in mind that the end user targets are typically an elderly generation with less exposure to online social media channels, the use of social networking will be kept to a reasonable amount in relation to the impact for dissemination. Setting up Twitter and/or Facebook.

7) Participation in External Conferences and Events Participation at workshops and conferences are encouraged to present project outcomes. In addition to presentation of scientific results as talks, Robohome2.0 may also have a stand or booth at suitable venues.

8) Organization of workshops

A dedicated workshop will be organized before the end of the project to sustain awareness about the

project and its results. The workshop will be possibly included in an international conference to increase the visibility in the ICT and healthcare scientific community.

9) Brochures and leaflets

Brochure and leaflet will be prepared at the beginning of the project and at least every year will be updated to the ongoing results. They will be distributed during the main events, conferences workshops and meetings with audience in which each of the partners will be involved

10) Testsites

As the long term handling of a test site presupposes a good relation with the community and elderly organizations, municipalities and general organizations surrounding the elderly, the projects needs to be viewed positively in such organizations and the general public. The establishment of a test site can give rise to contact with press/media and good results in test sites should be well spread in order to promote further test sites. Conversely the promotion of the project can lead to finding several candidate test sites. Therefore, an active promotion of the project with testsite specific activities is to be done. This includes spreading brochure material. This printed material is to be sent to target organizations from which test site candidates will be recruited. Results from test sites will naturally be included in the scientific dissemination strategy such as publications but non-technical results should be promoted via newsletters and press releases. The following table outlines the possible communication channels and how they reach to the various target groups. The selection of tools varies depending on the target audience.

|  |  | Target Group |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | EC | Academia | Industry | HealthCare Professionals | General Public | Media |
| Communication channels | Website | X | X | X | X | X | X |
|  | Newsletter |  | X | X | X | X |  |
|  | Press Release |  |  |  |  | X | X |
|  | Publications | X | X |  | X |  |  |
|  | Videos |  |  |  |  | X | X |
|  | Social Networking |  | X | X |  | X | X |
|  | Participation to conferences |  | X | X | X |  |  |
|  | Organization of dedicated workshops |  | X |  | X | X |  |
|  | Brochures and leaflets |  | X | X | X | X |  |
|  | Testsites |  |  |  | X | X |  |

Table 1 Communication tools used in Robohome2.0

# 3. Implementation

# 3.1 Work plan — Work packages, deliverables and milestones

## 3.1.1 Overall strategy and general description

The Robohome2.0 project will build on 10 work packages. WP9 and WP10 will cover transverse activities, namely: Dissemination and Exploitation and Management activities, while the other work packages will be devoted to the design, the development, the integration and the evaluation of the complete Rohome2.0 System.

WP1, Functional Specifications: will be carried on the basis of the needs and requirements of end-users: clinicians (SAS, PCL), caregivers (KORIAN and KOMMUN) and elders (PCL, SAS and KOMMUN). The Roohome2.0 platform will be designed to support the elder at home and to allow the caregivers and clinicians a reliable supervision. To this aim, a clear picture of the functionalities required for monitoring (the elder lifestyle, his/her psycho-physical status and the environment), for assistance in every day life tasks, for activities and for evaluation will be drawn and documented in D1.3. Modality for functional evaluation through the pilot (WP8) will also be defined, with case use scenarios (Task 1.6). Ethical submission documentation will also be prepared (Task 1.7).

WP2, Implementation requirements: will be carried out in pipeline with WP1 with the aim of defining the technical specifications of the system and of its components. The most suitable solution will be identified. Given the large number of components envisioned, particular attention is put on modularity and interoperability: diffused standards, hardware and software, will be used. The modality of evaluating the components and the whole system will be set as well as the requirements in terms of availability, dependability, accuracy and latency (Task 2.6).

WP3, Virtual caregiver and service robot: Infrastructure specifications will be defined. Autonomous navigation of Giraff will be developed and elder tracking with 3D camera implemented. The virtual caregiver that controls the entire system through state-of-the art AI functionalities will be developed. Functionalities that assist the elder in everyday tasks will be also implemented (Task 3.8, 3.9). Teleoperated clinical tests will be realized (Task 3.7).

WP4, Activity center: will provide activities under the form of adequate exer-games built inside the gamification framework. Automatic narration will be developed as a gluing elements of mini exer-games developed to guide each activity (Task 4.3). Personalized educational exer-games will also be developed (Task 4.4). Gaming results will be made available to the community to increase socialization (Task 6.3) and interaction data will be made available to the Virtual Caregiver for evaluation, assessment and tuning (Task 3.3, Task 3.6).

WP5, Monitoring systems: through networks that monitor the environment (Task 5.3) and collect physiological measurements (Task 5.6). A transparent monitoring system will be implemented in Tasks 5.1 and 5.2. The voice distributed command system used to call Giraff will be implemented in Task 5.5 and social monitoring in Task 5.4.

WP6, Community of users: Realization of a dynamic community in which the elders can find a suitable group of pairs with whom to interact. Motivation to use the community by elders will be addressed since its design (Task 6.1 and 6.3). The community will also allow the carers to access data from monitorings and activity center and will receive warnings from the Virtual Caregiver (Task 6.5).The Apps that allow access to Robohome2.0 functionalities thorugh a smart phone will be implemented in Task 6.6.

WP7, System integration: it will take care of the final integration of all the components identified above. To achieve most effective integration early testing of the components will be carried out from the technical and functional point of view in living labs in ORU and SAS to derive feed-backs from, family members, physicians, informal carers and elders themselves and suggestions to improve.. UMIL will set-up progressively a Robohome2.0, integrating and testing the components developed in increasing stages in WP3,WP4, WP5, WP6, under the guidance of GIRAFF, that will test and validate the final platform on its premises. D7.1, refined functional and technical specifications, due at M24, will provide the final view of the specifications of Robohome2.0. This task will end with D7.2 – Report on technical and functional tests of the Robohom2.0 system.

WP8, Robohome2.0 pilot: It will allow the testing of the system in real conditions and tuning it according to the feedback collected from elders, caregivers, family members, physicians and therapists. This WP will allows us to come with quantitative comprehensive evaluation of Robohome2.0 and the new modality of assistance offered by it. Functional and behavioral analysis will be a fundamental part of this evaluation.

WP9, Dissemination and exploitation: Conventional channels, like exhibitions, meeting, as well as non-conventional ones, like LinkedIn, YouTube, Facebook, will be exploited to diffuse the project results. Most effort will go towards private and public structures that offer support to elders.

WP10, Management: will provide all the support to the project, through a structure that will promote a shared view of the project and minimize risks. A strong emphasis will be devoted to ethical issues, through a dedicated ethical review board and to IPR management through a direct involvement of UMIL technology transfer office in the evaluation of project’s results.

## Timing of work packages and their components (GANNT Chart)

## Detailed work description

### WP1 – Functional specifications

| Work package number | 1 |  |  |  | Start date or starting event: |  |  |  |  |  |  | M1 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Work package title | Functional Specifications |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Participant number | 1 | 2 | 3 | 4 |  | 5 | 6 | 7 | 8 | 9 | 10 |  | 11 | 12 | 13 |
| Participant short name | UMIL | ORU | GIRAFF | UOP |  | SXT | PCL | POLIMI | BDIGITAL | SAS | KORIAN |  | SG | UMA | KOMUNN |
| Person-months per Participant | 5 | 7 | 0,5 | 4 |  | 0,5 | 9 | 5 | 2 | 8 | 9 |  | 2 | 2 | 4,5 |

Objectives: - To identify users and use cases of the Robohome2.0 system. - To define all the functionalities required to Robohome2.0 and define user-case scenarios. - Prepare the ethical submission document.

Partners role: PCL leads this WP for its large clinical experience with the elderly and strong tights with social services. Other main actors with similar profile are SAS and KOMMUN, thus combining the experience of 3 different couuntries. KORIAN provides the vision of a service provider. UMIL brings the experience in coordinating projects aimed to develop e-Health platform for rehabilitation promoting interaction between clinical and technological teams. BDIGITAL will provide the possibilities offered by virtual communities. Solutions that will be usable by the elder will be preliminary evaluated by UOP. Technological offer on monitoring , robotics and vision will be provided by POLIMI, UMA, GIRAFF and ORU. Description of work. We start from the elder’s and other Robohome2.0 users’ needs to move towards functional specifications to implementation specifications addressed by WP2 and then to implementation carried out in WP3, WP4, WP5, WP6, integration in WP7 and testing in WP8. Implementation specifications may eventually lead to adjustment of functional specifications (PERT diagram). These methodologies will lead to the definition of the user requirements, and of the design of the metrics to evaluate the user experience and acceptance of the robot. User specifications and functional requirements will be written in a comprehensive technical report (D1.1), publicly available, that lays the ground for the future development of the Robohome2.0 system modules. To achieve effectively WP2 goals, two approaches will be followed. The first approach, bottom-up, is based on soliciting the end users expectations by means of a continuous feedback through questionnaires, interviews and focus groups according to the different needs and organizations in the different pilot stes. This approach will be implemented looking directly at the users expectations through questionnaires, created specifically for each group of users, starting from the functionalities identified in the DoW. The second approach, top-down, is based on identifying functionalities and their operation modality through UML language or conceptual maps. The resulting schemes will be used to elicit further feed-back from the end-users. The data gathered from these two approaches will be integrated into a coherent and complete set of functions. In parallel, a few meetings will be organized in clinical sites in which the technology that can be used in the project will be shown live and discussed along with videos and mock-ups and discussed with caregivers and clinicians who will illustrate the suitability for their approach to care. A set of multiple applicability scenarios, spanning from the old independent adult to the chronic disabled person living at home will be defined and guidelines and metric for functional testing will be defined. This will include the acceptability by the users and their caregivers. Refinement of functional specifications will be obtained from the analysis of implementation requirements and from the early stages of the development of the components. Task 1.1(M1-M4) Identification and characterization of Robohome2.0 users (PCL, POLIMI, KORIAN, SAS, KOMMUN) Robohome2.0 groups of users will be identified: 1) the elder, 2) people with a technological role 3) people with a functional role: clinicians, care-givers, relatives and so forth. For each of these categories required functions are identified along with the relationships between the functions. Unified Modeling Language (UML) and conceptual maps can be used for instance to clarify such processes and roles. Main users are elderly subjects who are at risk of frailty, cognitive impairment, dependence and social exclusion. Frailty syndrome is defined as a state of excessive vulnerability to environmental factors accompanied by a progressive decrease in the functionality of many organs and body systems. Beyond this classical phenotype definition, the term frailty is operatively used in geriatric medicine to identify older adults who are at increased risk for future poor clinical outcomes, such as development of disability, dementia, falls, hospitalisation, institutionalisation or increased mortality. Inclusion/exclusion criteria will be defined on the basis of physical and mental conditions, their availability and willingness to be involved and, finally, of their living environment. In particular, compliance with technology has to be appreciated. A plan (including insurance cover) for emergency situations that might occur during the pilot study will be designed in collaboration with the EBR. Assessment measures will be identified to be used before entering in the Pilot and and the end. Primary outcome is the evaluation of the fraility condition. According to the principles of a Comprehensive Geriatric Assessment, the following specific outcomes will be measured at baseline and at the end of the pilot study: Measures of physical performance that can be Tinetti scale, Short Physical Performance Battery (SPPB), 4-m walking speed, balance and chair-stand tests; muscle strength (hand-grip strength); functional (ADL and IADL); cognitive status (MMSE); mood (Geriatric Depression Scale); nutritional status; quality of life ; satisfaction; frequency of access to Emergency Department/ hospitalization/ institutionalization; adherence to therapy; quality of life and satisfaction of the caregiver. Additional specific outcomes might be added according to the phenotype of the elder and his lifestyle (for example, HbA1c for a diabetic elder; number of daily naps). Task 1.2(M1-M12) Identification of the Robohome2.0 activities and assistance functions (SAS, KORIAN, PCL, KOMMUN, UMIL, POLIMI) A wide range of exercises aimed to counteract physical and cognitive decline will be defined according to current geriatric practice. Additional suggestions will be provided: a) A set of themes that can be suitable for the largest elder population to contain the exer-games, taking also into account gender difference. b) The parameters that determine the difficulty and that have to be tuned to the elder status (e.g. amplitude, accuracy or speed of the movement). c) The parameters to monitor the elder’s performance quality in terms of intensity, time and of correctness. d) Possible constraints on the design associated to elder characteristics, for instance elements size and contrast. e) Definition of the elements that concur to motivation. An effective and balanced reward system will be defined as well as several possible ways of defining levels of difficulty of the exercises in front of the elder residual capabilities. Most suitable card games to improve socialization will be defined. Assistance functions A set of objects that can be lost will be identified and the requirements of the smart drug dispenser defined. Groups of possible diets will be also identified in this task. Functional specifications of these services will be identified along with real case scenarios for testing. Task 1.3(M1-M12) Identification of clinical monitoring, transparent monitoring and environment monitoring functionalities (PCL, SAS, KORIAN, KOMMUN, BDIGITAL, POLIMI, UNIMI) Aims of clinical monitoring will be clearly identified and use case defined and reported in D1.3. Possible implementation modalities will also be described having in mind the whole spectrum of aspects to be monitored: A. Monitoring Cognitive and physical performance through exer-gaming provided by the activity center. The activities offered by Robohome2.0 and defined in Task 1.2 allow to collect data that are useful for monitoring the elder. These can be for instance the time required to complete a “memory” game or a puzzle or a physical exer-game, the score, the average number of points lost in card games, and so forth. Design of scenarios to administer classical psycho-physical tests with remote supervision of the clinicians are designed. B. Monitoring cognitive and physical decline through transparent monitoring. Suitable scenarios and associated objects and modalities is defined along with data accuracy Possible parameters that can be suitable as Degradation Indexes will be defined according to physiological knowledge on normal functions. Most suitable parameters that can be derived from the analysis of phone conversations is identified. C. Monitoring the elder lifestyle through environment sensors- Functions will be defined along with scenarios such us the number of hours of sleep, number of times the user goes to the toilet or sits in front of TV. D. Monitoring social interaction. A baseline of social attitude of the elder will be measured at pilot start with relatives and caregivers. Functions to measure deviations will be defined, like log book, use of the community, frequency of going out, input from caregivers provided from instance through on-line forms provided by the community (Task 1.4). Additional information is derived profiling phone calls. E. Monitoring Health Conditions. Physiological parameters that are required to monitor health conditions will be identified according to modality and frequency: e.g. blood pressure, heart rate, glucose concentration or saturation. Conditions that have to trigger an alert to the elder GP will be defined on the basis of the parameters measured and the elder clinical profile (Task 1.6). Task 1.4(M1-M12) Identification of the community of users functions (KORIAN, SAS, PCL, KOMMUN, BDIGITAL, UMIL) A role will be defined for each type of user and each role will have its own assigned permissions and specific functions. In particular, the relationship between the caregivers, the clinicians, the elders and the other possible users of ROBOHOME2.0 platform will be identified. Functions required to provide virtual interaction between community members, as also to run and review personalized activities adapted to the elder status will be identified with a tight cooperation between technological and clinical partners. Task 1.5(M1-M12) Identification of the functions of the virtual caregiver and of the service robot (PCL, KORIAN, SAS, KOMMUN, POLIMI, OUR, GIRAFF, UMA, UOP) A clear definition of: a) the recommendations required to the caregiver as output of Task 3.5; b) modalities of tuning of the exer-games and activities to the elder profile and statues and c) situations detected from monitoring and activity data that need caregivers or GP assistance. Clear definition of situations in which Giraff autonomus navigation is triggered, and constraints that have to be considered when planning the path. A definition of compliant approaching paths are defined as well asinteraction modalities (gesture, voice). Task 1.6(M7-M12) System functional evaluation (PCL, KORIAN, SAS, PCL, KOMMUN, UMIL, UOP) Given the expected interplay between the elder and the robot, and given that the type of assistance provided is multi-dimensional, the evaluation task will be complex and based on a set of indexes. Overall, the system activity will be evaluated using questionnaires for three comprehensive aspects: 1) measures for elder’s compliance with the intervention; 2) measures for elder’s satisfaction with the intervention; 3) customized measures for the achievement of the cognitive, physical, social and clinical objectives set at the beginning of the intervention. Measures for elder’s compliance with the system will be the frequency of use of the system and the rate of completion of the activities proposed. The elder’s satisfaction will be evaluated using the Technology Assessment Model (TAM) aimed to assess the impact of the technology, , according two main aspects: (i) the perceived usefulness and the perceived ease of use. The questionnaires will be administered before and at the end of the pilot to all actors, including family/non-family caregivers involved in the intervention. Moreover, since the specific typology of intervention, among the range of functions that Robohome2.0 can provide, will be customized according to the characteristics and the needs of each elder, users will be asked to define their own metrics and modalities to evaluate the overall effectiveness of the intervention, which might involve the cognitive, physical, social and clinical sphere. Finally, adequate clinical tests will be defined to assess the elder; data will be collected before and after Robohome2.0 usage and will be usable for designing a later randomized controlled trial that will compare Robohome2.0 technology with standard assistance provided by socio-health services. Such tests will be used in Task 8.4 for assessment. Task 1.7(M7-M12) Ethical submission (PCL, KORIAN, SAS, KOMMUN, All partners) Being volunteers and patients involved in the intervention, the pilot description will be submitted for approval to the competent Ethics Review Boards of SAS, PCL and KOMMUN. Together with the Ethics Review Board a consent form for participants will be elaborated. It will have at least the following fundamental components: it will be describe all the information concerning the characteristics of the intervention, including the possible expected risks; it will protect data confidentiality; it will guarantee subject’s freedom to refuse to participate to or to withdraw from the study at any time without affecting the preceding management plan. The consent to participate will be sought from the elder, but also from other possible users involved in the intervention (e.g. family/non-family caregivers). Task 1.8(M13-M18) Refinement of functional specifications (UMIL, PCL, SAS, KOMMUN, POLIMI, ORU, UOP, BDIGITAL) The specifications set in D1.1 will be reanalysed taking into account the constraints posed by technical offer and early implementation. The final functional specifications have still to match users requirement although with different modalities. For instance, a given physiological measurement turns out not reliable with available technology and the presence of a nurse or of a caregiver becomes required. The final specifications are collected inside D1.3, publicly available, that will offer the state of the art in assisted robots in smart environments.

Deliverables: D1.1 [R, CO] Preliminary functional specifications (PCL, M12). Elders inclusion / exclusion criteria will be defined. Required functionalities for monitorings: environment, psyho-physical, social and lifestyle, assistance both in everyday tasks and in therapy adherence, activity center and evaluation will be defined. Specifications of clinical tests will also be provided. All specifications will be supported by use-case scenario design. D1.2 [R, CO] Documentation for ethical commission submission (PCL, M12) D1.3 [R, PU] Final functional specifications. The functional specifications in D1.1 will be refined according to the definition of the implementation requirements in WP2 and to early testing in WP8. The final functional specifications represent therefore a complete document of the functionalities of a service robotic platform that can support the elder at home and will be fully exploited in WP9, as a scientific publication and as a publication targeted to policy makers (UMIL, M18).

### WP2 – Implementation requirements

| Work package number | 1 |  |  |  | Start date or starting event: |  |  |  |  |  |  | M2 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Work package title | Implementation requirements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Participant number | 1 | 2 | 3 | 4 |  | 5 | 6 | 7 | 8 | 9 | 10 |  | 11 | 12 | 13 |
| Participant short name | UMIL | ORU | GIRAFF | UOP |  | SXT | PCL | POLIMI | BDIGITAL | SAS | KORIAN |  | SG | UMA | KOMUNN |
| Person-months per Participant | 3 | 6 | 1 | 11 |  | 3 | 5 | 6 | 4 | 1 | 4 |  | 2 | 6 | 2 |

Objectives - Define the technical specifications of the Robohome2.0 platform and identify the most suitable components in terms of reliability, costs, availability. - To identify and design the main HRI interfacing modalities to maximize compliance and effectiveness. - To identify and design the main GUIs that will be displayed on the different displays used (Giraff monitor, TV monitor, smart phone and PC). - To design technical evaluation tests of the system components and of the whole platform.

Partners role: The implementation requirements are aimed at finding the best technology and implementation that matches the requirements in WP1. UOP for its experience in working with robots and users is the ideal candidate to lead the work. BDIGITAL will mainly contribute in defining the implementation specifications of the virtual community and of environmental monitors, POLIMI for designing the assistance system and with SXT and UMIL in designing the psycho-physical transparent monitoring. UMIL will provide its experience in designing game centers acquired in the FITREHAB and REWIRE project. UMA and GIRAFF will provide experience in working adeveloping Giraff. Clinical partners, PCL, SAS, and KORIAN will provide the users point of view. Description of work WP2 has the role of defining the technical specifications of the Robohome2.0 platform and of its components to comply with the functional specifications set in WP1. A tight coordination with activities in WP1 is needed and will be guaranteed by the PC. Cost, reliability, dependability, usability will be considered. The SW/HW specifications of all the components will be identified: robot, virtual caregiver, activity center, assistance, community and the different monitoring systems (environment, physiological parameters and lifestyle), so that the functions identified in WP1 are made available. Devices and applications that already match given functionalities will be considered. Modalities of integration of off-the-shelf and specifically designed components will be defined within a modular architecture suitable to be expanded already during the project. Given the fast pace of development of new sensors and physiological devices, Robohome2.0 will reserves the opportunity to integrate novel sensors that are made available in due course. Task 2.1(M2-M9) Identification of the technical functions for clinical monitoring and assistance (SXT, POLIMI, UMIL, GIRAFF, ORU, UMA) The components of the micro-architecture that constitutes the sensing module that provides pressure and motion of objects of everyday life is identified to match specifications set in WP1. Pressure and motion range and accuracy, sampling rate, maximum delay, drift, non-linearity and all the other characteristic parameters are defined as well as synchronization modalities. Recharging modalities and data transmission are also specified. When monitoring is carried out by Giraff camera, the joints and degrees of freedom that have to be tracked is identified. Specifications on size, style and graphical format of questionnaires for cognitive monitoring is defined. The micro-architectures for markering everyday objects and for remotely controlling the smart drug dispenser are identified, a proper miniaturized design produced and the transmission protocol defined. The components that allow measuring the physiological parameters with clinical validity will be identified with the best network structure. Task 2.2(M2-M9) Identification of the technical specifications of the environment and lifestyle monitoring (BDIGITAL, POLIMI, UMIL, GIRAFF, ORU) The the off-the-shelf components that have to be assembled to produce a reliable and accurate sensing embedded inside the environment, according to specifications set in WP1, will be identified and characterized. Temperature, luminosity, humidity, gas alerts, opening entrance door, presence in the rooms, will be among the monitors of choice. Sofa and bed pressure mattress as well as mattress humidity are among the possible measurements taken on lifestyle. For each of these measurements range, frequency, accuracy is defined. The most diffused networking systems, like z-wave, is analyzed and reported in D2.1. Task 2.3(M2-M12) Identification of the technical specifications of enhanced Giraff and activity center (UMIL, ORU, GIRAFF, POLIMI, UOP, SG, UMA) The autonomous navigation system of Giraff is defined by UMA to meet specifictions set in Task 1.5. Reacting navigation planning is fully explored. The most suitable framework to implement the reasoning engine based on DL will be identified, taking into account its speed and scalability. The conditions required by the distributed voice control system, are defined in terms of microphones aperture, signal to noise ratio and the words that have to be recognized. Languages differences will be addressed. The solution based on local DSP processing, envisaged in Robohome2.0, will be compared with a centralized solution based on Microsoft APIs for voice recognition, made available since Windows 7 OS. The most suitable platform to develop the activity center is identified, taking into account the compatibility with Windows OS mounted on Giraff, and the requirement to exercising using several display and input devices. Task 2.4(M2-M9) Identification of the technical specifications of the virtual community (BDIGITAL, POLIMI, UMIL, GIRAFF, ORU) The characteristics of the software and hardware elements that constitute the Virtual Community are defined in terms of workload, data storage and responsiveness. A high level architecture based on open source standards and accessible technologies is designed starting from the Integrated Continuous Care telemedicine platform) provided by BDIGITAL. A set of interconnection interfaces between the different Virtual Community components is defined. All technical requirements captured in this task will be used as input for the WP6 during the Virtual Community components development, deployment, testing and production tasks. Task 2.5(M3-M24) Design of the hierarchy of interfaces with Giraff, the activity center and the community (UOP, BDIGITAL, SAS, PCL, KORIAN, KOMMUN, UMIL) A flexible graphic user interface (GUI) will be designed to allow the different type of users to interact effectively with Ronohome2.0. Classical design rules set by Constantine and co-workers will be followed: 1. The structure principle. Your design should organize the user interface purposefully, in meaningful and useful ways based on clear, consistent models that are apparent and recognizable to users, putting related things together and separating unrelated things, differentiating dissimilar things and making similar things resemble one another. The structure principle is concerned with your overall user interface architecture. 2. The simplicity principle. Your design should make simple, common tasks simple to do, communicating clearly and simply in the user’s own language, and providing good shortcuts that are meaningfully related to longer procedures. 3. The visibility principle. Your design should keep all needed options and materials for a given task visible without distracting the user with extraneous or redundant information. Good designs do not overwhelm users with too many alternatives or confuse them with unneeded information. 4. The feedback principle. Your design should keep users informed of actions or interpretations, changes of state or condition, and errors or exceptions that are relevant and of interest to the user through clear, concise, and unambiguous language familiar to users. 5. The tolerance principle. Your design should be flexible and tolerant, reducing the cost of mistakes and misuse by allowing undoing and redoing, while also preventing errors wherever possible by tolerating varied inputs and sequences and by interpreting all reasonable actions reasonable. 6. The reuse principle. Your design should reuse internal and external components and behaviors, maintaining consistency with purpose rather than merely arbitrary consistency, thus reducing the need for users to rethink and remember. Figure 5 - Two possible Virtual Caregivers from the IGER system: a) a humanoid avatar, Hannah, b) a mascot, Piggy: some users preferred a puppet, that stresses the game nature of the interaction, while others felt more reassured seeing on the screen an avatar resembling a doctor. Interface elements, like text font size and colour, sprites dimension and scene apparent size, are made adjustable to the elder residual sight so that no effort is required for interacting through the chosen display. All interfaces will be designed incrementally. A first mockup with identified functionalities will be provided at M6 and refined afterwards with the feedback of all the formal caregivers mediated by SAS, PCL, KOMMUN, and KORIAN. A new interface constituted of mockup and real functionalities will be delivered every three month and questionnaires will be possibly updated. The GUI will be designed and adapted for web browser, smartphone applications, TV monitor and Giraff robot screen. Particular care will be put in the design of the virtual caregiver avatar, such that it does not fall in the so called “uncanny valley”. Its aspect will be stilyzed so as the subject clearly understands that the avatar is a humanoid being, but does not really pretend to be a human being (cf. Figure 5). We will design and provide several avatars so that the elder will be able to choose the preferred one according to his taste. Such avatar will be endowed with a repertoire of movements and simple facial animation with approximated lip synch among which the most suitable animation congruent with voice feed-back will be produced. Task 2.6(M2-M12) HRI and user requirement s analysis (UOP, PCL, SAS, KOMMUN, KORIAN) This task concerns the design of the multimodal HRI interfaces to facilitate natural interaction between the robot and the users. The interface combines various interaction modalities as speech, touch screen, movement. Focus is placed on interface facilities to manage the user’s explicit and implicit feedback. Such interfaces will be used in combination with a speech dialog system to facilitate interaction. The interface have also to provide speech-based feedback to ask questions, to solve pragmatic ambiguities, to motivate and encourage the elder. Scenario: Giraff approaches Ann this morning and says to her: “Come on Ann, today is a beautiful and sunny day, why don’t you call your nephew Jane to bring her to the park?”. Ann, was a bit said; she finds this a beautiful idea, called Jane and spent a wonderful morning. She was really greatful to Giraff. This informs the design of the interaction features, the HRI multimodal interface, and the design and analyses of the experimental sessions. The task will combine the use of questionnaires to reach a larger group of potential users in the different countries of the partners’ sites. In addition, individual interviews and focus-group sessions will be conducted to investigate specific design interaction issues in more depth. These methodologies will lead to the definition of the user requirements, the design of the metrics to evaluate the user experience, acceptance of the robot, and also the carers’ feedback that will be evaluated in Task 8.1. Task 2.7(M9-M12) Testing will proceed in two directions: technical testing and functional testing (UMIL, POLIMI, SXT, SG, BDIGITAL, UMA). A set of technical tests are designed for testing the functionalities of the whole platform and of each component. They will verify the proper communication between the components and their functioning according to the specifications set. Software will be developed in a high modular fashion, therefore unit testing methodology will be preferentially be used. This will allow the possibility to adapt easily the tests to specific sections of software that change throughout the development.

Deliverables: D2.1 (R, CO) Technical specifications of the platform and its components (POLIMI, M12) D2.2 (R, CO) HRI analysis and definition of robot-users interfacing modalities (UOP, M12) D2.3 (R/OTHER, CO) GUI design. Design of the major GUI of Robohome2.0 inspired to modularity and adaptation (UMIL, 24). D2.4 (R, CO) Design of testing the system and its components. The tests used and the data obtained at the end of the development of the components: WP3, WP4, WP5 and WP6 (POLIMI, M12).

### WP3 – Virtual Caregiver and service robot

| Work package number | 3 |  |  |  | Start date or starting event: |  |  |  |  |  |  | M3 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Work package title | Virtual Caregiver and service robot |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Participant number | 1 | 2 | 3 | 4 |  | 5 | 6 | 7 | 8 | 9 | 10 |  | 11 | 12 | 13 |
| Participant short name | UMIL | ORU | GIRAFF | UOP |  | SXT | PCL | POLIMI | BDIGITAL | SAS | KORIAN |  | SG | UMA | KOMMUN |
| Person-months per Participant | 5 | 15 | 1,5 | 2 |  | 1 | 7 | 9 | 2 | 2 | 3 |  | 0 | 22 | 3 |

Objectives: - To provide Giraff with autonomous navigation compliance with the elder. - To enable Giraff to provide elder tracking for monitoring; - To develop tele-monitored clinical tests to be performed by the elder at home; - To profile the user and update his/her profile according to data provided by the activity center, the environment and lifestyle monitoring and the psycho-physical monitoring and from inputs from the community of users; - To infer changes in the user condition from the whole information gathered by the sensorized home and the activity center; - To provide assistance in finding objects and to design and realize a smart drug dispenser.

Role of the partners: ORU leads this WP for its competences in AI. UMA coordinates the research on navigation and supports UMA with its expertise in using Kinect for exer-gaming. SXT leads the work on building assisting devices. BDIGITAL brings its expertise in designing and processing environmental data and GIRAFF the knowledge on robot infrastructure. PCL, SAS and KORIAN brings the view of robots users and on the definition of critical situations and the different warning levels required when monitoring the elder. on robot and virtual careviver. UOP will support the development of telemonitoring and assistance to made them most compliant. Description of work Aim of this WP is to transform Giraff from a teleoperated platform into an autonomous service robot that can provide assistance, advice and monitoring of the elder upon the work of the Virtual Caregiver embedded in Giraff. This will also provide profiling of the elder. Search of lost objects and smart drug dispenser will be realized. Task 3.1(M7-M18) Infrastructure technical specifications (ORU, GIRAFF, SXT, BDIGITAL, UMIL, POLIMI) To effectively develop the system, it is made clear that all components have to be developed such they can be easily and effectively integrated. It is important that the different parts of the system were communicating from start and therefore the definition of a proper software architecture is required: a middleware installed on Giraff PC, defined in this Task. We are aiming at OSGi architecture that is widely diffused for AAL applications, it allows integrating heterogeneous devices and it scales with new devices/services at need. This task defines also the software services that the infrastructure should support. The middlware should be able to support the acquisition of sensors data periodically or upon request. Some data require negligible delay, like gas alarms or voice commands, others, like presence sensors pose less tight constraints. Z-wave appears the best match for environment network, but other standards that would become available at project starts will be evaluated as well. Bluetooth connection seems the most effective transmission modality to acquire data from sensorized objects because of its tread-off between power and latency. Indeed Bluetooth connection has already been implemented in devices for clinical use, like the Tymo balance boards. Task 3.2(M3-M24) Enhanced navigation (UMA, UMIL, GIRAFF, ORU) is required for Giraff to move around autonomously without crashing over objects and finally, it is used to gentle approaching the elder. This task capitalizes on the experience on navigation and SLAM of UMA,. We provide the robot the capacity to move from one place of the house to another, selecting the best route (global navigation) and avoiding any obstacle encountered along its way (local navigation). As for the global navigation, houses present a highly structured topology, typically a corridor connecting rooms. Global navigation between two locations of a house (in general, from two different rooms) will proceed as follows: first, planning a sequence of intermediate places (from the topological map) from the start to the destination, and then to concatenate a series of reactive navigations between them extending to 3D the previous work of the UMA group on 2D reactive navigator. Apart from the geometrical and kinematics robot constraints, we will explore here how introduce additional proxemic constaints to path planning. We develop also an ecological approach for both the autonomous navigation of Giraff and its approach to the elder by identifying the path and velocity profile that are most suitable. Task 3.3(M3-M18) Motion tracking for transparent monitoring (UMA, UMIL, POLIMI) In this task a function that automatically determines the optimal location and orientation of Giraff to observe the elder to provide transparent monitoring (Task 5.2) is implemented. To obtain a clear view of the elder and his/her movement, the type of movement surveyed, its amplitude and position in space as well as the constraints provided by the room inside which the activity takes place, are considered. Elder motion is captured as a moving skeleton produced by Kinect SDK and described in quaternion notation. Task 3.4(M3-M12) Modeling the users and the functionalities of Robohome2.0 (ORU, UMIL, UMA, SAS, PCL) This task is concerned with creating semantic models (ontologies) that depict information about the end users, domain, activities, functionalities of objects etc. The goal is to align the various high level models in order to link them for eventual reasoning on the data provided by monitoring and activities. This information is used to tune the activities inside the activity center; this task will be developed in tight connection with UMIL. The actual elder profile will be initialized according to information gathered from clincians and caregivers, and it will be updated according to informations gathered by monitoring and activity. Elder’s idiosyncrasies is also considered. Task 3.5(M3-M27) Reasoning and Recommendation Layer (ORU, UMA, UMIL, POLIMI) Based on the models in Task 3.4, eventual rules are constructed that link the models with the data from the sensors, the community and the activity center. Such rules are then used for providing recommendations. Features of the reasoning layer are formed based on the representational model of knowledge. The semantic model which unifies various types of knowledge provided by different sources, allows to structure the domain of interest in terms of concepts (classes) and roles (relations between classes), namely TBox, along with ABox which is bout assertions on individuals (instances of the class). Given the knowledge structured in form of TBox and Abox in Description Language, the next step is implementing rules examples of which are OWL expressions or SWRL. These rules which allows the reasoner to infer implicit knowledge are written based on the requirements of the application. Since (deductive) reasoners implemented for DL (such as Pellet, FaCT++, HermiT) are based on top-down logic, the reasoning process starts with premises of rules and leads to necessarily true conclusions. For instance, in order to enable the reasoner to suggest different things mentioned in the following scenario, it is needed concepts such as person, friend, activity, social activity, etc., along with their relations are modeled in Tbox. Abox also needs to contain Anna, her friend and playing card as instances of aforementioned concepts. The key point in developing systems with the rules having time-based conditions (e.g., suggesting to call a friend if Anna has not heard about since a long time) is modeling the concept of time. The reasoner needs to be called in different intervals to check passed time for those concepts or actions (calling friend) which are included in a rule with a time concept. Furthermore, due to the unreliability of systems most of whose observations are provided by sensors, the reasoner needs to be also equipped with bottom-up logic where the truth of conclusions based on the evidence is plausible rather than certain. For this, a plug-in accompanying the DL reasoner needs to be implemented so as to prepare axioms and rules of the knowledge base for the abductive reasoning. In this way, the reasoner will also be able to reason even upon incomplete knowledge (lack of observations). Recommendations are presented via the caregiver avatar that passes the actual utterances with recommendations to the elder. We will also implement a function that selects the best channel to interact with the elder, according to his/her preferences and the devices status (e.g. it can be through an SMS or video message on mobile phone, through Giraff display or through TVscreen). SCENARIO: Anna is calling her friend less often in the last week. Giraff (ROBOHOME) identifies that Anna has to be suggested more social activities and suggests her more social activities, suggesting playing cards, give calls to Michela or Mary, who has not heard about since a long time, or to go with her friend to the violin concert of her nephew to which she was invited. SCENARIO. Maria has started to use a walking stick, with whom she feels more comfortable. However she is still stable enough and the caregiver identifies postural exer-games useful to maintain a good postural control for prolonged time. It suggests to Maria to play games like the arcade game: “Whac-A-Mole” in which she has to smash a virtual mole coming out the virtual floor displayed in front of her. Indeed such exer-games was fun but allows also Mary improve in managing her walking stick. Task 3.6(M2-M24) Teleoperated clinical evaluation (POLIMI, KORIAN, PCL, SAS, BDIGITAL, GIRAFF, UOP) These assessment tests are complementary to the transparent tests developed in WP5 and they have both the aim of a clinical validation of the cognitive and physical status of the elder. A procedure to compute the evaluation is designed and implemented. For cognitive tests can be the collection of the answers provided pressing a given virtual button on the screen. For physical tests, tracking with Giraff camera can provide the data required. Task 3.7(M7-M24) Development of a cooperative smart drug dispenser (SXT, POLIMI, BDIGITAL, UMIL) Its structure is constituted of a chest of drawers, each with an electro-magnetic lock, a led, and a micro-controller wireless connected to the Virtual Caregiver. Upon command, the chest drawer will un-lock only the right drawer from which the right pill will be taken and will switch on its associated led. At the same time, the virtual caregiver warns the elder through the devices available: Giraff, mobile phone and TV. Task 3.8(M7-M24) Development of an assistance system based on instrumented objects of everyday life (SXT, POLIMI, BDIGITAL, UMIL, UOP) In this task an assistance system able to locate of everyday objects (reading glasses, keys, mobile phone) will be developed. Some solutions have been proposed on the market. These are based on sticks or key rings to be used with specific Apps, but elderly people would have still to find by themselves the objects and, moreover, the mobile phone has not to be lost. The Phone can be located through GPS signal, but usually GPS signal cannot be received at home. Also RFID technologies already are used for tagging objects. However, RFID tags devices require a reader to be placed inside all the rooms, with a high impact on the house. We explore here an approach based on new Bluetooth technologies (v 4.0) that allows extending the range of detection, even with reduced power consumption. An adequate receiver software / hardware module will be realized that can be integrated inside Giraff to that the Virtual Caregiver can trigger Giraff to navigate and find objects. Software APIs will be realized also to support this functionality through the smart phone. Scenario. Jessica does not find her keys, call Giraffs and asks for the keys. Giraff activates and ask to the virtual caregiver help. This logs the actual power of the signal from the keys and guides Giraff towards an increase of the signal. Giraff starts moving to the right towards the sitting room, that is prioritized in the list of the rooms in the house. It then moves towards the dining room and registers and increase in the signal and moves in that room until it gets close to a drawer on the top of which are the keys. Giraff calls then the elder to get the keys.

Deliverables (brief description and month of delivery) D3.1 [R, PU] Methodology for profiling the elders and some real case scenarios (ORU, M12) D3.2 [R/OTHER, CO] Improved navigation functionalities (UMA, M24) D3.3 [R, PU] The reasoning and recommendation system (ORU, M24) D3.4 [R/OTHER, CO] Tested prototype of everyday life assistance and therapy compliance (SXT, M24)

### WP4 – Activity Center

| Work package number | 4 |  |  |  | Start date or starting event: |  |  |  |  |  |  | M3 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Work package title | Activity Center |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Participant number | 1 | 2 | 3 | 4 |  | 5 | 6 | 7 | 8 | 9 | 10 |  | 11 | 12 | 13 |
| Participant short name | UMIL | ORU | GIRAFF | UOP |  | SXT | PCL | POLIMI | BDIGITAL | SAS | KORIAN |  | SG | UMA | KOMMUN |
| Person-months per Participant | 27 | 7 | 0,5 | 4 |  | 4,5 | 6 | 16 | 4 | 2 | 5 |  | 0 | 8 | 1 |

Objectives: • Realize the Activity Center with full functionalities and communication infrastructure with the Virtual Caregiver; • Design, implement exer-games that can be adapted to the physical and cognitive status of the elder; • Design and develop automatic narration for long lasting games; • Explore the use of generic everyday physical objects as trackers; • Provide support to social activities and to card games in particular.

Role of partners: UMIL will lead this WP for its specific experience on gamification developed in FITREHAB and REWIRE projects. POLIMI will also participate supporting mainly multi-player gaming dsign. UOP, SAS, PCL and KORIAN will contribute to the most suitable game design and gameplay. UMA contributes on processing 3D camera data and GIRAFF in the architectural support. Description of work: The activity center will be built around the gamification concept. All elements will be considered. Gaming with instrumented objects will be experimented in Task 4.9. Task 4.1(M3-M27) Design and implementation of the activity center (UMIL, GIRAFF, UOP, PCL, SAS, KORIAN) The most suitable software architecture will be designed to support a large range of cognitive and physical exer-games, according to specifications set in WP1 and WP2, that can guide the elders through social cognitive and physical activities. Basic functionalities will comprehend loading scenes and avatars, collision detection, rendering, and animation capabilities. Most accepted standards for data representation will be used (e.g. XML for definition of activities and configuration, quaternions for motion representation). The center will be based on the IGER game engine and it is extended in several directions. We explore different visualization possibilities introducing the concept of device equivalence. This is a concept well known in the technology domain and it will be fully exploited here to allow the elder to exercise through the best display: Giraff display, computers display, mobile phones or the TV screen will be enabled. The middleware will be extended to provide this support, formatting the output to the current display chosen by the Virtual Caregiver as most suitable for a particular activity / message. A wireless connection between the game center and the TV will be realized using for instance miracast solution. An extrinsic motivation framework, common to all activities, based on balanced reward, game design of adequate cognitive complexity and gameplay at the proper level of challenge will be developed. Controlled randomization of assets, targets, voice feed-back avatar choice, and facial animation are all aimed to increase compliance with the therapy. Automatic mesh simplification algorithms, working on both geometry and viual appearance, will be adopted to create a sets of game assets of different LOD. Alternatively more simple heuristics based on objects count and on their dimensions will be used. An adequate measure of cognitive load, that takes into account both 3D geometry and texture, will be defined to match the elder profile. Task 4.2(M7-M12) Silhouette extraction for improved immersion (UMA, UMIL) In this task we aim to segment the body of the elder in front of the Giraff 3D camera from the background, and to use the obtained silhouette for visualizing the elder inside a virtual environment through alfa channel179. We start from the silhouette obtained segmenting the range image. Although this produces a robust identification of the user, the borders of the silhouette are jerky, and the silhouette is useless for our aims. We improve segmentation exploring local total variation regularization applied to the areas of RGB image corresponding to the silhouette border in the depth image. Regularization is used usually to filter noise preserving sharp edges, it will be used here to robustly identify the edges of the silhouette in RGB images thus improving segmentation. Task 4.3(M7-M21) Mini-games content generation (UMIL, ORU, UOP, PCL, POLIMI, SAS, KOMMUN) We begin from three starting points: the identified profiles of the elders, the associated mix of activities and a suitable theme (WP1): personalized environments will constitute the containers inside which the activities will be accommodated. We design mini-games, inside the theme chosen, that match the required exercises. We consider also that the mini-games will be assembled into a narration in Tasks 4.4. and 4.5. We design physical exer-games such that the elder can exercise alone or with her/his caregivers and friends either through the community (Task 6,1) or inside the house (Task 4.5). We also enable the elder to play in front of the TV. In this case Giraff will navigate besides the TV to survey the elder motion while playing. To avoid perspective distortion, correction for viewing angle of Giraff is implemented. SCENARIO: Robert gait is becoming slower and less stable. Giraff identifies that Robert needs to move more and identifies exercises for balance and posture as the best remedy. It proposes to him a set of exer-games to be played for a quarter of an hour for at least two weeks. It also shows to Robert the picture of all the other elders inside the Robohome2.0 community that has entered in the same program. The idea of a group of new people with whom Robert can compare turned out really motivating for him who start exercising regularly without missing a day. His caregiver and GP were extremely happy of this as they believe this would keep him far from needing a wheel-chair for longer time. Cognitive activities are based mainly on touch screen interaction. Exer-games are realized on specifications set in WP2, like for instance, puzzle, Simon, or other memory games. Content is generated according to the elder idiosyncrasies. For instance, puzzle games can be based on pictures uploaded by the elders; memory games a competition with Giraff the sequence of instructions of a given recipe (e.g. the preferred cake of the elder’s housband / wife), and so forth. Some popular games, like Ruzzle, can be incorporated inside training, promoting also socialization. Support for multiply is provided also for cognitive games. The activity center provides also simple questions for assessing purpose. For instance, when switching on the TV the virtual caregiver may ask a question from a cognitive test, picked up randomly, asking for instance the current day, season, month, the name of daughter or son and so forth. Social activities. Robohome2.0 takes advantage of multi-player support and audio-video interaction to provide inside the same display window a real-time video-stream of all the elders playing together, so that each elder sees the others and can interact with them (Task 4.6). SCENARIO: Anna is listless today. She is invited by the smart caregiver to contact her friends for a card game. Anna starts playing with Emma, Michela and Lina but Emma realizes that Anna is slower than usual to play her card and she is not at her best level. Emma herself leaves a message to her virtual caregiver that transmits the gentle message to Anna’s relatives. Task 4.4(M7-M30) Automatic narration (UMIL, POLIMI, UOP, ORU) These mini-games designed in Task 4.3 will be described through an ontology; this will highlight an initial and final state of the episode. Stochastic finite state machines are implemented to chain each next episode, with a probability transition that reflects the degree of compatibility of one episodes with respect to the next and the capability of that episode to support the activity prescribed (e.g. crossing a river can be implemented also through a puzzle game of through a memory game that assigns a reward that allows to accomplish the task). Drama curve will also be considering, alternating activity intense episodes to more quite ones. This methodology will provide the elder with an unpredictable sequence of episodes, thus creating a surprise element that is a fundamental ingredient for motivation. We will explore also reinforcement learning to make the activity center learn which can be the best next episode, for the elder, given his/her idiosyncrasies, by collecting her/his qualitative feedback at the end of each episode. We will also provide information that will be displaced inside the community (success rate, gaming time ….) that will be used to promote competition or cooperation and feed trust mechanisms. Task 4.5(M13-M36) Personalized educational games (UMIL, PCL, SAS, BDIGITAL, POLIMI) To realize effective educational games, all the functions and elements on which to build education: therapy, comorbidity, disease description and lifestyle have to be identified with clinicians and caregivers. Possible critical elements are defined as well as associated consequences. Throughout the game, the elder is guided to increase the knowledge about his/her condition, with a score mechanism that follows the degree of acquired knowledge and a gameplay that is tuned to the success rate. Task 4.6(M3-M24) Social activities through multiplayer games (POLIMI, UMIL, UOP, BDIGITAL) Two settings. Are provided. The first setting is based on multi-cast video streaming and most suitable technology to realize it will be analyzed. On the one side SkypeVideo APIs seem particularly suitable for this as they allow point to point video streaming, that can be manageable for allowing a few elders playing together. On another side WebRTC technology provides more secure video streaming because it offers a direct peer-to-peer streaming without having any other intermediary server. Moreover it is an open standard based on web technologies. The table, the card deck and the cards in the hand of the elder will be shown inside a virtual scene displayed on the screen. Merging video streams with virtual scene will take place at visualization time, resorting to alpha shading as shown in the Duckneglect system: The same infrastructure is made available to do physical exercises in a vitual group, for instance with a virtual. Such setting will promote also discussion and speech between the elders themselves and will promote socialization. Lastly it will be explored also to support collaborative work. We will explore for instance this through puzzle games that can be made cooperatively. SCENARIO Michela leaves in Milano. She is feeling lazy and a bit less social in the last days and is moving less time as shown by more time spent on the sofa, watching TV and the average decrease of telephone conversations. The virtual caregiver approaches her and, with nice voice, remembers that she was a dancer when she was young and that some exercise would indeed helpful to her. The Virtual Caregiver suggests also her that at 3pm in the afternoon there is a live virtual session of dancing for a group of people of her capability. Lucille is sceptic, but when the Virtual Care Giver remember her this appointment just after lunch, she decides to try. With her surprise, she sees in the group a old co-dancer of her, Lenita, living now in ORU. They are happy to make dance movements together and, at the end, they could restore the old friendhship. Since then they started meeting not only for the exercises, but also through video communication through Robohome2.0 platform. Eventually their nephews met each other and could meet one year in Italy and one in Sweden in summertime, enlarging the social dimension of their whole family. Michela and Lenita were very happy of this. Most of the work will be completed in the first year of the project (D4.1). We leave open the possibility of few refinements that could be implemented in the second year of the project, according to the technology offer that will be made available (D4.3). Task 4.7(M3-M18) Definition of calibration games for video and/or inertial systems (UMIL, SXT, POLIMI, UMA) This task is aimed at developing all the methods that allow fusing tracking data obtained from different sources. Initial calibration of the devices is carried out at the Service provider site before giving Robohome2.0 to the elder, but periodic refinement may become necessary and limited cognitive and physical residual capabilities of the elder should be fully taken into account. To simplify the process, ad hoc calibration objects that can be integrated in the room furniture will be studied. Alternative methods can be based on adequate games will be studied, like for instance for the calibration of the Kinect camera to provide registered RGB and range images. We will explore also the same data used to track everyday life activities (Task 5.2) to calibrate motion sensors embedded inside the objects. Task 4.8(M7-M27) Functional and usability tests (PCL, UMIL, SXT, POLIMI, BDIGITAL, SAS, KORIAN, UMA, KOMMUN) The activity center and its exer-games will be tested starting early in the project, when simple features and infrastructure is made available (D4.1) to the end of development. Such tests will be organized for groups of users who will evaluate the usability and effectiveness of the functionalities from the early prototypes to the final system to verify that they match users expectations and needs. Task 4.9(M13-M36) Smart gaming with instrumented objects (UMIL, UOP, POLIMI, UMA). Calibration carried out in Task 4.7 and sensorized objects built in Task 5.1 will be combined to make everyday objects game tracker. Moreover, these objects will be able to control gameplay with motion and pressure. We will fully explore this possibility to guide the elders through specific movements defined with the clinicians that can provide specific information and motion control.

Deliverables: D4.1 (R/OTHER, CO) A first nucleus of physical and cognitive games + silhouette tracking. A first user manual will be provided (UMIL, M12). D4.2 (R/OTHER, CO) The full system for education (POLIMI, M18). D4.3 (R/OTHER, CO) The full smart activity center with the final reference manual, user manual and installation manual (UMIL, 27).

### WP5 – Monitoring Systems

| Work package number | 5 |  |  |  |  | Start date or starting event: |  |  |  |  |  | M3 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Work package title | Monitoring Systems |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Participant number | 1 | 2 | 3 | 4 | 5 |  | 6 | 7 | 8 | 9 | 10 |  | 11 |  | 12 | 13 |
| Participant short name | UMIL | ORU | GIRAFF | UOP | SXT |  | PCL | POLIMI | BDIGITAL | SAS | KORIAN |  | SG | UMA |  | KOMMUN |
| Person-months per Participant | 9 | 4 | 0 | 0 | 30 |  | 9 | 20 | 12 | 3 | 5 |  | 7 | 0 |  | 2 |

Objectives: - To design and implement the sensorized objects and the communication infrastructure with the virtual caregiver and the service robot; - To design and implement environment, lifestyle and social monitoring; - To design a physiological monitoring network; - To design and implement a distributed voice control system; - To realize the sensorized home monitoring system; - To design and validate cognitive and physical transparent clinical tests.

Role of partners: POLIMI leads this WP for its specific experience in multimodal monitoring and assessment of users condition. POLIMI implements the physiological measurements network with the support of KORIAN, PCL, SAS, and KOMMUN and collaborate with PCL and SAS in the validation of the novel transparent clinical tests. SXT develops the sensorized objects for physical and cognitive monitoring and the micro-architecture that integrates monitoring system within Giraff, in collaboration with GIRAFF. Environmental and social monitoring work is led by BDIGITAL. SG develops the voice processing system in Task 5.4 and leads the development of the distributed voice command system. UMIL brings in its experience in motion analysis, mainly to design the most effective transparent tests in Task 5.2. Description of work: The aim of this WP is to provide a set of customized and off-the-shelf low cost devices and tools to monitor the elder behavior at home and his physical and cognitive condition. All the sensors are selected following the user and functional monitoring requirements (Task 1.3) and the technical specifications identified in Task 2.2, that define also the network connectivity. Modularity, flexibility and adaptability to the different use-case scenario is considered. Physiological sampling devices are also identified and connected with the Virtual Caregiver. We design and implement a novel cognitive and physical transparent system based on sensorized objects (Task 5.1 and 5.2). Identification of proper indexes and scales, and validation with standard clinical and instrumental evaluation indexes is carried out. Task 5.1 (M3-M24) Design of the micro-architecture for transparent physical monitoring through sensorized objects (SXT, UMIL, POLIMI, BDIGITAL) Micro-architectures based on micro-sensors of pressure and acceleration (Figure 6.1) are realized. Novel flat pressure sensors with ultra thin sensing circuits to sense contact forces will be considered so that they can be attached and adhere to objects surfaces in the contact area (Fig. 6A and B). This can be for instance the handle of a comb or of a walking stick. Inertial sensors can be integrated inside the body of the object (Fig. 6C). SXT has already developed inertial, wearable systems to analyze human movement at work, during sport activities or rehabilitation within the Protheo system. A micro-controller like Arduino is used to acquire the analog data from the sensors, digitalize them and send them to a radiotransmission module that transmits thorough low-power Bluetooth (class 4.0). Two modalities of data transfer will be made available: a) real-time transmission of the data in which the micro-controller will read the data from the sensors, process them and output in real-time the value through blue-tooth connection. It will be used for transparent monitoring. b) on-board storage of the data. This modality will be used to gather motion data during the day, both inside Figure 6 –A) Digitacts sensors by PPS; B) Flexiforce sensors by Tekscan; C) LIS331 acceleration sensors by STM and outside the house. An automatical download procedure will be developed that is triggered when the object is put in its resting location. Particular care is reserved to calibration, which is the determination of gain and offset parameters. Both inertial and pressure sensors will be calibrated before releasing the sensorized object. However, calibration parameters may change over time and their value may need to be adjusted. Offset and gain of pressure sensors can be refined by measuring the reading associated to a given load. Simple objects and procedure aimed to caregivers will be developed to periodically re-calibrate instrumented objects. Inertial sensors, constituted here of tri-axial accelerometers required to calibrate at least six parameters (3 offset and 3 gain parameters). However, knowing that when no motion is detected, the square norm of the output should be the norm of the gravity vector, auto-calibration can be carried out. This will be fully explored here to keep the motion sensors calibrated. In case, accelerometers will not provide the required accuracy, they will combined with gyroscopes to make measurements more robust. Psychological issues in accepting sensorized objects will be properly dealt with PCL and ORU partners as well as with PCL, SAS and KOMMUN psychologists. Task 5.2 (M7-M27) Design and clinical evaluation of transparent monitoring (POLIMI, UMIL, SXT, PCL) In this task psycho-physical monitoring of elder status will be performed by a novel approach that combines a robot to measure the elder movement by means of motion tracking (Task 3.3) in combination with the sensorized object realized in Task 5.1. The transparent monitoring is based on the principle that gestures are the expression of the motor and cognitive ability of the elder. We first identify start and end of a single gesture by identifying typical features on pressure and/or kinematic profile, like movement or pressure onset/offset. Time warping will them be applied to the data to enable a comparison with a baseline. Both statistical parametric models, like GLVM, or deterministic models like covariation patterns, will be fitted to the data to derive Gesture Degradation Indexes that can be of clinical relevance. Segmentation of motion and pressure data will allow also to evaluate the proper concatenation of actions that can be used for cognitive evaluation. We will implement PFSM to describe the concatenation of actions associated to different situations as a model of the elder behavior. High probability patterns, termed eigenbehaviours, can be extracted from this model and compared with the actual pattern to detect possible cognitive decline. The proposed synthetic indexes will be evaluated in their significance and sensitivity and validated in cooperation with PCL and SAS. A similar approach will be applied for transparent cognitive monitoring, in which a set of questions will be asked to the elder by the Virtual Caregiver, in different times and days. Answers will be registered and analyzed collectively to derive cognitive degradation indexes. Task 5.3(M7-M24) Design and implementation of environment and lifestyle monitoring (BDIGITAL, ORU, POLIMI, SXT) This network will chain several sensors that are associated to the home (Task 1.3). Different priorities is assigned to the different sensors Z-wave communication protocol for the ambient sensoring will be favored among other protocols due to its broad market share and open standards. The combination of presence, luminosity, humidity, temperature and cushion pressure data will be used to evaluate the user behaviour, and to detect abnormalities of daily habits. To illustrate, a particular case is the detection of insomnia and sleep abnormalities when presence is detected in different rooms at night, or a prolonged period in the bathroom with respect to his normal time can indicate a concealed pathology that can be detected by the Virtual Caregiver and then analyzed by the GPs. The same network will check for gas and smoke alarms that will immediately raise an alarm to the elder first and then to the carers. An architecture based on a Raspberry micro-server to collect and transmit the data the Virtual Caregiver is envisaged. Task 5.4(M7-M24) Design and implementation of social behavior monitoring (BDIGITAL, UMIL, ORU, PCL, SAS, SG) Social behavior will be tracked through heterogeneous information. First source information will be made available through a log book of activities compiled by the elder caregiver, for instance on a weekly basis. Such documentation will be provided preferentially through the community or through a smart phone app (Task 6.6). Access to the community and profiling of the phone conversations is computed to provide additional information. In this task an pitch analysis of the elder voice in phone conversation is carried out with the aim of identifying possible consistent changes of emotional state. To this aim, cepstrum analysis or Short Time Fourier Transform of audio signal with vocal folds opening and closing rates. The task will end with technical and functional testing. Task 5.5 (M7-M24) Design and implementation of distributed voice command system (SG, BDIGITAL, UMIL) A plug&play acoustic sensor will be designed and developed. This will be constituted of a microphone with a low-level speech processing software implemented through DSP dedicated processing. Its aim is to enable specific voice command execution. Such component shall be connected to sockets and transmit the signal through a wireless protocol (z-wave and BlueTooth Low energy will be considered first depending on their acceptance, bandwidth and latency). Possible post-processing inside the Robot or the Raspberry Pi microserver will be evaluated. Various speech analysis and recognition approaches based mainly on the cestrum coefficients and HMM models will be examined. The main objective to have stand-alone acoustic sensors plugged on sockets is the range limits the microphones have, so basic commands could not be detected if the robot is in a different room. Task 5.6 (M7-M24) Design and implementation of physiological measurements network (POLIMI, SXT, BDIGITAL, PCL, SAS, KORIAN, KOMMUN) We aim at low cost devices already available in the market that comply with all the medical equipment safety and quality standards are required (EN 1060-1, EN 1060-3, EN 1060-4 and ISO 8106). An initial detailed analysis of the state of the art and of the devices already available in the market at project start will be carried out as this is a field evolving at an extremely fast pace. A possibility would be to select off-the-shelf miniaturized OEM modules. These are cost-optimized and can offer accurate measures meeting all the medical equipment safety and quality standards. Specific modules are selected according to the needs of each elder and integrated inside Robohome2.0, so that a personalized physiological monitoring network is realized. Novel applications, like retinal imaging to measure oxygenation in a non intrusive way, will be considered in the early stage of the project to select the most friendly and still reliable solutions. Task 5.7(M19-M27) Functional and usability tests of the sensorized home (POLIMI, SXT, BDIGITAL, UMIL, PCL, SAS, KORIAN, KOMMUN) Each of the component developed in Tasks 5.1-5.4 will undergo extensive usability and technical tests. Modality of use of each sensor and components has been set in WP3. The actual implementation will be made available to PCL, SAS, KORIAN and KOMMUN that will verify the adequacy of the implementation and may suggest refinements. In parallel testing of the each monitoring network and of the whole network is carried out with particular attention on possible conflicts among the different components or bottlenecks at the Virtual Caregiver level.

Deliverables: D5.1 [R, CO] Design and development of the monitoring networks; a first report will be provided (BDIGITAL M12) D5.2 [R, CO] The full monitoring systems ready for usability testing (POLIMI, M18) D5.3 [R, PU] Validation of the clinical transparent clinical tests (POLIMI, M27) D5.4 [R, PU] Report on the functional and usability tests of the monitoring systems (POLIMI, M27)

### WP6 – Virtual Community

| Work package number | 6 |  |  |  | Start date or starting event: |  |  |  |  |  |  | M3 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Work package title | Virtual Community |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Participant number | 1 | 2 | 3 | 4 |  | 5 | 6 | 7 | 8 | 9 | 10 |  | 11 | 12 | 13 |
| Participant short name | UMIL | ORU | GIRAFF | UOP |  | SXT | PCL | POLIMI | BDIGITAL | SAS | KORIAN |  | SG | UMA | KOMMUN |
| Person-months per Participant | 6 | 2 | 0,5 | 3 |  | 0 | 2 | 5 | 32 | 3 | 3 |  | 5 | 0 | 2 |

Objectives: - Implement a Virtual Community based on web technologies conneting all users of Robohome2.0; - To provide a set of specific services oriented to elderly people and formal/informal caregivers to promote socialization and communication between them, and to offer a social and healthcare support to the elders; - To provide an interaction point for Virtual Community users; - To create an environment to increase elderly motivation, adherence, cognitive and physical stimulation.

Partners role: BDIGITAL will lead this WP for its wide experience in designing web-based communities inside the projects, Rewire, Backhome and Saapho and leads the design and implementation of the infrastructure. UOP supports interfaces development according to specifications set in Task 2.5. POLIMI provides the support for data recording. UMIL will lead the integration of gamification inside the community and provide analysis instruments. PCL, SAS and KOMMUN bring in the psychological, sociological and psychological view to obtain the most compliant implementation. ORU will bring in its expertise in designing functionalities mediated by Giraff robot. Description of Work: Task 6.1(M3-M18) Structuring the Virtual Community and management (BDIGITAL, UMIL, PCL, SAS, KOMMUN, KORIAN, ORU, UOP) Goal of this task is to provide a low level architecture of Virtual Community platform taking into account both functional and technical specifications identified in WP1 and WP2. An adequate client and server architecture will be designed using web services technology that will communicate through the Robohome2.0 infrastructure. Apache Tomcat, Java programming language, Spring framework, jQuery, Apache Tiles among others. The most suitable database type will be chosen, selecting between SQL or noSQL databases, taking into account the type of data produced by monitoring systems, activity center and community. The interfaces defined in WP2 are incorporated. Multi-user interaction is implemented with the same technology identified in Task 4.3. Task 6.2(M7-M24) Data repository design and implementation (POLIMI, UMIL, BDIGITAL, KORIAN) The data collected by Robohome2.0, provided by transparent monitorings and activities will be stored inside the database designed in Task 6.1. Functionalities to transfer data from the Giraff PC on a regular basis are implemented. A repository of live stories narrated by the elders is built to generate collective knowledge of close past of the elderly that would get otherwise lost. Task 6.3(M6-M18) Services design and implementation (BDIGITAL, UMIL, GIRAFF, SAS, PCL, KORIAN, KOMMUN) The set of services defined in Task 2.4 are integrated by a continuous osmosis from most popular social networks and from thematic networks of interest for the caregivers and the elders. The content will be filtered through adequate indexing, to provide the elder with personalized knowledge and annotations and comments will be collected, using classical threads technology. Aim is to increase the collective knowledge of the users. Additional services, like reminders, calendar, notifications will also be provided. Task 6.4(M12-M24) SOA layer and Communications (BDIGITAL, UMIL, GIRAFF) The Virtual Community is developed as a web application and installed on a dedicated server, which will have access to the internet in order to accept, validate and send communication requests between Virtual Community components. Communications among them will be implemented using a service oriented architecture (SOA) developed with Open Software components. Confidentiality will be analyzed and guaranteed in all communications. The output of this task will be integrated in development carried out in Tasks 6.5 and 6.6. Task 6.5(M12-M27) Applications for virtual community management and activities personalization (BDIGITAL, GIRAFF, POLIMI, UMIL, PSC, ORU, UOP) In this task all administrative GUI and functionalities are implemented. New elders or caregivers can be inserted. Tools for profiling the elder before installing Robohome2.0 will also be provided. GUI for the different main users categories: elder, formal and informal caregivers will be integrated. Tools for a cluster analysis of all the users will be provided. This task will design also the most suitable support for motivational elements like leader boards or other feed-back identified in Task 2.4. Task 6.6(M12-M27) Smartphone application (BDIGITAL, UMIL, SG, PCL, SAS) The Virtual Community will allow interaction beyond the use at home through the Virtual Caregiver. Therefore an interface specific to smart phones is developed. This will be preferentially used by caregivers. In this task the apps associated to the assistance function (Task 3.8) and to suggest recipies adequate to the elder diets will also be provided. Finally, the app that analyzes the voice pitch during elder conversations will be provided. Task 6.7(M13-M24) Self-organization of the community (UMIL, BDIGITAL, KORIAN, PCL, SAS) The analysis of the network of social ties among users, defined by symmetric or asymmetric relationships, is implemented and it is used to derive self-organized clusters of users. Such clusters will be characterized by homogenous interests and similarity in other parameters derived from the profile like interests, age, familiar status and so forth. These clusters will be used in Task 3.4 to refine patients profile, to provide better recommendation and to provide better filtering of knowledge delivered. Task 6.8(M13-M27) Functional and usability tests (BIDIGTAL, SAS, KORIAN, KOMMUN) The community and its components will be tested starting early in the project, when simple features and basic infrastructure will be made available up to the end of development. Such tests will be organized for groups of users who will evaluate the usability and effectiveness of the functionalities from the early prototypes to the final system to verify that they match users’ expectations and needs.

Deliverables (brief description and month of delivery) D6.1 [R/OTHER, CO] Virtual Community design. Report on the initial virtual community design and implementation of the basic features. Description of the structure of services planned to be included in the final version of the platform Robohome2.0 will be described. Questionnaires to evaluate the design of community at the functional and usability level will be defined (M15, BDIGITAL) D6.2 [R, CO] Virtual community final design and implementation. The complete final design and architecture of the community will be presented as well as the full list of services along with their description and user manual. The implementation process as well as the technical specifications of the platform on which virtual community is based will be described (M24, BDIGITAL) D6.3 [OTHER, CO] Virtual community software package. The associated software of the virtual community will be packaged in this deliverable. The installation manual will be presented along with the code. (M24, BDIGITAL)

### WP7 – Integration

| Work package number | 7 |  |  |  | Start date or starting event: |  |  |  |  |  |  | M13 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Work package title | Integration |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Participant number | 1 | 2 | 3 | 4 |  | 5 | 6 | 7 | 8 | 9 | 10 |  | 11 | 12 | 13 |
| Participant short name | UMIL | ORU | GIRAFF | UOP |  | SXT | PCL | POLIMI | BDIGITAL | SAS | KORIAN |  | SG | UMA | KOMMUN |
| Person-months per Participant | 8 | 5 | 8 | 2 |  | 4,5 | 0 | 4 | 8 | 0 | 1 |  | 3 | 6 | 0 |

Objectives: • To coordinate the integration of the modules developed in WP4, WP5, WP6 and WP7 into a complete first prototype of Robohome2.0 system; • To validate the functioning of the prototype.

Role of the partners: Integration will be carried out by partners who have developed the components under the lead of UMIL. BDIGITAL will supervise the integration of the community, POLIMI of the monitoring systems and assistance functionalities and UMIL of the activity center. GIRAFF will carry out extensive testing for validation. KORIAN will participate to the integration of the community to provide its view of final service provider and possible channel of commercialization of Robohome2.0. Description of work: Aim of this WP is the validation of the platform producing all the documentation required to allow using the platform in the pilot tests. Validation results will be assembled in a comprehensive report that will be made publicly available. Task 7.1(M7-M24) Communication development and testing (BDIGITAL, UMIL, GIRAFF, POLIMI, SXT) This is a critical task for integration. In this task the communication between all Robohome2.0 components: the game center, Giraff, the virtual community and the monitoring system will be developed and tested. This task will start early to develop a coherent view of development and communication. Data types, possible conflicts, technological requirements (bandwidth, protocols and transmission media) as well as the functional requirements (data anonimization, organization) are taken into account. Data confidentiality and safety is a main concern in the design phase and is properly addressed using OASIS web service security specifications (WS-Security protocol). Task 7.2 (M18-M27) Integration and testing of the community services (BDIGITAL, UMIL, GIRAFF, KORIAN) All the services developed in WP6 are integrated in the Robohome2.0 platform. Suitable tests are performed to evaluate the provided functionalities according to the users and technical specifications defined in WP1 and WP2. Several tests, based on use cases, will be performed with the purpose of ensuring the full integration of all the components that are part of the community. Task 7.3 (M7-M27) Integration of monitoring networks and activity center (POLIMI, SG, SXT, GIRAFF, BDIGITAL, ORU, UMA) All the selected and developed devices will have most different transmission capabilities and cabling the entire house cannot be feasible. A structure based on a set of networks based on WiFi transmission is the most reasonable. A Hub, for instance based on a Raspberry microprocessor, that integrates all environment sensors, manages them and communicate with the virtual caregiver, will be explored. Sensorized devices will have their own network as the delay required in transmission has to be short. We will start in subsequent steps, from early prototypes supporting few devices to the full set of networks and the activity center. Such progressive approach is fundamental to early detect possible conflicts and software / hardware incompatibilities. Task 7.4 (M21-M27) System testing and validation (GIRAFF, BDIGITAL, UMIL, SG, SXT, KORIAN, UOP) Quantitative experiments and tests are carried out over the whole platform according to the functional specifications set in WP1 and to the technical specifications set in WP2. This is widely tested in protected environments, represented by the living labs of ORU and SAS, to identify any bugs and/or functional limitations. An exhaustive testing at technical level will be performed before delivering the Robohome2.0 system for use and evaluation. Particular attention will be devoted to the characterization of the performance of the integrated system in terms of robustness, reliability, usability, and dependability. A specific focus will be paid to user safety. Furthermore, during integration of the Robohome2.0 system, consistency with international medical regulations and communication standards will be pursued by the Ethical Advisory Board. Full documentation of integration is provided in D7.3.

Deliverables (brief description and month of delivery) D7.1 [R, PU] Description of the hardware and software infrastructure of Robohome2.0. Interfacing specifications and SW and HW specifications of the components and of the whole system will be reported in a comprehensive way (BDIGITAL, M24). D7.2 [R, PU] Report on functional tests on the final integrated platform (UMIL, M27) Results on functional tests developed in collaboration with the different groups of users will be extensively reported. D7.3 [OTHER, CO] Integrated SW / HW prototype to be used for the pilot (UMIL, M27).

### WP8 – Robohome2.0 pilot

| Work package number | 8 |  |  |  | Start date or starting event: |  |  |  |  |  |  | M13 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Work package title | Robohome2.0 pilot |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Participant number | 1 | 2 | 3 | 4 |  | 5 | 6 | 7 | 8 | 9 | 10 |  | 11 | 12 | 13 |
| Participant short name | UMIL | ORU | GIRAFF | UOP |  | SXT | PCL | POLIMI | BDIGITAL | SAS | KORIAN |  | SG | UMA | KOMMUN |
| Person-months per Participant | 3 | 3 | 1 | 10 |  | 0 | 8 | 7 | 2 | 24 | 19 |  | 0 | 2 | 6 |

Objectives To evaluate the Robohome2.0 technology in a real home setting, for the following aspects: • usability by the elder, the caregivers and the physicians; • efficacy in assisting the elder in everyday living, therapy compliance, monitoring, evaluation and stimulation;

Partners role: SAS will be the leader of WP8 for its extensive expertise in this field. It will collaborate intensively with PCL and KOMMUN in all the aspects of testing. KORIAN and GIRAFF will look also closely to aspects involved in industrial exploitation, KOMMUN from the public and KORIAN from the private point of view. UMIL, POLIMI, BDIGITAL, UMA, BDIGITAL and ORU will contribute on information gathering on the use of the components and of the whole platform and assist in any issue with the technology. Intensive experimentation of robot interaction is carried out under the lead of UOP in Task 8.1. Description of work: Robohome2.0 is tested with at least 16 elders, selected by SAS (6), PCL (6) and KOMMUN (4) among the elders who meet inclusion criteria set in WP1. Each of them will be using the platform for at least 4 months: each partner enroll two elders for each platform assigned to them. Enrollment follows the rules of the reference center. A system personalized to elder needs will be installed in the elder’s house and he/she will be briefly trained. Full support is provided through phone or through the platform itself. In this pilot study not only the elder will be involved but also the network of his/her carers. The clinical partners will collect all the events associated to the pilot: hazards, criticalities, observations, suggestions, that will be compiled into a comprehensive report (D8.4). The sample size of 16 elders is the number that can realistically be treated for the 9 months training period that can be allocated for the trials. Keeping in mind that our primary aim is to assess the technical feasibility and usability, we cannot provide a power-based sample size estimation. Nevertheless, 21 subjects with different pre-frailty characteristics will allow us to obtain a generalizable evaluation of feasibility. We will also focus on the safety of the technology, on the elder’s compliance and satisfaction with the technology, and on the customized objectives as defined in Task 1.6. In particular, we will have enough man months (16*5 = 80) to register adverse events if there are any caused by Robohome2.0 training, and to acquire a large set of feed-back on compliance, usability, effectiveness and flexibility of the system and of its components. Task 8.1(M13-M36) Behavioral analysis (UOP, SAS, PCL, KOMMUN, KORIAN, UMIL) In this task we design experiments to evaluate interaction modalities of the elder with Giraff and the Virtual Caregiver. Long-term interaction and acceptance, matching perceived and actual ability, readability and responsiveness are among the factors that make the interaction with a robot successful. None of the above mentioned qualities can be considered in isolation: long-term interaction and acceptance, readability, responsiveness and matching of perceived and actual ability all impact on each other. As such it is impossible to develop one quality while neglecting the others. Our research and development on the HRI aspects focus on incrementally improving these HRI qualities through implementing the latest insights in the field of HRI and field testing with naive users. In particular, the choice of the open experimental scenarios and of controlled interaction experiments considers (i) the quality and effectiveness of long-term interaction and acceptance of the robot, (ii) matching of perceived and actual ability; (iii) feedback and readability of the interaction partners; (iv) responsiveness of the robot. For the qualitative and quantitative HRI behavioural analyses, in addition to video analyses of the human-robot interaction strategies, dialog transcripts and non-verbal behavior (gestures), questionnaire-based measurements will be collected after the experiments. This is based on the scales on Trust, Likability and Source Credibility used by Rau et al. (2009) and the Bartneck et al. (2009), questionnaires to measure a range of HRI factors (Anthropomorphism, Animacy, Likeability, Perceived Intelligence, and Perceived Safety). The experimental interaction tasks are based on the use case scenarios identified in Task 1.5. Results are used to refine the specifications, the components and the interfacing modalities to maximize robot compliance with the elder. Task 8.2(M13-M27) Early testing (ORU, KOMMUN, PCL, KORIAN, UMIL, SAS, UMA, POLIMI) ORU sets up a preliminary version of the system constituted of the Robohome2.0 components at different stages of completeness produced in WP3, WP4, WP5 and WP6. Such early prototype will be deployed in the living labs made available by ORU and SAS, updating the components with major updates provided by the WP leaders. This working platform is tested on different types of end users: therapists, clinicians, caregivers and elders themselves in collaboration with KOMMUN and PCL. The components will communicate with a simple network and the data collected will be made available for the analysis. This would allow to early identify criticalities in the interaction, compliance and usability and provide refinement of the specifications and of the final implementation. Task 8.3(M27-M36) Usability evaluation (SAS, PCL, KOMMUN, KORIAN, GIRAFF, UMIL, UOP, ORU) During and after the pilot trial all involved carers will answer a standardized questionnaire on system usability. This will be possibly based on TAM approach and will look on several aspects: easiness of use, compliance, pleasantness, perceived usefulness, looking at the point of view of the different users. Particular care is put on the adaptation mechanism and the evaluation of their suitability from the motivational and effectiveness point of view, as evaluated by the different users. Task 8.4(M25-M36) Quantitative evaluation (SAS, PCL, KOMMUN, UMIL, ORU, POLIMI, KORIAN) Given the number of elders studied and the time horizon of the project, the assessment of efficacy will remain preliminary. But, these preliminary data are necessary to design a future randomised controlled trials that will yield a valid assessment of efficacy. Efficacy here will be assessed with proper tests according to the specific main assistance goals with measures taken before and after entering the pilot. We will collect data on daily usage of monitoring, activity center, assistance and community by the elders and the other users. These will be regressed on several parameters related to elders like clinical status, age and gender, physical and cognitive deficits, to gather preliminary knowledge on whether certain subgroups of elders can accept the system better than others. Information on technical failures, operation errors, system abuse and hours spent with implementation and instructions will be recorded. These data will be reported to and discussed with the other partners to further improve and refine the Robohome2.0 components. The data will also be used to derive a preliminary estimation of the cost of implementation. Task 8.5 (M13 - M36) Analysis and assessment on the improvement in therapy adherence and elder-doctor communication (PCL, SAS, BDIGITAL, KOMMUN, UOP) Robohome2.0 provide to the elders several tools to cope with their own health management: physiological sampling, feed-back on activities, recommendation by the Virtual Caregiver, information from the community, a smart drug dispenser and video-communication with his/her GP. We expet that all these possibility will have a positive effect on the relationship between elder and doctors and on therapy compliance, both increasing by 15%. The evaluation would take into account the elder’s involvement his own lifestyle program, knowledge and management of diseases as well as satisfaction, acceptability level, adherence to the lifestyle program and to the therapy and usability. This will be done through specific questionnaires that address all these elements that will be compiled by the elder and by his/her carers. Other elements worthwhile to be considered will possibly emerge during the project and, in particular, from the early trials carried out in the living labs of SAS and KOMMUN. Further information on this issue will be obtained by means of the analysis of the use of the activity center and of the community. The summary of this work will be contained in D8.3. Task 8.6 (M13-M36) Platform deployment modalities (PCL, SAS, KOMMUN, UMIL, POLIMI, KORIAN) A survey on the platforms for remote elder assistance in Europe is carried out at project start and reported in D8.1, with the aim of identifying critical points and actual practices. Thie will serve as the basis for defining Robohome2.0 platform deployment modalities. Knowledge and expertise acquired through the project execution will be carefully analyzed to identify and describe possible winning elements. The most appropriate model to seamlessly connect at home assistance to hospitals, GP and elder service providers networks, appropriate service settings needed to guarantee a realistic implementation, adjusted to the needs of the elders and the reality and possibilities of service providers, will be studied and a business plan defined on these data in Task 9.5. Feedbacks obtained from the pilot test outcome is used to create best practices, guidelines and policy recommendations for the successful deployment of such platforms within the national health systems of the EU zone. Our reasonable goal would be to prolong the period in which elders can stay safely at home, still monitored and supervised in a way that is transparent to them. Besides increasing their quality life, we expect to reduce the cost of the National Health Service of at least 10% in primary and secondary recoveries and clinical visits.

Deliverables (brief description and month of delivery) D8.1 [PU, R] Analysis of assistance platforms on the market and their deployment modalities (KORIAN, M24) D8.2 [CO, R] Refinement of functional and technical specifications (UMIL, M24) D8.3 [PU, R] Report on deployment modalities and patient-doctor communication improvement and therapy compliance with Robohome2.0. will contain also possible scenarios and metrics to evaluate mainly the increase in therapy compliance and patient doctor relationship. (PCL, M36) D8.4 [PU, R] Assessment of Robohome2.0 effectiveness, compliance, usability and reliability in assisting the elders at home (SAS, 36)

### WP9 – Dissemination and exploitation

| Work package number | 9 |  |  |  | Start date or starting event: |  |  |  |  |  |  | M1 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Work package title | Dissemination and exploitation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Participant number | 1 | 2 | 3 | 4 |  | 5 | 6 | 7 | 8 | 9 | 10 |  | 11 | 12 | 13 |
| Participant short name | UMIL | ORU | GIRAFF | UOP |  | SXT | PCL | POLIMI | BDIGITAL | SAS | KORIAN |  | SG | UMA | KOMMUN |
| Person-months per Participant | 11 | 3 | 2 | 4 |  | 1 | 3 | 3 | 1 | 2 | 4 |  | 0,5 | 1 | 3 |

Objectives - to disseminate project results to the relevant target groups; - to promote best practice and/or further exploitation and to to facilitate the up-take of results by the market; - to assess sustainability and harmonise links of Robohome2.0 with related European and international initiatives.

Partners role: UMIL, leader of this WP, will work in tight collaboration with POLIMI, head of the technical committee and PCL, head of the functional committee to promote dissemination among the different stakeholders of the project. All the other partners will contribute with suggestions and material for the different domains and to the different diffusion actions according to their specific expertise. Description of work: Main goal of this task is to ensure effective and wide spread diffusion of project results, channeling the diffusion of the different results to the proper audience to raise globally the perception of the new possibilities offered to the elder for assisted living through grounded results. The unique mix of the consortium, made of information technology experts, clinicians, caregivers, policy makers and companies allows the discussion and the presentation of the results from different points of view. Conventional channels like exhibitions, meetings, as well as non-conventional ones like LinkedIn, YouTube, Facebook, will be exploited to diffuse the project results. The EC communication Officer will be kept informed in due time of any diffusion activity. Main focus of the project is to improve elder care and the dissemination effort will be directed mainly in this direction: Health and Social service providers at different levels, private and public, will be contacted throughout the project to demonstrate the project results and receive a valuable feed-back. The project is expected to have a strong outcome also in the ICT domain. Industrial exploitation modalities of the whole system and of single components will be discussed throughout the project. A right of first refusal will be granted to the consortium industrial partners that will be privileged in exploiting technology developed. A use and dissemination plan will be prepared in the first year of the project (D9.1) and continuously updated until the end (D9.2). Fundamental for project exploitation will be the feed-back from the stakeholders. To this aim, workshops, small meetings and exchange visits will be organized, in which Robohome2.0 members and stakeholder will come together to discuss how the developed system should be assessed and against what criteria increase in the duration and quality of life at home should be evaluated. Task 9.1(M1-M36): Definition of a dissemination plan (UMIL, All partners) A dissemination plan is designed by UMIL together with all partners during the first 6 months of the project, identifying the communication objectives, activities and tools for dissemination, and distributing the work among partners. This will be discussed during the Kick-off meeting. Updates of the dissemination plan will be provided at months 12, 24 and 36. Task 9.2(M1-M36): Creation and maintenance of the project website (UMIL) UMIL will take care of designing, populating, and publishing the project website within the first 3 months, aiming to outline the project aims, share technical information among partners, make the project deliverables and results available online, and activate a discussion forum for the scientific community interested in Robohome2.0. A restricted access section will give partners the opportunity to access drafts of documents and to provide input to the development process. Task 9.3(M1-M35): Organization of a Workshop and of Presentations/Seminars (UMIL, ORU, GIRAFF, UOP, POLIMI, BDIGITAL, PCL, SAS, UMA, KORIAN) Dissemination activities will be carried out by all partners throughout the whole project duration and include: a) information about the project and its aims to stakeholders; b) presentation of interim results and of the final ones in national and international specialized publication organs and peer-reviewed journals in the relevant areas; c) presentations of interim and final results at national and international conferences in the area, in the form of papers/posters; d) organisation of workshops, presentations and seminars to sustain awareness about the project and its results; e) a Final Workshop will take place at the end of the project in which live demos will be shown. Relevant stakeholders will be invited. (Month 36). Task 9.4(M1-M36): Participation in Trade Fairs and Exhibitions (KORIAN, UMIL, SXT, SG, GIRAFF, BDIGITAL, KOMMUN) Robohome2.0 industrial partners will participate in relevant European and International Trade Fairs and Exhibitions held inside and outside Europe by hiring stands at which hands-on technology demonstrations will be held. Moreover, all participants will attend major European and International conferences and/or workshops to demonstrate Robohome2.0 achievements, such as AAL Forum, Bucharest, 9-12 September 2014. Task 9.5(M1-M36): Industrial exploitation of results (KORIAN, SG, SXT, GIRAFF UMIL, POLIMI, BDIGITAL, UMA) An Exploitation plan is prepared during the project period and finalized at the end of the project. The plan presents how the partners involved in Robohome2.0 intend to exploit the results of the research and development activities. The plan takes into account the different regions/countries and their specific features and priorities identifying actual and potential industrial and sales partners. Possible risks and hurdles which need to be tackled before starting the exploitation of project results are identified and measured in order to minimise their impact and corrective actions recommended. Appropriate alliances for the deployment of project results are investigated. Negotiation and contracting with potential industrial and commercial partners will be started as soon as possible. Task 9.6(M18-M36): Business plan (KORIAN, SXT, SG, GIRAFF, UMIL, SAS, PCL, KOMMUN) A business plan will be prepared for the end of the project substantiated with the data gathered during the pilot. We will summarize inside a business plan a set of possible business goals, the reasons they are believed attainable with the development of Robohome2.0, and the plan for reaching those goals. Financial and technological content will be highlighted as well as competitive advantage with respect to similar systems will be highlighted. Task 9.7(M1-M36): Management of collaboration with external organizations (UMIL, PCL, SAS, KORIAN, BDIGITAL, UOP, POLIMI, KOMMUN) The goal of this task is to manage the collaboration with external organisations. PCL, a National center for Geriatry and SAS, the reference node for Socio-Health public services in Andalusia have developed a long term follow up and a continuous elder care assistance with screening of fraility. Due to this, they have the possibility to follow the elders in different stages of pre-fraility functional development and they will be able to maintain a strong connection with elders groups through GPs on the territory. Task 9.8(M1-M36): Cluster activities, development of strategic vision and synergies with other EC projects (UMIL, All partners) During the lifetime of the project, contributions to technical roadmaps and standardisation of modular, multi-modal pro-active assisted living will be analyzed and examined. Continua Health Alliance (CHA) and Assisted Ambient Living joint program (AAL) are particularly suitable and participation of Robohome2.0 will be evaluated. Synergies with other projects of Horizon2020 is explored to make provisions to complement or adopt existing standard interfaces and network protocol, and components and to favor interoperability and scalability. The goal would be to pursue the idea of Robohome2.0 experimental testing platform as a living lab in which novel components can be tested and integrated. Task 9.9(M2-M36): Scientific dissemination. (UMIL, SAS, PCL, ORU, BDIGITAL UOP, POLIMI, UMA) Potential conferences relevant to the project content will be continually updated on the web-site and a web-based conference calendar to alert the relevant project partners to deadlines for submissions of papers and conference registrations. A minimum of 5 peer-reviewed journal articles and 8 publications on major conferences are expected. The results shown may increase the interest of the different research communities involved to invest into improving elder assistance levels. Coordination of the scientific dissemination will be carried out by UMIL. PCL will play the role of shaping the information related to the project for the National Health Providers and of producing the material adequate to diffuse, and sensibilize the Health Provider of the EC countries.

Deliverables (brief description and month of delivery) D9.1 [PU, DEC] Project Website (UMIL, M3) D9.2 [PU, DEC] Project leaflet, poster (UMIL, M6) D9.3 [CO, R] Preliminary exploitation and dissemination plan (UMIL, M12) D9.4 [CO, R] Refined exploitation and dissemination plan, with refined poster (UMIL, M24) D9.5 [CO, R] Final exploitation and dissemination plan, with final leaflet and poster (UMIL, M36)

### WP10 – Management

| Work package number | 10 |  |  |  | Start date or starting event: |  |  |  |  |  |  | M1 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Work package title | Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Participant number | 1 | 2 | 3 | 4 |  | 5 | 6 | 7 | 8 | 9 | 10 |  | 11 | 12 | 13 |
| Participant short name | UMIL | ORU | GIRAFF | UOP |  | SXT | PCL | POLIMI | BDIGITAL | SAS | KORIAN |  | SG | UMA | KOMMUN |
| Person-months per Participant | 12 | 1 | 0,3 | 1 |  | 1 | 1 | 2 | 1 | 2 | 1 |  | 0,5 | 1 | 1 |

Objectives: The WP aims to ensure that the project remains on track and a successful completion of the Robohome2.0 project providing administrative and scientific co-ordination This includes the following detailed objectives: Objectives of the scientific coordination are: - to manage the overall scientific and ethical activities of the project according to approved plans; - to monitor, track and control deviations due to progress, costs, financial and scheduling changes; - to ensure that the required reporting is prepared and delivered in a timely manner; - to implement an administration and communication infrastructure to establish a basis for efficient and easy communication within the project. Also to ensure that external communication (project website, dissemination and exploitation) is undertaken and controlled by the project management, to raise the proper level of expectation; without any hype, but with a realistic shared evaluation. - to perform a procedure for updating and revising the plans due to changes and new knowledge. - to communicate with the Commission, with the Consortium and with other project bodies; - overseeing science & society issues, related to research conducted within the project; - Promotion of gender equality in the project; - Risk Management Plan implementation; - Managing IPR issue. Objectives of the administrative-financial management are: - Overall financial, administrative and contractual management of the consortium, ensuring continuous and timely communication; - Obtaining financial statements of partners; - Managing the Consortium Agreement among the partners; - Organisational and logistic support for training activities, conferences, workshops and meetings.

Partners role: All partners are involved in this WP since each organisation has to provide the mandatory financial and administrative documents requested by the EC. UMIL will act as coordinator. All other partners will nominate a member in the PSC and will participate in steering the progress of work. Management will take advantage of a reserved area set-up in the Web-site installed and developed in WP9. UMIL will be in charge of IPR management. Description of work: The main objective of the project management work package is to ensure a successful completion of the Robohome2.0 project providing administrative and scientific co-ordination. This work package is aimed at scientific and strategic project management including project meetings, project internal reviews, strategic discussions and the technical coordination among partners. The basic aim of this WP is to keep the project correct dynamics by setting the appropriate mechanisms to achieve the objectives. It will work to ensure the successful completion of the project by interacting with all the other WPs, not only in terms of tasks and deadlines fulfillment but also in terms of quality of the results. Particular attention will be paid to the management of risks and issues and to their early detection with a pro-active attitude in solving them, already experimented in coordinating the projects FITREHAB and REWIRE. Task 10.1(M1-M36): Planning and scheduling. (UMIL, All partners) This task will provide accurate planning of different actions during the project’s lifetime. Activities that have to be performed in this task are: - form the PSC and the technical and functional committees. Install the internal EAB (UMIL, All partners). - providing inputs and needs for changes (All partners); - defining and checking consequences according to budget, scheduling and objectives UMIL); - communicating and arranging meetings (UMIL); - defining management meetings Agenda (All partners based on UMIL proposal); - collecting partners inputs on meeting Agenda (UMIL); - circulating meeting agenda and logistic information. Preparing minutes of each meeting (UMIL). - preparing updated plans for final approval in the Project Steering Committeee (PSC) (UMIL). This might include the request of amendments to the European Commission; in this case the involvement of the partners is distributed as follows: a) amendment requested for technical issues (UMIL and all partners); b) amendment requested for entrance or withdrawal of beneficiaries (UMIL and all partners); - communicating updated plans with the consortium members. Large use of IT-based communication platforms, like Skype, will be used to cut the costs and increase the responsiveness (UMIL). Task 10.2(M1-M36): Progress and costs reporting. (UMIL, All partners) Robohome2.0 brings together researchers from different institutes and different countries. In order to establish common operational procedures and taking into account the enlarged Robohome2.0 partnership, UMIL prepares written guidelines and operational instructions to be followed by the partners for carrying out their research activities, that have to be approved by the PSC. This task focuses on project’s reporting starting from the individual reports provided by the partners. Periodic reports for the EC are issued every 12 months and at project completion. The reports contain an overview of the activities undertaken during the period, a summary of the S&T results, a list of the deliverables published and of the milestones reached during the period, a description of the monitoring actions (measurement / evaluation / corrective actions) undertaken to assure adherence to the project workplan, the financial statements by each participant and their summary. Activities that have to be performed in this task are: - providing administrative/financial data and relative explanations requested for each reporting period: table including detailed explanation of the use of the resources for each partner, Form C and if applicable Certificate on Financial Statement. The procedure includes the preparation of draft documents and then once the EC approves the costs, signature of the Form C. (All partners) - providing customised templates for reporting to all concerned participants (cf. Task 1.1, UMIL); - assistance on the use of the on-line tools for the completion of the financial reporting, and on how to complete the templates and revision of their first draft documents (UMIL); - first control on the administrative/financial documents provided by partners (UMIL and All partners). Once the PC approves the financial report of each partner the latter can proceed with the final draft to be up-loaded in the on-line system (All partners); - maintaining a document repository for reporting (UMIL); - submitting on time reports deliverable, milestone reports and cost claims of the required quality (UMIL); - creating periodic reports (UMIL). The periodic report for each period, will regroup in one single report both the technical report and financial reporting. The latter will include also the Financial Statements and the Certificates. The final report will comprise a final publishable summary report, the plan for use and dissemination of foreground and a report covering the wider societal implications of the project, in the form of a questionnaire. UMIL as Coordinator is in charge and responsible to create the final version of reports. Task 10.3(M1-M36): Monitoring, control and quality management. Risk Management (UMIL, All partners) This task will ensure that approved plans are monitored and controlled. Progress control will be done at WP level by measuring resources and costs. Activities to be performed include: - research and development progress control (UMIL); - cost control (UMIL, All partners). In this context each partner prepares periodical estimates on expenditure from which UMIL will produce a lumped estimate. These figures will be discussed within PSC to evaluate possible deviations and correction actions. - checking schedules, deliverables and milestones (UMIL). - risk analysis (UMIL, All partners). Risk management is fundamental to keep the project on track and to tackle early any hazard in which the project might incur. Risk management addresses the monitoring of scientific/technical results, their dissemination/ exploitation and of the overall project coordination. It comprises the supervision of the project management performance and its assessment, change of procedures, if necessary, and monitoring of the impact of such changes on the overall project progress. Task 10.4(M1-M4): Set-up of the end-users advisory board and of the project committees (UMIL, All partners) Robohome2.0 consortium believes that a continuous, effective and reliable feed-back of users is fundamental for the project success. Beside the functional committee that will bring the end-users point of view, we aim also to have an external independent advice. To this aim, in the first stage of the project key figures for each type of end-users will be identified: informal caregivers: relatives, elders, formal care-givers: nurses, physiotherapists, Psychologists and clinicians, and ICT personnel. They will be invited to be part of an end-users advisory board. This will meet at M6 of the project with the PSC and, afterwards, at M12 M24 and M36. Their role will be a pro-active evaluation of the project and suggestions of improvements that will fully discussed with the PSC of Robohome2.0. Task 10.5(M1-M36) IPR management (UMIL, All partners) Knowledge developed in Robohome2.0 will be secured as early as possible by the consortium as a whole and each partner individually. PSC and single partners will evaluate which results are suitable to be patented and identify the best options to protect SW and HW aspects of the results; patenting will be the method of choice in most cases. A continuous patent survey throughout the project will ensure the priority to the IPR. UMIL will lead this task, with the contribution of the director of its TTO, with the role of scouting the solutions developed and secure the results as early as possible to avoid that early disclosure would make patenting not possible. A report will summarize the IPR activities and achieved patents at the end of the project (M36).

Deliverables (brief description and month of delivery) D10.1 [OTHER, PU] Set-up of the end-users advisory board (UMIL, M4) D10.2 [R, CO] Project management and quality plan. Report on ethical guidelines and regulations (UMIL, M6) D10.3 [R, CO] Periodic Report I (UMIL, M12) D10.4 [R, CO] Periodic Report II (UMIL, M24) D10.5 [R, CO] Periodic Report III (UMIL, M36) D10.6 [R, CO] Final Report (a public section is provided) (UMIL, M36).

### List of Workpackages

| Work package No | Work Package Title | Lead Participant No | Lead Participant Short Name | Person-Months | Start Month | End month |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Functional Specifications | 6 | PCL | 47 | 1 | 18 |
| 2 | Implementation requirements | 4 | UOP |  | 2 | 24 |
| 3 | Virtual caregiver and Service robot | 2 | ORU |  | 3 | 27 |
| 4 | Activity center | 1 | UMIL |  | 3 | 36 |
| 5 | Monitoring Systems | 7 | POLIMI |  | 3 | 27 |
| 6 | Virtual Community | 8 | BDIGITAL |  | 3 | 27 |
| 7 | Integration | 3 | GIRAFF |  | 10 | 27 |
| 8 | Robohome2.0 pilot | 9 | SAS |  | 13 | 36 |
| 9 | Dissemination and Exploitation | 1 | UMIL | 34,50 | 1 | 36 |
| 10 | Management | 1 | UMIL | 24,5 | 1 | 36 |
|  |  |  |  | Total months |  |  |

### List of major deliverables

| Deliverable (number) | Deliverable name | Work package number | Short name of lead participant | Type | Dissemination level | Delivery date |
| --- | --- | --- | --- | --- | --- | --- |
| 9.1 | Project Website | 9 | UMIL | DEC | PU | M3 |
| 10.1 | Set-up of the end-users advisory board | 10 | UMIL | OTHER | PU | M4 |
| 9.2 | Project leaflet, poster | 9 | UMIL | DEC | PU | M6 |
| 10.2 | Project management and quality plan. Report on ethical guidelines and regulations | 10 | UMIL | R | CO | M6 |
| 1.1 | Functional specifications | 1 | PCL | R | PU | M12 |
| 1.2 | Ethical submission | 1 | PCL | R | CO | M12 |
| 2.1 | Technical specifications | 2 | POLIMI | R | CO | M12 |
| 2.2 | HRI analysis and definition of robot-users interfacing modalities | 2 | UOP | R | CO | M12 |
| 2.4 | Design of testing the system and its components | 2 | POLIMI | R | CO | M12 |
| 3.1 | Methodology for profiling the elders and the functionalities and some real case scenarios | 3 | ORU | R | PU | M12 |
| 4.1 | A first nucleus of physical and cognitive games + silhouette tracking | 4 | UMIL | R/OTHER | CO | M12 |
| 5.1 | Design and development of the monitoring networks; a first report will be provided | 5 | BDIGITAL | R | CO | M12 |
| 9.3 | Preliminary exploitation and dissemination plan | 9 | UMIL | R | CO | M12 |
| 10.3 | Periodic Report I | 10 | UMIL | R | CO | M12 |
| 6.1 | Virtual Community design and structure | 6 | BDIGITAL | R | CO | M15 |
| 1.3 | Final functional specifications | 1 | UMIL | R | PU | M18 |
| 4.2 | The full system for education | 4 | POLIMI | R/OTHER | CO | M18 |
| 5.2 | The full monitoring systems ready for usability testing | 5 | POLIMi | R | CO | M18 |
| 2.3 | GUI Design | 2 | UMIL | R/OTHER | CO | M24 |
| 3.2 | Improved navigation functionalities | 3 | UMA | R/OTHER | CO | M24 |
| 3.3 | The reasoning and recommendation system | 3 | ORU | R | PU | M24 |
| 3.4 | Tested prototype of everyday life assistance and therapy compliance | 3 | SXT | R/OTHER | CO | M24 |
| 6.2 | Virtual community final design and implementation | 6 | BDIGITAL | R | CO | M24 |
| 6.3 | Virtual community software package | 6 | BDIGITAL | OTHER | CO | M24 |
| 7.1 | Description of the hardware and software infrastructure of Robohome2.0. | 7 | BDIGITAL | R | PU | M24 |
| 8.1 | Analysis of assistance platform available on the market and their deployment modalities | 8 | KORIAN | R | PU | M24 |
| 8.2 | Refinement of functional and technical specifications | 8 | UMIL | R | CO | M24 |
| 9.4 | Refined exploitation and dissemination plan, with refined poster | 9 | UMIL | R | CO | M24 |
| 10.4 | Periodic Report II | 10 | UMIL | R | CO | M24 |
| 4.3 | The full smart activity center with the final reference manual, user manual and installation manual | 4 | UMIL | R/OTHER | CO | M27 |
| 5.3 | Validation of the clinical transparent clinical tests | 5 | POLIMI | R | PU | M27 |
| 5.4 | Report on the functional and usability tests of the monitoring systems | 5 | POLIMI | R | PU | M27 |
| 7.2 | Report on functional tests on the final integrated platform | 7 | UMIL | R | PU | M27 |
| 7.3 | Integrated SW / HW prototype to be used for the pilot | 7 | UMIL | OTHER | CO | M27 |
| 8.3 | Report on deployment modalities and patient-doctor communication improvement and therapy compliance with Robohome2.0 | 8 | PCL | R | PU | M36 |
| 8.4 | Assessment of Robohome2.0 effectiveness, compliance, usability and reliability in assisting the elders at home | 8 | SAS | R | PU | M36 |
| 9.5 | Final exploitation and dissemination plan, with final leaflet and poster | 9 | UMIL | R | CO | M36 |
| 10.5 | Periodic Report III | 10 | UMIL | R | CO | M36 |
| 10.6 | Final Report (a public section is provided) | 10 | UMIL | R | CO | M36 |

### Effort per Task per partner

## Graphical presentation of the components and how they inter-relate (Pert chart)

# 3.2 Management Structure and procedures

## 3.2.1 Organizational structure and the decision-making

When establishing the consortium, great attention was placed to fully cover the different aspects involved in Robohome2.0, by choosing partners capable of dealing as effectively as possible with their tasks. We found an enthusiastic feedback to the participation both to the consortium and to the advisory board. The Management structure consists of:

- the Project Co-ordinator (PC) Nunzio Alberto Borghese from UMIL;

- the Project Steering Committee (PSC), formed by all partners, being the Principal Investigators (PIs) of the 13 partners. Each member of the PSC is entitled to nominate a substitute to attend any meeting when a member is unable to attend. The PSC will be the organ of the consortium entitled to make decisions.

Given the size of the consortium and the type of project, two committees will be formed, with the aim of making internal discussion easier. The first committee, the functional committee lead by PCL, will supervise the functional aspects of Robohome2.0, and it is constituted of PCL, KOMMUN, SAS, KORIAN, UOP and UMIL. The committees will discuss specific issues related to functional aspects and their implementation, coordinates relevant information and feed-back to the PC. The second committee, the technical committee led by POLIMI, is devoted to discuss technical aspects and their implementation. It will comprehend POLIMI, UMIL, ORU, GIRAFF, UOP, SXT, BDIGITAL, SG and UMA. Other partners will possibly adhere to the committees or to their initiatives. The two committees will discuss specific issues, possibly keeping trace of the discussion, and they will report the conclusion to the PC. The PC will forward relevant information to all partners and, in case decisions have to be made, it will request a PSC meeting for final decision. A committee specifically devoted to manage the Ethical issues will be set-up, the Ethical Advisory Board of the project, led by PCL. It will comprehend: PCL, KOMMUN, SAS and UMIL. It has the responsibility for monitoring the conformity of the project to the ethical standards, analyzing all the ethical issues of the project like data protection, privacy, approval of the draft of the proposal to the ethical committee (cf. Task 1.7), gender issues, proper level of communication.The WP leaders are responsible to assure the successful completion of their relevant workpackages. At every level, decisions will be made by consensus whenever possible, to keep the maximum collaborative atmosphere inside the consortium. If a major dispute arises (for example between partners), it will be referred to the PSC. A decision will be made by two-thirds majority. In the event of a deadlock, P1 will have the casting vote. The Robohome2.0 administrative headquarters will be located at UMIL premises in Milano. Concerning the suitability to the tasks of the participants, the Principal Investigators (PIs) of each partner have long experience in their fields of knowledge and they hold senior positions of responsibility within their own organisations.The role of the PC is mainly a coordinating role, while that of the PSC is of decision maker. PC is responsible for:

- supervising and controlling the research programme, including control of research progress towards the milestones;

- representing the REWIRE Consortium in the communication with the EU;

- communicating and negotiating with the EC after approval of the PSC;

- distributing funds among partners;

- preparing common formats and templates to be used by the partners for reporting activity;

- collecting and preparing the mandatory reports and submitting them to the EU;

- managing ethical issues, in collaboration with the EAB;

- organizing, convening and participating in the PSC meetings.

- managing technological risks by identifying and classifying them and by putting them in contingency plans.

- performing detailed planning and co-ordination of the work, taking the responsibility for the completion and quality assurance of each WP;

- providing a trimestral update on project development;

The PSC will have the responsibility for making all the decisions in the project, among which:

- setting the scientific priorities, within the existing objectives and budget framework;

- maintaining and implementing the Consortium Agreement:

- discussing the most adequate potential solution to risks and, in case, implementing them;

- monitoring and reporting processes and results, based on deliverables accomplished;

- proposing and approving corrective actions, when any problems occur that might affect achievements or delay activities and deliverables, thus ensuring the adherence to the project timetable;

As Robohome2.0 is deeply concerned of end-users need, an End-Users Advisory Board will be set-up early in the project. This body will include high profile members in the following areas: informal caregivers: relatives, elders, formal care-givers: nurses, physiotherapists, Psychologists and clinicians, and ICT personnel. They will be chosen by the PSC already at the first Project Steering Committee (kick-off meeting), taking into account partners suggestions, match with Robohome2.0 aims and nationality. The EUAB will meet during the PSC meeting to discuss and advice about functions defined and their implementation and the components realized to guarantee maximum compliance.

Matters related to Confidentiality and IPR handling will be explicitly defined in the Consortium Agreement that will address the following points:

• IPR related to developed processes and technologies;

• Definition of business rules for the exploitation of result;

• Rules for the exploitation and use of Robohome2.0 IPR by the partners.

In particular, the following principles will be respected:

• Foreground shall be the property of the partner that developed the Foreground. When Foreground has been developed jointly by two or more partners, these partners shall agree procedures for the joint ownership of the Foreground.

• A participant may publish or allow the publication of data, on whatever medium, concerning knowledge it owns or knowledge it generated under work carried out within the project, provided that this does not affect the protection of that knowledge.

• Participants shall grant access rights to the other participants to pre-existing know how necessary for the execution of the project, on a royalty-free basis.

• All partners will specify the Background to which partners are granted access, together with a statement that all other Background is excluded from access. Partners’ background will be specified within Consortium Agreement to be issued before project’s beginning.

Some of the information generated during the development of Robohome2.0 system has to be considered as confidential. In this regard, partners will be asked to sign a non-disclosure agreement as a specific article of the consortium agreement. Each partner will evaluate the potential for patenting the foreground developed in the project and the PSC reserves the right to patent all or part of its results produced during the course of the project.

As far as HW/SW will be imported from other projects the IPR will be saved as agreed in the other. projects. The parties of the consortium will respect the individual IPRs. If, in the course of carrying out work on the project, a joint invention is made and more than one partner contributes to it, the participants concerned may jointly apply to obtain the relevant rights together. Each party has the right to exclude specific pre-existing know-how from the other participants’ access, as far as the restrictions are announced before the signature of the contract with the EC. Knowledge and pre-existing know-how shall be used only for the purposes for each partner’s access rights to it have been granted and only for so long as it is necessary for those purposes.

### List of milestones

| Milestone number | Milestone name | Related work package(s) | Estimated date | Means of verification |
| --- | --- | --- | --- | --- |
| 1 | Set-up of end-users advisory board | 9,10 | M4 | All members have provided written agreement |
| 2 | Functional description of Robohome2.0 | 1,2,9,10 | M12 | Document containing the complete platform technological and functional specification |
| 3 | Running prototypes of the components endowed with a limited set of functionalities | 3,4,5,6,9,10 | M18 | Tests report on running prototype of the components endowed with a limited set of functionalities. |
| 4 | Running components of Robohome2.0 | 3,4,5,6,9,10 | M24 | Functional and technological documentation of the components and their testing that show that the components implement the specifications in WP1 and WP2 and run flawless. |
| 5 | Running Robohome2.0 platform | 7,9,10 | M27 | Functional and technological documentation of field testing the whole Robohome2.0 platform, documenting that it runs flawless. |
| 6 | Final report | 8,9,10 | M36 | Report on applying Robohome2.0 to single elders at home Report on results obtained from the analysis of all the patients. |

## 3.2.2 Explain why the organizational structure and decision-making mechanisms are appropriate to the complexity and scale of the project

The management structure guarantees the proper and prompt implementation of activities, as indicated in the contract terms with the EU. The management structure and operational functions are similar to those adopted successfully for the Rewire project. From a functional point of view, management will deal with the following sub-processes:

1. implementation of the project’s components;

2. innovation management & reporting.

The structure envisaged is functional to exploit these two sub-processes.

A brief description of the main objectives, activities and responsibilities associated with managing implementation is described in the following Table.

| Objectives | Activities & responsibilities |
| --- | --- |
| To establish common operational procedures | P1 develops common templates and forms to be used by each participant in order to document the project’s progress (both scientific and administrative/financial). For example: common format for all the project deliverables, cost statement forms, risk analysis templates, task activity evaluation forms, etc. Non-paper deliverables will be always completed by a short paper description of their contents and aims (Task 10.2). |
| To ensure integration of the different research teams | Meetings at the health providers sites will be organized early in the project to build a shared view of Robohome2.0, and of its aims. Trimestral updates on project progress will be provided to all partners. The PSC establishes the rules for the day-to-day activities of the different research groups and defines the proper tools and infrastructures for implementing the co-operation between the different research groups. The constitution of a functional and technical committee will help the discussion among homogenous groups of partners. |
| To prepare and agree on the IPR and access rights. To maintain the Consortium Agreement (CA) | The PSC agrees on IPR, exploitation rights of the projects results, common knowledge access rights, etc. The partners adhere to the CA. A careful analysis of the deriving IPR issues will be carried out by the PSC and the rules for the management of IPR are agreed within the Consortium and included in the CA. The CA will also regulate any previous know-how |
| To organise periodic meetings of the PSC | P1 takes care of the organisation of periodic meetings to verify the development of the various project components and tune further development. |
| To monitor the project financial status | Every period, each partner prepares a cost statement, which declares the sustained costs broken down by type of activity; a justification of its overall costs incurred, linking these costs to the resources deployed and to the activity performed during the period. Each partner transmits to P1 the information. P1 evaluates and agrees with the cost statements received. P1 is responsible to collect the information and prepare the financial report for the EC. In the reserved area of the website, resources tables will be shared for internal monitoring of the overall resources consumed. An open source tool, like dotProject.net, might be used. |
| To assure complete and timely reporting to EC | Every period P1 prepares a periodic report that contains an overview of the activities undertaken during the period; a summary of the S&T results achieved during the period; a list of the deliverables published and of the milestones reached during the period; a description of the actions carried out in the “Monitoring” process, i.e. the measurement / evaluation / corrective actions carried out to ensure adherence to the project workplan; a financial statements provided by each participant; a summary financial report. After the end of the project, P1 prepares a final report including a final publishable summary report and the DUP. The PSC will agree the above documents and P1 submits them to EU. |

The PSC will meet at the start of the project (kick-off meeting) and 2 times per year or on an ad hoc basis as requested. The meetings will normally be scheduled to rotate between the principal contractors’ home bases. Technical meeting will be scheduled for the project’s progress and needs. These will be organized typically by clusters of partners and open to all the others. A plenary review meeting will be held at M12, M24 and M36 with Project Officer and reviewers. Meetings will be organized at the clinical partners site in the early phase of the project.

## 3.2.3 Describe how effective innovation management will be addressed in the management structure and work plan

Regarding management of innovation, it is worth distinguishing between:

- internal” knowledge, i.e. consortium access to the information needed to carry out the research programme;

- study on the best ways to diffuse the tools developed through the Robohome2.0 project;

- spreading of knowledge toward the scientific and industrial community, i.e. enlargement of the researchers base and dissemination activity;

- knowledge transfer to the EU, i.e. reporting activity;

- intellectual protection provisions;

- exploitation plan.

A brief description of the main objectives, activities and responsibilities associated with managing knowledge is described in the following Table.

| Objectives | Activities & responsibilities |
| --- | --- |
| To guarantee that information is available where and when it is needed. | The PSC defines and implements access rights provisions to the documentation and the results achieved during the project. Within these provisions, P1 is responsible for deciding what information is needed and for collecting it from the partners. P1 is then responsible for publishing these internal documents, deliverables and reports on an electronic workspace that can be used by each partner of the Consortium to download documents and run discussions. |
| To support the dissemination / exploitation of the project results | The PSC approves the dissemination activities defined within the WP9 “Dissemination/Exploitation. PSC is responsible for revising draft Exploitation plan (Task 9.1). P1 is responsible to ensure the full functionality the project web site. To this aim, the partners submit their contributions to P1 and P1 structures and spreads the information / reports / deliverables received from the partners. |
| To prepare and organize diffusion material. | Each deliverable will be analyzed and eventually edited to become suitable for diffusion through conventional (press-release, newsletters and so forth) and non conventional (LinkedIn, YouTube, Facebook, and so forth) channels. Given the comprehensive nature of the project, major deliverables associated to milestones could be grouped to provide chapters to be published in major books of the area. |
| To assure complete and timely information to EC of dissemination activities | P1 will inform in due time the Communication Officer of all the Communications and Dissemination activities (Press Releases, website launch, articles, etc.) to enable a proper relay of these activities within Europa, the eHealth newsletter, Healthtech Wire platform, etc. |

To maximize the effectiveness of the result a good balance between fast publishing the results (requested by the research institutions) and thorough evaluation of their innovative potential and their suitability to be secured through a patent, have to be balanced. For this reason, partners will be required to submit to the PSC an early draft of any publication or document to be diffused so that its novelty impact can be evaluated in due time. The consortium is built such that industrial partners in the project can exploit the results of the research. For this reason, a right of first refusal will be granted to industrial partners of the project. However, to avoid that other interesting opportunities are lost, a time limit will be defined for this option. No conflicts of interests are expected to arise during the project. Anyway, the CA will cover conflict situations. The first objective to resolve a conflict would be to reach a consensus. However, if over a reasonable length of time the conflicting parties have fully described and defended their conflicting positions but without resolution, then in order to avoid deadlock in the project’s operational progress, the approval of a two-thirds majority of the partners will be considered conclusive. P1 will have the casting vote.

## 3.2.4 Describe any critical risk, relating to project implementation

A continuous monitoring of risks emerging during project development will be carried out.The Consortium will ensure an internal control of the project development to early identify critical issues and operational bottlenecks. The proposed methodology is based on a three-stage approach, the Risk Identification, the Risk Assessment and the Mitigation Plans. First, all risks will be identified (cf. “Table on critical risks for the implementation”) and evaluated on a qualitative scale. After the first risk identification, all risks will be plotted into a risk analysis matrix (Figure 7a). This will highlight the two parameters used to characterize each risk: the probability and its but also their possible impact on the project. These two parameters provide to the PC all the information needed for a risk prioritisation. Furthermore, the Critical Risks Matrix will provide a sound basis to highlight the most significant potential risks and lead to the development of corrective mitigation action planning. The risk mitigation planning four-stage process described in     Figure 7b guarantees that corrective actions are chosen after a meticulous analysis of alternative options. WP leaders will constantly monitor identified critical risks associated to their WP. The results of these risk mitigation actions will be implemented only upon the approval by the PSC.

Figure 7a: Example of Risk Assessment matrix.			   Figure 7b: Mitigation planning

### Table of critical risks for the implementation

| Description of risk | Work package(s) involved | Proposed risk-mitigation measures |
| --- | --- | --- |
| Technical risk: Robohome2.0 features do not match expectations of the end users. Probability low: WP1 is completely devoted to transfer users’ expectations and needs in specific requirement for Robohome2.0. Futhermore, the adoption of participatory design in the development of the single system modules allows a continuous matching of Robohome2.0 features to users expectations. The end-users advisory board will also help Robohome2.0 to avoid this. Impact high: the system will have little used. | 1, 8 | Additional resources will be allocated to designing tasks to better collect users expectations. Early checking through living lab experiments, will allow to include them in the second cycles of refinement (cf. Pert diagram) |
| Technical risk: The technologies used to implement Robohome2.0 prototypes are not the most suitable for the project purposes. Probability low: WP2 will allow chosing the best technological solutions to implement Robohome2.0 functions. Impact Medium: the system is modular and components can be substituted later in the final prototype. | 2, 8 | The architecture design is modular and flexible allowing an easy addition or substitution of technological components throughout the development project phase. |
| Technical risk: The developed system has limits in usability and accessibility. Probability Low: Usability and accessibility rules are taken in account in design and development phases, with specific behavioral testing (Task 3.4, Tasks 8.1 and 8.2). Impact Medium: limit in usability will allow use only to particular groups of users. | 3, 8 | A continuous feedback from the end users, starting from early pilot in living labs, and from the End-Users Advisory Board will allow modifications of the weak interfaces all along project development |
| Consortium risk: Divergence among partners on project direction Probability Low: Consortium agreement rules every conflict situation. The research of consensus is the first objective. Impact Medium: Goals of Robohome2.0 are clearly described in this document. No major deviations can take place. | All | PC will put a strong effort in finding a solution most suitable to all involved parties. After a reasonable amount of time has been allowed for illustration and defence of conflicting positions, in order to avoid deadlock in project operational progress, the approval of simple majority of Partners will be verified. |
| Management risk: Unexpected delays in project development. Probability Medium: Due to the high complexity of the project, a few components may not be realized within the expected time. Impact Medium: A delay in the project may take place. | 3, 4, 5, 6, 7 | Robohome2.0 management is structured to maintain a continuous monitoring on all administrative and technical aspects. In case criticalities in the development of a component are detected, re-evaluation of the task duration is carried out. This delay may be compensated by other tasks. Last resort would be to discuss with the PO project prolongation beyond M36 |
| Management risk: Risks related to the protection of involved users data. Probability Low: All data collected within Robohome2.0 project are anonymous and the project is carried out in compliance with the Directive 95/46/EC about data protection. Moreover the Ethical Advisor Board will supervise all the project activities. Impact High. | 8, 9 | Robohome2.0 clinical partners are well experienced and will monitor all along project’s life with regards to ethics and privacy issues. Respective Ethical Committees will be consulted and ethical approval requested before any experimentation involving patients. |
| Technical risk: We will not be able to fit inside one PC both the game engine, the video processing required for tracking and the interfaces to the monitoring systems. Risk very low. The highest computational load is on the game engine. UMIL has accumulated a large experience on its game engine, that runs in real-time on a wide range of computers, also less power than the Core i7 mounted on Giraff. Impact High. Latency in the graphics with respect to elder movements would destroy amusement that is one of the elements on which gamification is built | 4, 7 | In this situation we will consider either a new generation PC to be integrated inside Giraff or an embedded PC for acquisition and processing data from Kinect camera that communicates in real-time (e.g. via GigaEthernet network) with the PC on Giraff. |
| There will be not enough exer-games to cover the needs specified in WP1. Risk very low: Exer-games will be developed upon IGER system that has allowed developing a total of 17 exer-games for REWIRE in one year. Impact medium: The impact depends on the criticality of the exer-games that could not be implemented. | 4 | We will allocate extra-resources to exer-games development during the second year of the project. |
| Technical risk: We will not be able to find enough elders for the pilot study. Risk low: PCL, SAS and KOMMUN serve a very large number of elders every year. Impact medium: Pilot duration needs to be prolonged. | 8 | We will reconsider the conditions set to enroll the patients and possibly contact other centers / hospitals. |

# 3.3 Consortium as a whole

## 3.3.1 Describe the consortium

The Robohome2.0 consortium is composed of 13 partners from 5 European countries (Italy, Spain, United Kingdom, France and Sweden). It gathers experts from the technological sector (UMIL, ORU, GIRAFF, UOP, SXT, POLIMI, BDIGITAL, SG, UMA), the clinical, psychological and assistance sectors (PCL, SAS, KOMMUN), the public administration (SAS, KOMMUN) and a large service provider (KORIAN). It joins the big industry (KORIAN), the small industry (SXT, SG, GIRAFF), the universities (UMIL, UOP, POLIMI, UMA), a private research center (BDIGITAL). Indeed, the consortium includes all the different perspectives involved in remote elder assistance. The technological development is led by UMIL. POLIMI will lead the research on Monitoring systems, BDIGITAL of the virtual community, ORU of the virtual caregiver, UMA of Giraff, UMIL of the activity center and UOP will take care of realizing meaningful interaction between the elder and the robot. Technological development will be continuously supported by the end-user partners: KOMMUN, SAS and PCL. These will lead the design of the Robohome2.0 functionalities and they will do the pilots tests. All the three parties have already been involved international projects and are reference centers in their country. Technology assessment and exploitation evaluation will be carried out by KORIAN supported by PCL, SAS and KOMMUN. Looking at the specific competencies, a multidisciplinary project always needs a “link partner” expert in enhancing dialogue and collaboration among clinical and technological experts. This role is covered by UML who has covered this role successfully in the projects FITREHAB and REWIRE. Two living labs will be set-up, one in Malaga and one in Orebro in which early testing will be carried out. Looking at the dissemination of the results, all the academic partners are strongly committed to spread their research results while KORIAN will supervise the exploitation with the help of SXT, SG and GIRAFF.

### 3.3.2 Describe the industrial / commercial involvement in the project

KORIAN is aiming to incorporate Robohome2.0 technology to enlarge its range of assistance services to the elder at home. SXT and SG are interested in developing innovative solutions in their specific domains and GIRAFF will be the natural node through which provide the technology to KORIAN. SG and SXT will bring specific competence in signal processing and sensing micro-architectures. With Robohome2.0 they will exploit their competence for potential new attractive market. GIRAFF is extremely interested in further developing Giraff robot. It totally adhere to the open source approach and it will exploit applications that show potentiality for the market.

# 3.4 Resources to be committed

## 3.4a Number of person / months required

|  | WP1 | WP2 | WP3 | WP4 | WP5 | WP6 | WP7 | WP8 | WP9 | WP10 | Total Person/ Months per Participant |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1/UMIL | 5 | 3 | 5 | 27 | 9 | 6 | 8 | 3 | 11 | 12 | 89 |
| 2/ORU | 7 | 6 | 15 | 7 | 4 | 2 | 5 | 3 | 3 | 1 | 53 |
| 3/GIRAFF | 0,5 | 1 | 1,5 | 0,5 | 0 | 0,5 | 8 | 1 | 2 | 0,3 | 15,3 |
| 4/UOP | 4 | 11 | 2 | 4 | 0 | 3 | 2 | 10 | 4 | 1 | 41 |
| 5/SXT | 0,5 | 3 | 1 | 4,5 | 30 | 0 | 4,5 | 0 | 1 | 1 | 45,5 |
| 6/PCL | 9 | 5 | 7 | 6 | 9 | 2 | 0 | 8 | 3 | 1 | 50 |
| 7/POLIMI | 5 | 6 | 9 | 16 | 20 | 5 | 4 | 7 | 3 | 2 | 77 |
| 8/BDIGITAL | 2 | 4 | 2 | 4 | 12 | 32 | 8 | 2 | 1 | 1 | 68 |
| 9/SAS | 8 | 1 | 2 | 2 | 3 | 3 | 0 | 24 | 2 | 2 | 47 |
| 10/KORIAN | 9 | 4 | 3 | 5 | 5 | 3 | 1 | 19 | 4 | 1 | 54 |
| 11/SG | 2 | 2 | 0 | 0 | 7 | 5 | 3 | 0 | 0,5 | 0,5 | 20 |
| 12/UMA | 2 | 6 | 22 | 8 | 0 | 0 | 6 | 2 | 1 | 1 | 48 |
| 13/KOMMUN | 4,5 | 2 | 3 | 1 | 2 | 2 | 0 | 6 | 3 | 1 | 24,5 |
| Total Person/Months | 58,5 | 54 | 72,5 | 85 | 101 | 63,5 | 49,5 | 85 | 38,5 | 24,8 | 632,3 |

## 3.4b ‘Other direct cost’

| 3/GIRAFF | Cost (€) | Justification |
| --- | --- | --- |
| Travel | 11.000 | 4.5K for project meetings, 6.5K for short visits and development / testing on partners site |
| Equipment | 9.700 | 1 robot Giraff: 9.7K |
| Other goods and services | 2.000 | Small mechanical components, electronics and cables |
| Total | 22.700 |  |

| 4/UOP | Cost (€) | Justification |
| --- | --- | --- |
| Travel | 17.000 | 4.5K for project meetings, 7K for Scientific meetings, 5.5K for short visits and development / testing on partners sites |
| Equipment | 9.700 | 1 robot Giraff: 9.7K |
| Other goods and services | 13.000 | 5K for students projects and 3K for external auditing 5K for material and software for testing. |
| Total | 39.700 |  |

| 5/SXT | Cost (€) | Justification |
| --- | --- | --- |
| Travel | 11.000 | 4.5K for project meetings, 6.5K for short visits and development/testing on partner sites |
| Equipment | 12.800 | 4.2K for specific SW licenses for the time dedicated to the project. 4.2K for SDK and licenses for new generation low-power CPUS and Bluetooth 4 Smart device SDK. 0.9K for 1 PC for development end test on field (three years and further demonstration). 3.5K for special plants and equipment for the production for the prototypes. |
| Other goods and services | 12.000 | Small mechanical components, electronics and cables. Small subcontracting for assembly and testing. |
| Total | 35.800 |  |

| 6/PCL | Cost (€) | Justification |
| --- | --- | --- |
| Travel | 13.000 | 4.5K for project meetings, 5.5K for scientific meetings; 2K for short visits and development/testing on partner sites |
| Equipment | 29.100 | 3 robots Giraff: 29.1K |
| Other goods and services | 3.000 | Clinical material for tests |
| Total | 45.100 |  |

| 7/POLIMI | Cost (€) | Justification |
| --- | --- | --- |
| Travel | 11.000 | 4.5K for project meetings, 4.5K for Scientific meetings, 2K for short visits and development / testing on partners sites. |
| Equipment | 30.000 | 12 full sets for clinically validated instrumentation for: blood pressure and heart rate physiological measurements (4800K), Equipment for multiparameters physiological measures (HR, BP Glucose, Oxygenation, 14400K), Glucometers (8400K). 2 laptop (2400K) |
| Other goods and services | 7.500 | 3,5K for external auditing, 4K for small mechanical components, electronics and cables |
| Total | 48.500 |  |

| 9/SAS | Cost (€) | Justification |
| --- | --- | --- |
| Travel | 14.000 | 7k for project meetings, 4k for WP training meetings, 3k for dissemination events attendance |
| Equipment | 29.100 | 3 robots Giraff: 29.1K |
| Other goods and services | 4.500 | 1.5K for pilot material, 3K for auditing and meeting organization |
| Total | 47.600 |  |

| 11/SG | Cost (€) | Justification |
| --- | --- | --- |
| Travel | 14.000 | 5.5K for project meetings, 8.5K for short visits and testing on partners site. |
| Equipment | 0 | - |
| Other goods and services | 9.000 | DSP and FPGA development boards, hardware components, development software for 9K Euros. |
| Total | 23.000 |  |

| 12/UMA | Cost (€) | Justification |
| --- | --- | --- |
| Travel | 18.000 | 9 K for project meetings, 6 K for scientific events (conferences, workshops, etc.), 3 K for supporting the pilot test site and for short visit to partner sites |
| Equipment | 9.700 | 1 robot Giraff: 9.7K |
| Other goods and services | 3.500 | 1.5K for PSC meetings organization, 2K for Kinect, webcam, calibration structures and objects |
| Total | 31.200 |  |

| 13/KOMMUN | Cost (€) | Justification |
| --- | --- | --- |
| Travel | 10.000 | 4.5 K for project meetings, 5,5 K for scientific events (conferences, workshops, etc.) |
| Equipment | 9.700 | 1 robot Giraff for 9.7K |
| Other goods and services | 2.000 | Clinical material for tests |
| Total | 21.700 |  |

# Abbreviations

AAL – Ambient Assisted living

ADL – Activity of Daily life

AI – Artificial Intelligence

CA – Consortium Agreement

CHA – Continuous Health Alliance

COPD - Chronic obstructive pulmonary disease

DB – DataBase

DL – Description Language

DoW – Description of Work

EAB – Ethical Advisory Board

EUAB – End-Users Advisory Board

EC – European Commission

FP7 – 7th FrameProgram

FTD – Fronto Temporal Dementia

GLVM - Gaussian Latent Variable Models

GP – General Practitioner

GUI – Graphical User Inteface

HRI – Human Robot Interfaces

HW – Hardware

ICER – Incremental Cost Effectiveness Ratio

IGER – Intelligent Game Engine for Rehabilitation

IPR – Intellectual Property Right

IT – Information technology

KOMMUN – Orebro Municipality (Orebro Kommun)

NUI – Natural Users Interfaces

OS- Operating System

OWL – Ontoloty Web Language

PC – Project Coordinator

PCL – Fondazione IRCCS Cà Granda Ospedale Maggiore Policlinico

PFSM – Probabilistic Finite State Machines

PO – Project Officer

PSC – Project Steering Committee

QMCI - Quick Mild Cognitive Impairment score (test)

RFID – Radio Frequency Identification Device

RGB – RedGrenBlue, a digital color image code

TAM – Technology Assessment Model

TRL – Technology Readiness Level.

SMS – Short Message Service

SOA – Service Oriented Architecture

SQL – Structured Query Language

SXT – SXT srl

SW - Software

SWRL – Semanting Web Rules Language

TUG – Timed Up and Go, test used for physical assessment

UML - Unified Modeling Language

VC – Virtual Caregiver

VCA – Virtual Caregiver Avatar

Giannakouris k., Aging characterizes the demographic perspective in the European Societies, Eurostat, Statistics in focus, 2008, 72. http://eppeurostat.ec.europa.eu

P. Buerhaus, BCurrent and future state of the US nursing workforce, J. Amer. Med. Assoc., vol. 300, no. 20, pp. 2422–2424, 2008. Nursing Shortage Fact Sheet, American Association of Colleges of Nursing, 2010. Online at http://www.aacn.nche.edu/media/FactSheets/NursingShortage.htm...

http://oreilly.com/web2/archive/what-is-web-20.html

http://www.giraff.org/

T.Bickmore, R.Picard, Establishing and maintaining long-term human-computer relationships, ACM Trans. CHI, Volume 12:2, 2005, pp 293 – 327.

Alexopoulos G. Depression in the elderly. Lancet, 2005; 365: 1961-70.

M. Fayzullin, V. S. Subrahmanian, M. Albanese, C. Cesarano, A. Picariello, Story creation from heterogeneous data sources, Multimedia Tools and Applications, 33(3), 351-377, 2007.

Cattinelli I, Goldwurm M, Borghese NA, Interacting with an artificial partner: modeling the role of emotional aspects, Biol. Cybern. 99(6), 473-489, 2008.

V. Propp, Morphology of the Folktale: Revised and Edited with Preface by L.A. Wagner, Introduction by A. Dundes (Vol. 9), University of Texas Press, 2010.

https://developers.google.com/translate/

http://www.z-wave.com/

E. Baum, D. Jarjoura, A. E. Polen, D. Faur, and G. Rutecki, BEffectiveness of a group exercise program in a long-term care facility: A randomized pilot trial. J. Amer. Med. Directors Assoc., vol. 4, pp. 74–80, 2003.

D. Dawe and R. Moore-Orr, BLow-intensity, range-of-motion exercise: Invaluable nursing care for elderly patients, J. Adv. Nursing, 21, pp. 675–681, 1995.

M. D. McMurdo and L. M. Rennie, BA controlled trial of exercise by residents of old people’s homes, Age and Ageing, vol. 22, pp. 11–15, 1993.

V. Thomas and P. Hageman, B Can neuromuscular strength and function in people with dementia be rehabilitated using resistance-exercise training? Results from a preliminary intervention study, J. Gerontol. A, Biol. Sci. Med. Sci., vol. 58, pp. M746–M751, 2003.

S. Colcombe and A. Kramer, BFitness effects on the cognitive function of older adults, Psychol. Sci., vol. 14, pp. 125–130, 2003.

S. J. Colcombe, A. F. Kramer, K. I. Erickson, P. Scalf, E. McAuley, N. J. Cohen, A. Webb, G. J. Jerome, D. X. Marquez, and S. Elavsky, BCardiovascular fitness, cortical plasticity,and aging,[ in Proc. Nat. Acad. Sci. USA, 2004, vol. 101, pp. 3316–3321.

W. Spirduso and P. Clifford, BReplicationof age and physical activity effects on reaction and movement time, J. Gerontol., vol. 33, pp. 26–30, 1978.

Z. B. Moak and A. Agrawal, BThe association between perceived interpersonal social support and physical and mental health: Results from the national epidemiological survey on alcohol and related conditions, J. Public Health, vol. 32, pp. 191–201, 2010.

L. K. George, D. G. Blazer, D. C. Hughes, and N. Fowler, BSocial support and the outcome of major depression,[ British J. Psychiatry, vol. 154: 478–485, 1989.

E. Paykel, BLife events, social support and depression,[ Acta Psychiatrica Scandinavica, vol. 89, pp. 50–58, 1994.

B. Prospective relations between social support and depression: Differential direction of effects for parent and peer support? J. Abnormal Psychol., vol. 113, pp. 155–159, 2004.

S. A. Stansfeld, G. S. Rael, J. Head,M. Shipley, and M. Marmot, B Social support and psychiatric sickness absence: A prospective study of British civil servants, Psychol. Med., vol. 27, pp. 35–48, 1997.

1.Nathan DG. Careers in translational clinical research - Historical perspectives, future challenges. JAMA 2002;287(18):2424-7.

http://www.innovation4welfare.eu/307/subprojects/robo-m-d.html

http://www.aal-europe.eu/projects/excite/

http://www.innovation4welfare.eu/287/fitrehab.html

http://www.signomotus.it/h_cad_site/h_cad_accessible/system_description.htm

http://www.backhome-fp7.eu/content/project

http://www.cupid-project.eu/

http://rgs-project.upf.edu

M. Pirovano, R. Mainetti, G. Baud-Bovy, P.L. Lanzi, N.A. Borghese, IGER – Intelligent Game Engine for Rehabilitation, IEEE Trans. CIAIG, submitted. Short version in Proc. CIG 2012.

N.A. Borghese, P.L. Lanzi, R. Mainetti, M. Pirovano, Apparatus and method for rehabilitation employing a game engine, US Application 13/911577, 2013

Laurie K. Garda, Wendy Armstrong, Amy Blew, Jyotsna Rao ,US Patent US20120253509, 2013.

Steven N. W. Hunter, David M. Browning, Dennis J. Fuhrman, William C. Park, IV. Automatic apparatus for storing and dispensing packaged medication and other small elements, US7100792 B2, 2006.

http://www.zephyranywhere.com/healthcare/zephyrlife-home/

http://www.alivecor.com/home

http://www2.imec.be/be_en/home.html

http://www.diabetes.co.uk/diabetes_care/blood_glucose_monitor_guide.html

https://www.glooko.com/android

Clark RA, Pua YH, Fortin K, Ritchie C, Webster KE, Denehy L, Bryant AL, Validity of the Microsoft Kinect for assessment of postural control, Gait & Posture, 36(3), 372-377, 2012.

Berg KO, Wood-Dauphinee SL, Williams JT, Gayton D. Measuring balance in the elderly: preliminary development of an instrument. Physiotherapy Canada 1989;41:304-311.

Podsiadlo, D; Richardson, S (1991). "The timed 'Up & Go': A test of basic functional mobility for frail elderly persons". Journal of the American Geriatrics Society 39 (2): 142–8. PMID 1991946.

Morse JM, Morse RM, Tylko SJ. Development of a scale to identify the fall-prone patient. Can J Aging 1989;8;366-9.

http://www.xsens.com/products/

http://www.gaitup.com/

http://www.digifit.com/shop/health.asp.

http://z-devicetest.zausan.com/index.php?lang=en

Serio SM, Assaf T, Cecchi F, Laschi C, Dario P. A novel Wireless Toy for Measuring Infants’ Bimanual Actions. The Fourth IEEE RAS/EMBS Int. Conference on Biomedical Robotics and Biomechatronics Roma, Italy. June 24-27, 2012

J Hermsdörfer J, Bienkiewicz M, Cogollor JM, Russel M, Jean-Baptiste E, Parekh M, Wing AM, Ferre M, Hughes C. CogWatch Automated Assistance and Rehabilitation of Stroke-Induced Action Disorders in the Home Environment. D. Harris (Ed.): EPCE/HCII 2013, Part II, LNAI 8020, 343–350, Springer 2013,

O’Caoimh R, Gao Y, McGlade C et al. Comparison of the Quick Mild Cognitive Impairment (Qmci) screen and the SMMSE in Screening for mild cognitive impairment. Age Ageing 2012; 41(5): 624–9.

Folstein MF, Folstein SE, McHugh PR. Journal of Psuchiatric Research 1975;12:189. Molloy DW, Standish TIM. A guide to the Standardized Mini-Mental State Examination. Int Psychogeriatrics 1997;9: 87–94.

http://www.doctot.com/doctot-apps/dementia-app/.

Grossman M. Fronto temporal dementia: a review. J Int Neuropsychol Soc. 2002;8:566–583

E. Vargiu, L. Ceccaroni, L. Subirats, S. Martin, and F. Miralles. User Profiling of People with Disabilities - A Proposal to Pervasively Assess Quality of Life. In ICAART 2013 - Proceedings of the 5th International Conference on Agents and Artificial Intelligence, Volume 2, J. Filipe, A. L. N. Fred (Eds.) Barcelona, Spain, 15-18 February, 2013. SciTePress 2013.

http://www.z-wave.com/

https://www.sticknfind.com/, http://www.thetileapp.com

Clark RA, Pua YH, Fortin K, Ritchie C, Webster KE, Denehy L, Bryant AL, Validity of the Microsoft Kinect for assessment of postural control, Gait & Posture, 36(3), 372-377, 2012.

Mainetti R, Sedda A, Ronchetti M, Bottini G, Borghese NA. Duckneglect: video-games based neglect rehabilitation. Tech Health Care 21 97–111 97, 2013.

J Fasola and MJ Mataric Using Socially Assistive Human–Robot Interaction to Motivate Physical Exercise for Older Adults, IEEE Proc. Vol. 100,No. 8, August 2012, pp. 2512-2526.

J. Schell, The Art of Game Design: Book of Lenses. Elsevier, 2008

“From Game Design Elements to Gamefulness: Defining ‘Gamification’”, Sebastian Deterding et al., Proceedings of the 15th International Academic MindTrek Conference. 2011

Deterding, S., Dixon, D., Khaled R., & Nacke L. From Game Design Elements to Gamefulness: Defining “Gamification”, Proceedings of MindTrek, 2011

http://www.leaderboarded.com/home/

http://wiisports.nintendo.com/

J. Schell, The Art of Game Design: Book of Lenses. Elsevier, 2008.

Csikszentmihalyi M, ―Flow: The psychology of optimal experience,‖Harper Perennial, 1991.

Kirk J, ―Burning man,‖ http://www.gq.com/news-politics/newsmakers/201202/burning-man-sam-brown-jay-kirk-gq-february-2012?currentPage=1, 2012

“Meaningful play - getting gamification right”, Sebastian Deterding, Google Tech Talk 2011

“Design outside the Box”, Jesse Schell, DICE Summit 2010

Mainetti R, Sedda A, Ronchetti M, Bottini G, Borghese NA. (2013) Duckneglect: video-games based neglect rehabilitation. Technology and Health Care 21 97–111 97. DOI 10.3233/THC-120712 IOS Press.

M. Zuckerman, J. Porac, D. Lathin, R. Smith, and E. L. Deci, BOn the importance of self-determination for intrinsically motivated behavior,[ Personality Social Psychol. Bull., vol. 4, pp. 443–446, 1978.

E. Deci and R. Ryan, Intrinsic Motivation and Self-Determination in Human Behavior. New York: Plenum, 1985, pp. 29, 318, 322.

. Gervàs, Pablo – 2012 - Story Generation Algorithms. The Living Handbook of Narratology. Accessed online at http://wikis.sub.uni-hamburg.de/lhn/index.php/Story_Generator_Algorithms.

Mani, Inderjeet - 2013 - Story Generation Algorithms. The Living Handbook of Narratology. Accessed online at http://wikis.sub.uni-hamburg.de/lhn/index.php/Computational_Narratology.

McIntyre, Neil - 2011 - Learning to tell tales: automatic story generation from corpora, PhD Thesis

J. Meehan. An interactive program that writes stories. In Proceedings of the 5th International Joint Conference on Artificial Intelligence, pages 91–98, Cambridge, Massachusetts, 1977.

Dehn, N, Story Generation After TALE-SPIN, In IJCAI (Vol. 81, pp. 16-18), 1981.

M. Lebowitz. Story-telling as planning and learning. Poetics, 14:483–502, 1985.

S. R. Turner. Ministrel: A Computer Model of Creativity and Sotrytelling. UCLA, 1992.

R. Pérez y Pérez and M. Sharples. Mexica: A computer model of a cognitive account of creative writing. Journal of Experimental and Theoretical Artificial Intelligence (JETAI), 13(2):119–139, April 2001.

Swartjes and M. Theune. The virtual storyteller: Story generation by simulation. In Proc. 20th Belgian-Netherlands Conference on Artificial Intelligence, BNAIC 2008, pages 257–264, Enschede, the Netherlands, October 2008.

C. Fairclough and P. Cunningham. A multiplayer case based story engine. In Proc. of the 4th Int. Conf. Intelligent Games and Simulation (GAME-ON 2003), pages 41–46, London, UK, November 2003.

Riedl MO, Young RM, Narrative planning: balancing plot and character, Journal of Artificial Intelligence Research, 39(1), 217-268, 2010

McIntyre, Neil - 2011 - Learning to tell tales: automatic story generation from corpora, PhD Thesis.

Klein, S., J.F. Aeschlimann, D. F. Balsiger, S. L. Converse, C. Court, M. Foster, R. Lao, J. D. Oakely & J. D. Smith. Automatic Novel Writing. UWCS Tech Report No. 186, 109 pages, 1973.

Bringsjord, Selmer; Ferrucci, David's Artificial Intelligence and Literary Creativity: Inside the Mind of Brutus, A Storytelling Machine 1st (first) edition by Bringsjord, Psychology Press [Hardcover] (1999)

Pemberton L. (1989) A modular approach to story generation, in: 4th European ACL, Manchester, 1989 217–224.

H. Liu and P. Singh. Makebelieve: Using commonsense reasoning to generate stories. In Proc. of the 18th National Conference on Artificial Intelligence, pp 957–958, Edmonton, CA, August 2002.

M. Fayzullin, V. S. Subrahmanian, M. Albanese, C. Cesarano, and A. Picariello. Story

creation from heterogeneous data sources. Multimedia Tools and Applications, 33 (3):351–377, June 2007.

F. Peinado, P. Gervás, and B. Díaz-Agudo. A description logic ontology for fairy tale generation. In Proceedings of the 4th International Conference on Language Resources and Evaluation: Workshop on Language Resources for Linguistic Creativity, pages 56–61, Lisbon, Portugal, May 2004.

Kerfoot BP, Baker H, Pangaro L, Agarwal K, Taffet G, Mechaber AJ, Armstrong EG. An online spaced-education game to teach and assess medical students: a multi-institutional prospective trial. Acad Med. 2012 Oct;87(10):1443-9.

M. Graafland, J. M. Schraagen and M. P. Schijven. Systematic review of serious games for medical education and surgical skills training. Article first published online: 7 SEP 2012 DOI: 10.1002/bjs.8819

Adams SA. Use of "serious health games" in health care: a review. Stud Health Technol Inform. 2010;157:160-6.

Emeka G. Anyanwu, Anatomy adventure: A board game for enhancing understanding of anatomy, Anatomical Sciences Education, 2014, 7, 2

Shieh L. et al., Septris, 2011, available online at http://med.stanford.edu/septris/game/SeptrisTitle.html

PL Lanzi, D Loiacono, E Parini, F Sannicolo’, C Scamporlino & M. Pirovano. Tuning Mobile Game Design Using Data Mining. IGC 2013 conference

http://www.badbloodgame.net/

Lyttle, DJ; Ryan, A. (2010). "Factors' influencing older patients' participation in care: A review of the literature". Int. J. Older People Nursing 5(4): 274–282.

Mainetti R, Sedda A, Ronchetti M, Bottini G, Borghese NA. (2013) Duckneglect: video-games based neglect rehabilitation. Technology and Health Care 21 97–111 97. DOI 10.3233/THC-120712 IOS Press.

Pirovano M, Ren CY, Frosio I, Lanzi PL, Prisacariu V, Murray DW, Borghese NA, Robust Silhouette Extraction from Kinect Data, In: Image Analysis and Processing–ICIAP 2013 (pp. 642-651). Springer Berlin Heidelberg, 2013.

VA Prisacariu ID Reid PWP3D: Real-time Segmentation and Tracking of 3D Objects, Int. J. Computer Vision, 98(3), 2013; CY Ren, VA Prisacariu, DW Murray, I Reid: STAR3D: Simultaneous Tracking and Reconstruction of 3D Objects Using RGB-D Data. ICCV 2013: 1561-1568.

http://research.microsoft.com/en-us/projects/surfacerecon/

http://msdn.microsoft.com/en-us/library/dn188670.aspx

.L. Blanco, J. Gonzalez-Jimenez, J.A. Fernandez-Madrigal, "Optimal Filtering for Non-Parametric Observation Models: Applications to Localization and SLAM", The International Journal of Robotics Research (IJRR), vol. 29, no. 14, 2010.

http://www.universaal.org/index.php/en/

MU Ahmed, A Loutfi, Physical Activity Identification using Supervised Machine Learning and based on Pulse Rate, International Journal of Advanced Computer Sciences and Applications 4 (7), 2013.

M Alirezaie, A Loutfi, Ontology alignment for classification of low level sensor data. Knowledge Eng. Ontology Dev KEOD Best Student Paper Award, 2012.

Breazeal, C. C.Kidd, A.Thomaz, G.Hoffman, and M.Berlin, “Effects of nonverbal communication on efficiency and robustness in human- robot teamwork,” in Intelligent Robots and Systems, 2005. (IROS 2005), pp. 708 – 713.

Coradeschi, S.; Cesta, A.; Cortellessa, G.; Coraci, L.; Gonzalez, J.; Karlsson, L.; Furfari, F.; Loutfi, A.; Orlandini, A.; Palumbo, F.; Pecora, F.; von Rump, S.; Stimec, A.; Ullberg, J.; Östlund, B., "GiraffPlus: Combining social interaction and long term monitoring for promoting independent living," The 6th Int. Conf. Human System Interaction (HSI), 2013, pp.578,585.

Broz F., Di Nuovo A., Belpaeme T., Cangelosi A. Multimodal Robot Feedback for Eldercare. Workshop at IEEE ROMAN IEEE International Symposium on Robots and Human Interactive Communications. 2013.

Li S, Wrede B Why and how to model multi-modal interaction for a mobile robot companion In: AAAI Technical Report SS-07-04: Interaction Challenges for Intelligent Assistants. Stanford: AAAI Press: 71–79 2007.

NA Borghese, M Pirovano, PL Lanzi, S Wuest and ED de Bruin (2013), Computational Intelligence and Game Design for effective home-based stroke at Home Rehabilitation. Games for Health Journal. April 2013, Vol. 2, No. 2: 81-88.

Leimeister, J.M.; Sidiras, P.; Krcmar, H., "Success factors of virtual communities from the perspective of members and operators: an empirical study," System Sciences, 2004. Proceedings of the 37th Annual Hawaii International Conference on , vol., no., pp.10 pp. 5-8 Jan. 2004.

http://www.leaderboarded.com/home/

Christensen H, Griffiths K, Jorm A Delivering interventions for depression by using the internet: randomised controlled trial BMJ 2004;328:265. Griffiths K, Farrer L and Christensen H. The efficacy of internet interventions for depression and anxiety disorders: a review of randomised controlled trials. Medical Journal of Australia, 2010

Paré G, Moqadem K , Pineau G, and St-Hilaire C, Clinical Effects of Home Telemonitoring in the Context of Diabetes, Asthma, Heart Failure and Hypertension: A Systematic Review, J Med Internet Res. 2010 Apr-Jun; 12(2).

I. Carpinella, P. Crenna, E. Calabrese, M. Rabuffetti, P. Mazzoleni, R. Nemni, and M. Ferrarin Locomotor Function in the Early Stage of Parkinson’s Disease, IEEE Trans. Neural Syst. Rehab. Engin., Vol. 15, No. 4, 2007, 543-551. R. Baltadjieva, N. Giladi, L. Gruendlinger, C. Peretz, and J. M. Hausdorff, “Marked alterations in the gait timing and rhythmicity of patients with de novo parkinson’s disease,” Eur. J. Neurosci., vol. 24, no. 6, pp. 1815–1820, Sep. 2006. Ansuini Caterina; Begliomini Chiara; Ferrari Tania; Castiello Umberto Testing the effects of endgoal during reach-to-grasp movements in Parkinson's disease. Brain and cognition 2010;74(2):169-77.

E.Todorov, M-Jordan, Optimal feedback Control as a Theory of Motor Coordination, Nature Neuroscience, 2002; E.Todorov, Optimality principles in sensorimotor Control, Nature Neuroscience, 2004.

Rasmussen, C.E.; Williams, C.K.I (2006). Gaussian Processes for Machine Learning. MIT Press.

N.D. Lawerence and A.J. Moore. Hierarchical Gaussian process latent variable models. In Z. Gharamani, Ed. Proc. Int. Conf. Machine Learning, vol. 24::481-488, 2007; Titsias and Lawrence, Proc. 13th Int. Conf. on Artiﬁcial Intelligence and Statistics (AISTATS) 2010.

Grasso, R., Bianchi, L., Lacquaniti, F. (1998) Motor patterns for human gait : backward versus forward locomotion. J. Neurophysiol. 80 : 1868-1885.

Cattinelli I, Goldwurm M, Borghese NA, Interacting with an artificial partner: modeling the role of emotional aspects, Biol Cybern,99(6), 473-489, 2008.

Scott A Green, Mark Billinghurst, Xiaoqi Chen, J Geoffrey Chase Human-robot collaboration: A literature review and augmented reality approach in design International Journal of of Advanced Robotic Systems (2008) Volume: 5, Issue: 1, Pages: 1-18; G. Guerra-Filho and Y. Aloimonos. Understanding visuomotor primitives for motion synthesis and analysis. Comp. Anim. Virtual Worlds, 17:207–217, 2006. P. Beaudoin, S. Coros, A. Anagnostopoulos, M. Vlachos, M. Hadjieleftheriou, E. J. Keogh, and P. S. Yu. Global distance-based segmentation of trajectories. In KDD, pages 34–43, 2006). A. Ghotkar, G.K. Kharate, Hand Segmentation Techniques to Hand Gesture Recognition for Natural Human Computer Interaction Int. Journal of Human Computer Interaction (IJHCI), Volume (3) : Issue (1) : 2012

http://www.callcentrehelper.com/how-to-use-vocal-pitch-and-pace-on-the-phone-2644.htm

P. A. Naylor, A. Kounoudes, J. Gudnason, and M. Brookes, “Estimation of Glottal Closure Instants in Voiced Speech using the DYPSA Algorithm,” IEEE Trans on Speech and Audio Processing, vol. 15, pp. 34–43, Jan. 2007

http://www.mathworks.com/matlabcentral/linkexchange/links/797-voicebox-speech-processing-toolbox-for-matlab

http://pen.made-in-china.com/showroom/dragonxander

http://www.indiegogo.com/projects/sticknfind-bluetooth-powered-ultra-small-location-stickers

Junyi Zhou, Jing Shi. Performance evaluation of object localization based on active radio frequency identification technology. J. Computers in Industry archive. Vol. 60:9, 2009, pp 669-676.

“From Game Design Elements to Gamefulness: Defining ‘Gamification’”, Sebastian Deterding et al., Proceedings of the 15th International Academic MindTrek Conference. 2011

Zichermann, Gabe; Cunningham, Christopher (August 2011). "Introduction". Gamification by Design: Implementing Game Mechanics in Web and Mobile Apps (1st ed.). Sebastopol, California: O'Reilly Media. p. xiv. ISBN 1449315399.

J. Schell, The Art of Game Design: Book of Lenses. Elsevier, 2008.

Csikszentmihalyi M, ―Flow: The psychology of optimal experience,‖Harper Perennial, 1991.

Byron Reeves, J. Leighton Read (2009). Total Engagement: Using Games and Virtual Worlds to Change the Way People Work and Businesses Compete. Harvard Business Press. p. 177. ISBN 978-1-4221-4657-6.

N.A. Borghese, P.L. Lanzi, R. Mainetti, M. Pirovano, Apparatus and method for rehabilitation employing a game engine, US Application 13/911577, 2013.

Ramscar, M., Hendrix, P., Shaoul, C., Milin, P. and Baayen, H. (2014), The Myth of Cognitive Decline: Non-Linear Dynamics of Lifelong Learning. Topics in Cognitive Science, 6: 5–42. doi: 10.1111/tops.12078

S.Kim A.K. Dey Simulated Augmented Reality Windshield Display as a Cognitive Mapping Aid for Elder Driver Navigation, CHI2009

Colombo, R., Pisano, F., Mazzone, A., Delconte, C., Micera, S., Carrozza, M. C., Dario, P., et al. Design strategies to improve patient motivation during robot-aided rehabilitation. Journal of neuroengineering and rehabilitation, 4, 3, 2007,

Mainetti R, Sedda A, Ronchetti M, Bottini G, Borghese NA, Duckneglect: video-games based neglect rehabilitation, Tech Health Care, 21(2), 97-111, 2013.

M. Zuckerman, J. Porac, D. Lathin, R. Smith, and E. L. Deci, BOn the importance of self-determination for intrinsically motivated behavior Personality Social Psychol. Bull., vol. 4, pp. 443–446, 1978.

E. Deci and R. Ryan, Intrinsic Motivation and Self-Determination in Human Behavior. New York: Plenum, 1985, pp. 29, 318, 322.

Togelius J, Whitehead J and Bidarra R (2011) Procedural content generation in games. IEEE Transactions on Computational Intelligence and AI in Games 3(3):169-171, doi: 10.1109/TCIAIG.2011.2166554.

E. Propp, Morphology of the Folktale: Second Edition, Revised and Edited with Preface by Louis A. Wagner, Introduction by Alan Dundes, 1968, original version in Russian, 1928.

F. Peinado, P. Gervás, and B. Díaz-Agudo. A description logic ontology for fairy tale generation. In Proceedings of the 4th International Conference on Language Resources and Evaluation: Workshop on Language Resources for Linguistic Creativity, pages 56–61, Lisbon, Portugal, May 2004.

Cattinelli I, Goldwurm M, Borghese NA, Interacting with an artificial partner: modeling the role of emotional aspects, Biol Cybern,99(6), 473-489, 2008.

Jordan MI, Bishop C, Introduction to graphical models, 2004.

Villacorta P, Quesada L and Pelta D. Automatic Design of Deterministic Sequences of Decisions for a Repeated Imitation Game with Action-State Dependency - Proc. CIG 2012.

Alamia M, Borghese NA, (2010) Creating long gait animation sequences through Reinforcement Learning Frontiers in Artificial Intelligence and Applications; Volume 226, 2011; Neural Nets WIRN10 – Proc.20th Italian Workshop on Neural Nets, pp. 144 – 151.

Riedl and Young, Narrative Planning: Balancing Plot and Character, Journal of Artificial Intelligence Research 39 (2010) 217-268.

JR Lukos C Ansuini, M Santello, Anticipatory control of grasping: independence of sensorimotor memories for kinematics and kinetics J Neurosci. 28(48): 12765–12774, 2008.

Topka H, Konczak J, Dichgans Coordination of multi-joint arm movements in cerebellar ataxia: analysis of hand and angular kinematics. J.Exp Brain Res. 1998 Apr;119(4):483-92.

T. W. Bickmore and R. W. Picard, B Establishing and maintaining long-term human-computer relationships[ ACM Trans. Comput.-Human Interaction, vol. 12, no. 2, pp. 293–327, Jun. 2005.

Belpaeme, T., Baxter, P., Read, R., Wood, R., Cuayáhuitl, H., Kiefer, B., Racioppa, S., Kruijff-Korbayová, I., Athanasopoulos, G., Enescu, V., Looije, R., Neerincx, M., Demiris, Y., Ros-Espinoza, R., Beck, A., Cañamero, L., Hiolle, A., Lewis, M., Baroni, I., Nalin, M., Cosi, P., Paci, G., Tesser, F., Sommavilla, G. & Humbert, R. (2012) Multimodal Child-Robot Interaction: Building Social Bonds. Journal of Human-Robot Interaction, 1(2), 33-53.

Takayama, L., Dooley, D. and Ju, W. (2011). Expressing thought: Improving robot readability with animation principles. Proceedings of the IEEE/ACM International Conference on Human-Robot Interaction.

T. Ducourant, S. Vieilledent, Y. Kerlirzin, and A. Berthoz, “Timing and distance characteristics of interpersonal coordination during locomotion,” Neuroscience Letters, vol. 389, no. 1, pp. 6–11, November 2005.

E. Sisbot, L. Marin-Urias, R. Alami, and T. Simeon, “A Human Aware Mobile Robot Motion Planner,” IEEE Transactions on Robotics, vol. 23, no. 5, pp. 874–883, Oct. 2007; D. J. Feil-Seifer and M. J. Matari´c, “People-Aware Navigation For Goal-Oriented Behavior Involving a Human Partner,” in Proceedings of the International Conference on Development and Learning, Frankfurt am Main, Germany, Aug. 2011.

De Cindio, F, Peraboni, C, Building digital participation hives: Toward a local public sphere. In M Foth, L Forlano, C Satchell & M Gibbs (Eds), From social butterfly to engaged citizen: Urban informatics, social media, ubiquitous computing, and mobile technology to support citizen engagement. MIT Press, 2011

Nonaka I., Takeuchi H., The Knowledge Creating Company, University Press, Oxford 1995.

Communication from the Commission to the European Parliament, the Council, the European Economic and Social Committee and the Committee of the regions on “Telemedicine for the benefit of patients, healthcare systems and society”, COM(2008)689, November 2008

Meystre, S., The current state of telemonitoring: A comment on the literature. Telemedicine and E-Health (2005), 11, 63-9

Paré, G., Jaana, M., Sigotte, C., Systematic Review of Home Telemonitoring for Chronic Diseases: The Evidence Base, Journal of the American Medical Informatics Association (2007), 14, 3: 269-277.

LeRouge C, Tulu B, Forducey P, The Business of Telemedicine: Strategy Primer, Telemedicine and e-Health, vol.16, n.8, October 2010

Bensink, M., Hailey, D., Wootton, R., Home telehealth: Connecting care within the community. In: Wootton, R., Dimmick, S.L., Kvedar, J.C. (eds). The evidence Base. Oxon: Royal Society of Medicine Press, 2006, p 53-62

LaMonte MP, Bahouth MN, Xiao Y, Hu P, Baquet CR, Mackenzie CF. Outcomes from a comprehensive stroke telemedicine program. Telemed J E Health. 2008;14(4):339-344.

Hess DC Wang S Gross H Nichols FT Hall CE Adams RJ. Telestroke: extending stroke expertise into underserved areas. Lancet Neurol 2006 5(3):275-278.

McCue MJ, Palsbo SE. Making the business case for telemedicine: an interactive spreadsheet. Telemed J E Health. 2006;12(2):99-106.

Sritipsukho PF, Riewpaiboon AF, Chaiyawat PF, Kulkantrakorn K. Cost-effectiveness analysis of home rehabilitation programs for Thai

stroke patients. J Med Assoc Thai 2010;93(Suppl 7):262-70.

Gori C. & Da Roit B. (2006) The Italian way to commodification of care. In: C. Ungerson & S. Yeandle (Eds) The Changing Boundaries Between Paid and Unpaid Care, pp.223–258. Palgrave, London

Gori C. Home care in Italy: a system on the move, in the opposite direction to what we expect. Health Soc Care Community. 2012 May;20(3):255-64

Lamura G. et al. (2010) Migrant workers in the long-term care sector: lessons from Italy. Health and Ageing Newsletter 22 (1), 1–6.

Gori C. Home care in Italy: a system on the move, in the opposite direction to what we expect. Health Soc Care Community. 2012 May;20(3):255-64

http://eur-lex.europa.eu/LexUriServ/LexUriServ.do?uri=COM:2008:0689:FIN:EN:PDF

http://eur-lex.europa.eu/JOHtml.do?uri=OJ:C:2009:318:SOM:en:HTML

Pinson, Linda. (2004). Anatomy of a Business Plan: A Step-by-Step Guide to Building a Business and Securing Your Company’s Future (6th Edition). Page 20. Dearborn Trade: Chicago, USA.

Ortún V, Pinto JL, Puig-Junoy J. La economía de la salud y su aplicación a la evaluación. Aten Primaria,

2001; 27:62

Fried LP, Walston J. Frailty and failure to thrive. In: Hazzard WR, Blass JP, Ettinger WH Jr, et al, eds. Principles of Geriatric Medicine and Gerontology. 5th edition. New York, NY: The McGraw-Hill Companies;2003;1487-1502

Tinetti ME. Performance-oriented assessment of mobility problems in elderly patients. JAGS 1986; 34: 119-126

Puthoff M. (2008) Outcome measures in cardiopulmonary physical therapy: SPPB. Cardiopulmonary Physical Therapy J. 19 (1): 17-22

Guralnik JM, Ferrucci L, Simonsick EM et al. Lower-extremity function in persons over the age of 70 years as a predictor of subsequent disability. N Engl J Med 1995; 332: 556–61

Action Plan on “Prevention and early diagnosis of frailty and functional decline, both physical and cognitive, in older people” of the European Innovation Partnership on Active and Healthy Ageing (Bruxelles, November 6, 2012)

F.D. Davis, "Perceived usefulness, perceived ease of use, and user acceptance of information technology", MIS Quarterly vol. 13, no. 3, pp. 319–340, 1989.

V. Venkatesh, M.G. Morris, G.B. Davis, and F.D. Davis, "User acceptance of information technology: Toward a unified view", MIS Quarterly, Vol. 27, No. 3, pp. 425–478, 2003

http://www.z-wave.com/

L Constantine and H. Windl “Usage-Centered Design: Scalability and Integration with Software Engineering.” In C. Stephanidis and J. Jacko (Eds.) Human-Computer Interaction: Theory and Practice. Proceedings of the 10th International Conference on Human-Computer Interaction, Crete, Greece, 22-27 June 2003. Mahwah, New Jersey: Lawrence Erlbaum Associates, 2003. L.Constantine, . Software for Use: A Practical Guide to the Models and Methods of Usage-Centered Design, Addison-Wesley, 1st ed. 1999.

http://www.theage.com.au/news/entertainment/when-fantasy-is-just-too-close-for-comfort, The Age, June 10, 2007. Mori, Masahiro (1970). Bukimi no tani The uncanny valley (K. F. MacDorman & T. Minato, Trans.). Energy, 7(4), 33–35. (Originally in Japanese). 48 J. Seyama, R.S. Nagayama, The Uncanny Valley: Effect of Realism on the Impression of Artificial Human Faces, Presence, Vol. 16, No. 4, August 2007, 337–351, 2007

M. Pirovano, R. Mainetti, G. Baud-Bovy, P.L. Lanzi, N.A. Borghese, IGER – Intelligent Game Engine for Rehabilitation, IEEE Trans. CIAIG, submitted.

Broz F., Di Nuovo A., Belpaeme T., Cangelosi A. Multimodal Robot Feedback for Eldercare. Workshop at IEEE ROMAN IEEE International Symposium on Robots and Human Interactive Communications. 2013.

Kolawa, Adam; Huizinga, Dorota (2007). Automated Defect Prevention: Best Practices in Software Management. Wiley-IEEE Computer Society Press.

http://www.osgi.org/

http://tyromotion.com/en/products/tymo/overview

J.L. Blanco, J. Gonzalez-Jimenez, J.A. Fernandez-Madrigal, "Optimal Filtering for Non-Parametric Observation Models: Applications to Localization and SLAM", The International Journal of Robotics Research (IJRR), vol. 29, no. 14, 2010

J. Gonzalez-Jimenez, C. Galindo, F. Melendez-Fernandez, J.R. Ruiz-Sarmiento, "Building and Exploiting Maps in a Telepresence Robotic Application", 10th International Conference on Informatics in Control, Automation and Robotics (ICINCO), Reykjavic, Iceland, 2013

E Vargiu, L Ceccaroni, L Subirats, S Martin, and F Miralles. User Profiling of People with Disabilities - A Proposal to Pervasively Assess Quality of Life. In ICAART 2013 - Proceedings of the 5th Int. Conf. on Agents and Artif. Intelli. Vol. 2, J Filipe, ALN Fred (Eds) Barcelona Spain, SciTePress 2013.

Gruber, Thomas R. (June 1993). "A translation approach to portable ontology specifications". Knowledge Acquisition 5 (2): 199–220, 1993.

http://en.wikipedia.org/wiki/Whac-A-Mole

https://www.sticknfind.com/, http://www.thetileapp.com

Berends, Johan H. and Veldhuis, Gerrit J. and Lambeck, Paul V. and Popma, Theo J.A. Device equivalence in integrated optics. Journal of Lightwave Technology, 13 (10). pp. 2082-2086. ISSN 0733-8724, 1995.

http://www.wi-fi.org/wi-fi-certified-miracast%E2%84%A2

Mainetti R, Sedda A, Ronchetti M, Bottini G, Borghese NA. (2013) Duckneglect: video-games based neglect rehabilitation. Technology and Health Care 21 97–111 97. DOI 10.3233/THC-120712 IOS Press.

Rigiroli P, Campadelli P, Pedotti A, Borghese NA (2001), Mesh Refinement with Colour Attributes, Computers & Graphics. Vol 25(3), pp 449-461, 2001.

Pirovano M, Ren CY, Frosio I, Lanzi PL, Prisacariu V, Murray DW, Borghese NA, Robust Silhouette Extraction from Kinect Data, In: Image Analysis and Processing–ICIAP 2013 (pp. 642-651). Springer Berlin Heidelberg, 2013.

Rudin, L. I.; Osher, S.; Fatemi, E. "Nonlinear total variation based noise removal algorithms". Physica D 60: 259–265, 1992

M Pirovano, R Mainetti, E Surer, PL Lanzi and NA Borghese Melding Exercises and Games to Design Effective and Sage Exergames for Rehabilitation,

Mainetti R, Sedda A, Ronchetti M, Bottini G, Borghese NA Duckneglect video-games based neglect rehabilitation. Tech. Health Care 21 97–111 97. 2013.

Pirovano M, Ren CY, Frosio I, Lanzi PL, Prisacariu V, Murray DW, Borghese NA, Robust Silhouette Extraction from Kinect Data, In: Image Analysis and Processing–ICIAP 2013 (pp. 642-651). Springer Berlin Heidelberg, 2013

http://www.tekscan.com/flexiforce.html

http://www.sxt-telemed.it/Products/Protheo/Protheo.aspx

http://www.arduino.cc/

. Frosio, F. Pedersini and N. A. Borghese, Autocalibration of Triaxial MEMS Accelerometers with Automatic Sensor Model Selection, IEEE Sensors Journal, Vol. 2, No. 6, June 2012, pp. 2100-2108.

Vidal E, Thollard F de la Higuera C Casacuberta F Carrasco RC. Probabilistic finite-state machines - part I and II, IEEE Trans. PAMI, 27(7) 1013-1035, 2005

N Eagle and A Pentland, Eigenbehaviors: Identifying Structure in Routine. Proc. Ubicomp 2006.

E. Jacobsen and R. Lyons, The sliding DFT, Signal Processing Magazine vol. 20, issue 2, pp. 74–80 (March 2003).

E.g. http://www.medlab.eu/english/modules/, http://www.casmed.com/files/documents/OEM_SellRev00.pdf

http://www.google.com/patents/US6477394

M. C. González, C. A. Hidalgo, A.-L. Barabási Understanding individual human mobility patterns. Nature 453, 779-782 (2008). Mark S. Handcock and Adrian E. Raftery Model-based clustering for social networks J. R. Statist. Soc. A (2007) 170, Part 2, pp. 301–354.

Takayama, L., Dooley, D. and Ju, W. (2011). Expressing thought: Improving robot readability with animation principles. Proceedings of the IEEE/ACM International Conference on Human-Robot Interaction.

http://www.continuaalliance.org/

http://www.aal-europe.eu/