UOP Interfaces design required discussion and meeting among partners => UOP higher Traveling

Resources required

1. UMIL

- Staff on project: 2 Senior researchers for 23 MM total + 2 Post-docs for 30 MM each + 1 Manager of TTO for 2 MM

- Equipment: 1 robot Giraff: 9.7K

- Travel: 4.5K for project meetings, 4.5K for short visits and development / testing on partners site, 6K for scientific meetings in which to present Robohome2.0 results, 3K for visiting on site and coordination / management activities.

- Subcontracting: External auditing: 3.5K; catering for meetings 1.5K.

2. ORU

- Staff on project:

- Equipment: 1 robot Giraff: 9.7K

- Travel:

- Subcontracting: 3K for external auditing.

3. Giraff Technologies AB

- Staff on project: 15,3MM Senior researchers.

- Equipment: 1 robot Giraff: 9.7K

- Travel: 4.5K for project meetings, 5.5K for short visits and development / testing on partners site.

- Subcontracting: None.

4.University of Plymouth

- Staff on project: 1 PI for 5 MM, 1 Post-doc for 36MM.

- Equipment: 1 robot Giraff: 9.7K

- Travel: 4.5K for project meetings, 11.5K for short visits and development / testing on partners sites.

- Subcontracting: 3K for external auditing; 5K for students projects.

5. SXT Srl - Sistemi per Telemedicina

- Staff on project:

- Equipment:

- Travel:

- Subcontracting:  .

6. Fondazione IRCCS Cà Granda Ospedale Maggiore Policlinico

- Staff on project:

- Equipment: 3 robots Giraff: 29.1K

- Travel:

- Subcontracting:  .

7. Politecnico di Milano

- Staff on project: 2 Senior researchers for 23 MM total + 2 Post-docs for 27 MM each.

- Equipment:

- Travel:

- Subcontracting: External auditing 3.5K; .

8. Fundació Privada Barcelona Digital Centre Tecnològic

- Staff on project:

- Equipment:

- Travel:

- Subcontracting: External auditing, 3.5K; .

9. Servicio Andaluz de Salud

- Staff on project:

- Equipment: 3 robots Giraff: 29.1K

- Travel:

- Subcontracting: 3K for external auditing .

10. Korian

- Staff on project: 1 PI for 10 MM, 1 Junior investigator for 7MM, 1 Junior geriatrist for 13 MM; 1 junior physiotherapist for 13 MM; 1 psychologist for 8 MM; 1 nurse for 3 MM.

- Equipment: None

- Travel: Travel: 4.5K for project meetings, 7.5K for short visits and testing on partners site.

- Subcontracting: None.

11. Signal GeneriX Ltd

- Staff on project:

- Equipment:

- Travel:

- Subcontracting:

12. Unviersity of Malaga

- Staff on project:

- Equipment: 1 robot Giraff: 9.7K

- Travel:

- Subcontracting:  .

13. OREBRO Municipality

- Staff on project:

- Equipment:

- Travel:

- Subcontracting:  .